## Sheet1
شعارات المشروع (Logos) | اسم المشروع (Project Name) | عنوان المستند (Doc Title) | الرقم المرجعي (Ref. No) | تاريخ الإصدار (Date) | المرسل (From) | المستقبل (To) | الموضوع (Subject) | الطقس (Weather) | الحرارة (Temp) | جدول العمالة (Manpower) | جدول المعدات (Equipment) | وصف العمل (Description) | نسبة الإنجاز (Progress %) | المعوقات (Hindrances) | المرفقات (Photos) | تم الإنشاء (Prepared By) | المراجعة (Reviewed By) | الاعتماد (Consultant)
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-002 | 2024-11-02 | Contractor | Consultant | Daily Report - Day 2 | Very Hot | 48C | 119 | 15 | Ongoing: Blockwork at multiple zones. | 0.27% | None | Site_View_2.jpg | Erik Foster | Eng. Abdullah (PM) | Cheryl Martinez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-003 | 2024-11-03 | Contractor | Consultant | Daily Report - Day 3 | Sunny | 30C | 134 | 10 | Ongoing: Plastering at multiple zones. | 0.41% | None | Site_View_3.jpg | Mary Holmes | Eng. Abdullah (PM) | Daniel Lowe
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-004 | 2024-11-04 | Contractor | Consultant | Daily Report - Day 4 | Very Hot | 40C | 141 | 10 | Ongoing: Door Installation at multiple zones. | 0.55% | None | Site_View_4.jpg | James Heath | Eng. Abdullah (PM) | Eric Berger PhD
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-005 | 2024-11-05 | Contractor | Consultant | Daily Report - Day 5 | Sunny | 31C | 97 | 12 | Ongoing: Ceramic Tiling at multiple zones. | 0.68% | None | Site_View_5.jpg | Robin Johnston | Eng. Abdullah (PM) | Rachel Franklin
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-006 | 2024-11-06 | Contractor | Consultant | Daily Report - Day 6 | Very Hot | 45C | 117 | 8 | Ongoing: Gypsum Ceiling at multiple zones. | 0.82% | None | Site_View_6.jpg | Marcus Potter | Eng. Abdullah (PM) | Jane Lewis
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-007 | 2024-11-07 | Contractor | Consultant | Daily Report - Day 7 | Very Hot | 43C | 145 | 19 | Ongoing: Plastering at multiple zones. | 0.96% | None | Site_View_7.jpg | Stacy Kelly | Eng. Abdullah (PM) | Sean Collins
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-009 | 2024-11-09 | Contractor | Consultant | Daily Report - Day 9 | Sunny | 38C | 125 | 17 | Ongoing: Gypsum Ceiling at multiple zones. | 1.23% | None | Site_View_9.jpg | Colin Freeman | Eng. Abdullah (PM) | Joshua Ramos
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-010 | 2024-11-10 | Contractor | Consultant | Daily Report - Day 10 | Sunny | 32C | 147 | 15 | Ongoing: Painting First Coat at multiple zones. | 1.37% | None | Site_View_10.jpg | Sharon Brady | Eng. Abdullah (PM) | Debra Frazier
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-011 | 2024-11-11 | Contractor | Consultant | Daily Report - Day 11 | Very Hot | 42C | 148 | 8 | Ongoing: Painting First Coat at multiple zones. | 1.51% | None | Site_View_11.jpg | Carrie Tyler | Eng. Abdullah (PM) | Nicole Thompson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-012 | 2024-11-12 | Contractor | Consultant | Daily Report - Day 12 | Sunny | 22C | 91 | 11 | Ongoing: Painting First Coat at multiple zones. | 1.64% | None | Site_View_12.jpg | John Valenzuela | Eng. Abdullah (PM) | Johnny Phillips
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-013 | 2024-11-13 | Contractor | Consultant | Daily Report - Day 13 | Sunny | 23C | 117 | 16 | Ongoing: Gypsum Ceiling at multiple zones. | 1.78% | None | Site_View_13.jpg | John Watts | Eng. Abdullah (PM) | James Morton
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-014 | 2024-11-14 | Contractor | Consultant | Daily Report - Day 14 | Very Hot | 45C | 139 | 20 | Ongoing: Painting First Coat at multiple zones. | 1.92% | None | Site_View_14.jpg | Joseph Becker | Eng. Abdullah (PM) | Tammy Hutchinson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-016 | 2024-11-16 | Contractor | Consultant | Daily Report - Day 16 | Very Hot | 44C | 32 | 12 | Ongoing: Door Installation at multiple zones. | 2.19% | None | Site_View_16.jpg | Laura Robinson | Eng. Abdullah (PM) | Sarah Underwood
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-017 | 2024-11-17 | Contractor | Consultant | Daily Report - Day 17 | Sunny | 21C | 91 | 6 | Ongoing: Painting First Coat at multiple zones. | 2.33% | None | Site_View_17.jpg | Carol Sims | Eng. Abdullah (PM) | Benjamin Hicks DDS
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-018 | 2024-11-18 | Contractor | Consultant | Daily Report - Day 18 | Sunny | 36C | 120 | 11 | Ongoing: Gypsum Ceiling at multiple zones. | 2.47% | None | Site_View_18.jpg | Tara Brown | Eng. Abdullah (PM) | James Hill
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-019 | 2024-11-19 | Contractor | Consultant | Daily Report - Day 19 | Sunny | 29C | 31 | 7 | Ongoing: Blockwork at multiple zones. | 2.6% | None | Site_View_19.jpg | Marc Rasmussen | Eng. Abdullah (PM) | Pamela Price
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-020 | 2024-11-20 | Contractor | Consultant | Daily Report - Day 20 | Sunny | 37C | 39 | 10 | Ongoing: Gypsum Ceiling at multiple zones. | 2.74% | None | Site_View_20.jpg | John Carter | Eng. Abdullah (PM) | Carl Owens
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-021 | 2024-11-21 | Contractor | Consultant | Daily Report - Day 21 | Very Hot | 40C | 59 | 6 | Ongoing: Door Installation at multiple zones. | 2.88% | None | Site_View_21.jpg | Sheila Clark | Eng. Abdullah (PM) | Casey Gonzales
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-023 | 2024-11-23 | Contractor | Consultant | Daily Report - Day 23 | Very Hot | 40C | 54 | 16 | Ongoing: Plastering at multiple zones. | 3.15% | None | Site_View_23.jpg | Michelle Cobb | Eng. Abdullah (PM) | James Armstrong
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-024 | 2024-11-24 | Contractor | Consultant | Daily Report - Day 24 | Sunny | 26C | 71 | 16 | Ongoing: Painting First Coat at multiple zones. | 3.29% | None | Site_View_24.jpg | Debra Sullivan | Eng. Abdullah (PM) | Rachael Alvarez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-025 | 2024-11-25 | Contractor | Consultant | Daily Report - Day 25 | Sunny | 38C | 72 | 5 | Ongoing: Ceramic Tiling at multiple zones. | 3.42% | None | Site_View_25.jpg | James Sanders | Eng. Abdullah (PM) | Victoria Cole
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-026 | 2024-11-26 | Contractor | Consultant | Daily Report - Day 26 | Sunny | 36C | 77 | 10 | Ongoing: Ceramic Tiling at multiple zones. | 3.56% | None | Site_View_26.jpg | Brian Cook | Eng. Abdullah (PM) | Shelley Collins
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-027 | 2024-11-27 | Contractor | Consultant | Daily Report - Day 27 | Sunny | 26C | 35 | 6 | Ongoing: Plastering at multiple zones. | 3.7% | Material Delay | Site_View_27.jpg | Emily Nguyen | Eng. Abdullah (PM) | Matthew Dillon
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-028 | 2024-11-28 | Contractor | Consultant | Daily Report - Day 28 | Sunny | 36C | 64 | 6 | Ongoing: Ceramic Tiling at multiple zones. | 3.84% | None | Site_View_28.jpg | Douglas Ryan | Eng. Abdullah (PM) | Michael Johnson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-030 | 2024-11-30 | Contractor | Consultant | Daily Report - Day 30 | Sunny | 29C | 127 | 20 | Ongoing: Blockwork at multiple zones. | 4.11% | None | Site_View_30.jpg | Thomas Gallagher | Eng. Abdullah (PM) | Alexandra Mays
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-031 | 2024-12-01 | Contractor | Consultant | Daily Report - Day 31 | Very Hot | 40C | 89 | 10 | Ongoing: Ceramic Tiling at multiple zones. | 4.25% | None | Site_View_31.jpg | Laurie Ortega | Eng. Abdullah (PM) | Wesley Edwards
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-032 | 2024-12-02 | Contractor | Consultant | Daily Report - Day 32 | Sunny | 27C | 121 | 19 | Ongoing: Plastering at multiple zones. | 4.38% | None | Site_View_32.jpg | Carolyn Zimmerman | Eng. Abdullah (PM) | Terry Ramirez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-033 | 2024-12-03 | Contractor | Consultant | Daily Report - Day 33 | Sunny | 36C | 96 | 12 | Ongoing: Painting First Coat at multiple zones. | 4.52% | None | Site_View_33.jpg | Jennifer Singh | Eng. Abdullah (PM) | Breanna Harris
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-034 | 2024-12-04 | Contractor | Consultant | Daily Report - Day 34 | Very Hot | 44C | 49 | 15 | Ongoing: Door Installation at multiple zones. | 4.66% | None | Site_View_34.jpg | Peter Maxwell | Eng. Abdullah (PM) | Rachel Diaz
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-035 | 2024-12-05 | Contractor | Consultant | Daily Report - Day 35 | Very Hot | 40C | 122 | 14 | Ongoing: Blockwork at multiple zones. | 4.79% | None | Site_View_35.jpg | Danielle Wilson | Eng. Abdullah (PM) | Marissa Davis
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-037 | 2024-12-07 | Contractor | Consultant | Daily Report - Day 37 | Very Hot | 45C | 98 | 15 | Ongoing: Plastering at multiple zones. | 5.07% | None | Site_View_37.jpg | Jennifer Sanders | Eng. Abdullah (PM) | Melissa Robinson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-038 | 2024-12-08 | Contractor | Consultant | Daily Report - Day 38 | Sunny | 30C | 32 | 8 | Ongoing: Painting First Coat at multiple zones. | 5.21% | None | Site_View_38.jpg | Christine Campbell | Eng. Abdullah (PM) | Jessica Gibson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-039 | 2024-12-09 | Contractor | Consultant | Daily Report - Day 39 | Sunny | 37C | 61 | 18 | Ongoing: Door Installation at multiple zones. | 5.34% | None | Site_View_39.jpg | Vanessa Lewis | Eng. Abdullah (PM) | Juan Walker
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-040 | 2024-12-10 | Contractor | Consultant | Daily Report - Day 40 | Sunny | 30C | 145 | 6 | Ongoing: Gypsum Ceiling at multiple zones. | 5.48% | Material Delay | Site_View_40.jpg | Michelle Alvarez | Eng. Abdullah (PM) | Rebecca Wright
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-041 | 2024-12-11 | Contractor | Consultant | Daily Report - Day 41 | Very Hot | 47C | 128 | 15 | Ongoing: Blockwork at multiple zones. | 5.62% | None | Site_View_41.jpg | Michael Martinez | Eng. Abdullah (PM) | Molly Stewart
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-042 | 2024-12-12 | Contractor | Consultant | Daily Report - Day 42 | Very Hot | 47C | 70 | 19 | Ongoing: Plastering at multiple zones. | 5.75% | None | Site_View_42.jpg | Justin Nguyen | Eng. Abdullah (PM) | Joseph Smith
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-044 | 2024-12-14 | Contractor | Consultant | Daily Report - Day 44 | Sunny | 39C | 144 | 11 | Ongoing: Plastering at multiple zones. | 6.03% | None | Site_View_44.jpg | Lori Nichols | Eng. Abdullah (PM) | Damon Carpenter
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-045 | 2024-12-15 | Contractor | Consultant | Daily Report - Day 45 | Very Hot | 45C | 33 | 18 | Ongoing: Ceramic Tiling at multiple zones. | 6.16% | None | Site_View_45.jpg | Brian Tran | Eng. Abdullah (PM) | Frank Williams
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-046 | 2024-12-16 | Contractor | Consultant | Daily Report - Day 46 | Sunny | 22C | 134 | 10 | Ongoing: Plastering at multiple zones. | 6.3% | None | Site_View_46.jpg | Erica Rodriguez | Eng. Abdullah (PM) | Linda Smith
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-047 | 2024-12-17 | Contractor | Consultant | Daily Report - Day 47 | Sunny | 39C | 146 | 5 | Ongoing: Door Installation at multiple zones. | 6.44% | None | Site_View_47.jpg | Charles Hanson | Eng. Abdullah (PM) | Robert Little
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-048 | 2024-12-18 | Contractor | Consultant | Daily Report - Day 48 | Sunny | 25C | 118 | 12 | Ongoing: Painting First Coat at multiple zones. | 6.58% | None | Site_View_48.jpg | Timothy Jacobson | Eng. Abdullah (PM) | Emily Barron
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-049 | 2024-12-19 | Contractor | Consultant | Daily Report - Day 49 | Very Hot | 43C | 79 | 20 | Ongoing: Ceramic Tiling at multiple zones. | 6.71% | None | Site_View_49.jpg | Keith Hanson | Eng. Abdullah (PM) | Christopher Smith
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-051 | 2024-12-21 | Contractor | Consultant | Daily Report - Day 51 | Sunny | 31C | 123 | 9 | Ongoing: Painting First Coat at multiple zones. | 6.99% | Material Delay | Site_View_51.jpg | Joshua Williams | Eng. Abdullah (PM) | Michele Silva
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-052 | 2024-12-22 | Contractor | Consultant | Daily Report - Day 52 | Very Hot | 45C | 80 | 20 | Ongoing: Blockwork at multiple zones. | 7.12% | Material Delay | Site_View_52.jpg | Aaron Garcia | Eng. Abdullah (PM) | Joseph Gray
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-053 | 2024-12-23 | Contractor | Consultant | Daily Report - Day 53 | Very Hot | 44C | 83 | 6 | Ongoing: Ceramic Tiling at multiple zones. | 7.26% | None | Site_View_53.jpg | Matthew Torres | Eng. Abdullah (PM) | Sean Brooks
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-054 | 2024-12-24 | Contractor | Consultant | Daily Report - Day 54 | Sunny | 36C | 89 | 5 | Ongoing: Blockwork at multiple zones. | 7.4% | None | Site_View_54.jpg | Debra Boyd | Eng. Abdullah (PM) | Diane Leonard
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-055 | 2024-12-25 | Contractor | Consultant | Daily Report - Day 55 | Very Hot | 44C | 105 | 11 | Ongoing: Ceramic Tiling at multiple zones. | 7.53% | None | Site_View_55.jpg | Larry Hernandez | Eng. Abdullah (PM) | Michelle Martinez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-056 | 2024-12-26 | Contractor | Consultant | Daily Report - Day 56 | Very Hot | 45C | 64 | 18 | Ongoing: Plastering at multiple zones. | 7.67% | None | Site_View_56.jpg | Laura Conway MD | Eng. Abdullah (PM) | Kim Robinson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-058 | 2024-12-28 | Contractor | Consultant | Daily Report - Day 58 | Sunny | 23C | 45 | 13 | Ongoing: Door Installation at multiple zones. | 7.95% | None | Site_View_58.jpg | Troy Choi | Eng. Abdullah (PM) | Mary Dixon
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-059 | 2024-12-29 | Contractor | Consultant | Daily Report - Day 59 | Sunny | 33C | 47 | 13 | Ongoing: Ceramic Tiling at multiple zones. | 8.08% | None | Site_View_59.jpg | Allison Marshall | Eng. Abdullah (PM) | Todd Stewart
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-060 | 2024-12-30 | Contractor | Consultant | Daily Report - Day 60 | Sunny | 36C | 105 | 14 | Ongoing: Painting First Coat at multiple zones. | 8.22% | None | Site_View_60.jpg | Deborah Chapman | Eng. Abdullah (PM) | Daisy Nguyen
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-061 | 2024-12-31 | Contractor | Consultant | Daily Report - Day 61 | Very Hot | 44C | 88 | 11 | Ongoing: Painting First Coat at multiple zones. | 8.36% | None | Site_View_61.jpg | Laura Phillips | Eng. Abdullah (PM) | Michael Griffin
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-062 | 2025-01-01 | Contractor | Consultant | Daily Report - Day 62 | Sunny | 28C | 63 | 5 | Ongoing: Plastering at multiple zones. | 8.49% | None | Site_View_62.jpg | Susan Morris | Eng. Abdullah (PM) | Bradley Vega
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-063 | 2025-01-02 | Contractor | Consultant | Daily Report - Day 63 | Very Hot | 40C | 84 | 9 | Ongoing: Ceramic Tiling at multiple zones. | 8.63% | None | Site_View_63.jpg | Erika Smith | Eng. Abdullah (PM) | David Austin
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-065 | 2025-01-04 | Contractor | Consultant | Daily Report - Day 65 | Sunny | 34C | 125 | 5 | Ongoing: Painting First Coat at multiple zones. | 8.9% | None | Site_View_65.jpg | Steven Johnson | Eng. Abdullah (PM) | Amanda Manning
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-066 | 2025-01-05 | Contractor | Consultant | Daily Report - Day 66 | Sunny | 35C | 109 | 5 | Ongoing: Plastering at multiple zones. | 9.04% | None | Site_View_66.jpg | Sharon Allen | Eng. Abdullah (PM) | Barbara Sullivan
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-067 | 2025-01-06 | Contractor | Consultant | Daily Report - Day 67 | Very Hot | 41C | 110 | 17 | Ongoing: Plastering at multiple zones. | 9.18% | None | Site_View_67.jpg | John Browning | Eng. Abdullah (PM) | Sara Reynolds
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-068 | 2025-01-07 | Contractor | Consultant | Daily Report - Day 68 | Very Hot | 47C | 40 | 19 | Ongoing: Ceramic Tiling at multiple zones. | 9.32% | None | Site_View_68.jpg | Sara Goodwin | Eng. Abdullah (PM) | Michael Ford
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-069 | 2025-01-08 | Contractor | Consultant | Daily Report - Day 69 | Sunny | 25C | 54 | 8 | Ongoing: Plastering at multiple zones. | 9.45% | None | Site_View_69.jpg | Judy Alvarez | Eng. Abdullah (PM) | Joshua Zamora
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-070 | 2025-01-09 | Contractor | Consultant | Daily Report - Day 70 | Sunny | 24C | 126 | 6 | Ongoing: Ceramic Tiling at multiple zones. | 9.59% | None | Site_View_70.jpg | Lisa Garza | Eng. Abdullah (PM) | Jerry Stanley
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-072 | 2025-01-11 | Contractor | Consultant | Daily Report - Day 72 | Sunny | 22C | 36 | 14 | Ongoing: Door Installation at multiple zones. | 9.86% | None | Site_View_72.jpg | Christine Parks | Eng. Abdullah (PM) | Bradley Brock
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-073 | 2025-01-12 | Contractor | Consultant | Daily Report - Day 73 | Sunny | 31C | 55 | 6 | Ongoing: Plastering at multiple zones. | 10.0% | None | Site_View_73.jpg | Robert Nixon | Eng. Abdullah (PM) | Gregory Sanders
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-074 | 2025-01-13 | Contractor | Consultant | Daily Report - Day 74 | Sunny | 30C | 124 | 13 | Ongoing: Gypsum Ceiling at multiple zones. | 10.14% | Material Delay | Site_View_74.jpg | Kelly Mitchell | Eng. Abdullah (PM) | Savannah Holmes
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-075 | 2025-01-14 | Contractor | Consultant | Daily Report - Day 75 | Sunny | 35C | 124 | 20 | Ongoing: Plastering at multiple zones. | 10.27% | None | Site_View_75.jpg | Monica Lopez DVM | Eng. Abdullah (PM) | Samantha Yates
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-076 | 2025-01-15 | Contractor | Consultant | Daily Report - Day 76 | Very Hot | 43C | 132 | 8 | Ongoing: Ceramic Tiling at multiple zones. | 10.41% | None | Site_View_76.jpg | Anthony Mathews | Eng. Abdullah (PM) | Jeremiah David
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-077 | 2025-01-16 | Contractor | Consultant | Daily Report - Day 77 | Very Hot | 42C | 148 | 6 | Ongoing: Ceramic Tiling at multiple zones. | 10.55% | None | Site_View_77.jpg | David Davis | Eng. Abdullah (PM) | Terri Jones
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-079 | 2025-01-18 | Contractor | Consultant | Daily Report - Day 79 | Sunny | 21C | 37 | 12 | Ongoing: Blockwork at multiple zones. | 10.82% | None | Site_View_79.jpg | William Kelly | Eng. Abdullah (PM) | Wesley Pope
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-080 | 2025-01-19 | Contractor | Consultant | Daily Report - Day 80 | Sunny | 31C | 65 | 8 | Ongoing: Gypsum Ceiling at multiple zones. | 10.96% | None | Site_View_80.jpg | Ronnie Mann | Eng. Abdullah (PM) | Patricia Holland
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-081 | 2025-01-20 | Contractor | Consultant | Daily Report - Day 81 | Sunny | 25C | 83 | 19 | Ongoing: Painting First Coat at multiple zones. | 11.1% | None | Site_View_81.jpg | Nicholas Henderson | Eng. Abdullah (PM) | David Herman
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-082 | 2025-01-21 | Contractor | Consultant | Daily Report - Day 82 | Sunny | 22C | 65 | 16 | Ongoing: Painting First Coat at multiple zones. | 11.23% | Material Delay | Site_View_82.jpg | Michael Brown | Eng. Abdullah (PM) | Kyle Henderson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-083 | 2025-01-22 | Contractor | Consultant | Daily Report - Day 83 | Very Hot | 43C | 114 | 9 | Ongoing: Blockwork at multiple zones. | 11.37% | None | Site_View_83.jpg | Sharon Harper | Eng. Abdullah (PM) | Ashley Green
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-084 | 2025-01-23 | Contractor | Consultant | Daily Report - Day 84 | Sunny | 37C | 126 | 7 | Ongoing: Ceramic Tiling at multiple zones. | 11.51% | Material Delay | Site_View_84.jpg | Kelsey Chambers | Eng. Abdullah (PM) | Steven Perez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-086 | 2025-01-25 | Contractor | Consultant | Daily Report - Day 86 | Very Hot | 47C | 137 | 10 | Ongoing: Gypsum Ceiling at multiple zones. | 11.78% | Material Delay | Site_View_86.jpg | Chelsea Daniel | Eng. Abdullah (PM) | Robin Williams
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-087 | 2025-01-26 | Contractor | Consultant | Daily Report - Day 87 | Sunny | 39C | 95 | 18 | Ongoing: Blockwork at multiple zones. | 11.92% | None | Site_View_87.jpg | Pamela Kelly | Eng. Abdullah (PM) | Adam Wallace
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-088 | 2025-01-27 | Contractor | Consultant | Daily Report - Day 88 | Sunny | 29C | 147 | 19 | Ongoing: Plastering at multiple zones. | 12.05% | None | Site_View_88.jpg | Lance Lewis Jr. | Eng. Abdullah (PM) | Zoe Williams
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-089 | 2025-01-28 | Contractor | Consultant | Daily Report - Day 89 | Sunny | 38C | 36 | 9 | Ongoing: Ceramic Tiling at multiple zones. | 12.19% | Material Delay | Site_View_89.jpg | Michael Johnson | Eng. Abdullah (PM) | Kyle Zamora
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-090 | 2025-01-29 | Contractor | Consultant | Daily Report - Day 90 | Sunny | 28C | 31 | 6 | Ongoing: Gypsum Ceiling at multiple zones. | 12.33% | None | Site_View_90.jpg | Karen Allen | Eng. Abdullah (PM) | Michael Fowler
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-091 | 2025-01-30 | Contractor | Consultant | Daily Report - Day 91 | Very Hot | 43C | 54 | 8 | Ongoing: Gypsum Ceiling at multiple zones. | 12.47% | None | Site_View_91.jpg | Jeremy Marshall | Eng. Abdullah (PM) | Alison Levy
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-093 | 2025-02-01 | Contractor | Consultant | Daily Report - Day 93 | Sunny | 30C | 46 | 9 | Ongoing: Door Installation at multiple zones. | 12.74% | None | Site_View_93.jpg | Christopher Conley | Eng. Abdullah (PM) | Cynthia Mcintyre
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-094 | 2025-02-02 | Contractor | Consultant | Daily Report - Day 94 | Very Hot | 43C | 126 | 19 | Ongoing: Painting First Coat at multiple zones. | 12.88% | Material Delay | Site_View_94.jpg | Tony Jones | Eng. Abdullah (PM) | Shannon Fitzgerald DDS
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-095 | 2025-02-03 | Contractor | Consultant | Daily Report - Day 95 | Sunny | 36C | 66 | 5 | Ongoing: Plastering at multiple zones. | 13.01% | None | Site_View_95.jpg | April Carter | Eng. Abdullah (PM) | Jennifer Miller
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-096 | 2025-02-04 | Contractor | Consultant | Daily Report - Day 96 | Sunny | 30C | 109 | 5 | Ongoing: Door Installation at multiple zones. | 13.15% | None | Site_View_96.jpg | William Washington | Eng. Abdullah (PM) | Matthew Allen
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-097 | 2025-02-05 | Contractor | Consultant | Daily Report - Day 97 | Sunny | 21C | 95 | 17 | Ongoing: Door Installation at multiple zones. | 13.29% | None | Site_View_97.jpg | Michael Chase | Eng. Abdullah (PM) | Jessica Daniels
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-098 | 2025-02-06 | Contractor | Consultant | Daily Report - Day 98 | Very Hot | 41C | 64 | 10 | Ongoing: Ceramic Tiling at multiple zones. | 13.42% | None | Site_View_98.jpg | Jeremy Ramirez | Eng. Abdullah (PM) | Lori Moore
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-100 | 2025-02-08 | Contractor | Consultant | Daily Report - Day 100 | Very Hot | 41C | 44 | 9 | Ongoing: Painting First Coat at multiple zones. | 13.7% | None | Site_View_100.jpg | Christopher Salazar | Eng. Abdullah (PM) | Patricia Meadows
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-101 | 2025-02-09 | Contractor | Consultant | Daily Report - Day 101 | Very Hot | 43C | 113 | 13 | Ongoing: Blockwork at multiple zones. | 13.84% | None | Site_View_101.jpg | John Russo | Eng. Abdullah (PM) | Joe Vincent
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-102 | 2025-02-10 | Contractor | Consultant | Daily Report - Day 102 | Sunny | 28C | 73 | 18 | Ongoing: Door Installation at multiple zones. | 13.97% | None | Site_View_102.jpg | Brooke Wade | Eng. Abdullah (PM) | Christopher Lucas
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-103 | 2025-02-11 | Contractor | Consultant | Daily Report - Day 103 | Sunny | 24C | 55 | 11 | Ongoing: Blockwork at multiple zones. | 14.11% | None | Site_View_103.jpg | Kimberly Simon | Eng. Abdullah (PM) | Mary Thompson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-104 | 2025-02-12 | Contractor | Consultant | Daily Report - Day 104 | Sunny | 39C | 70 | 10 | Ongoing: Painting First Coat at multiple zones. | 14.25% | None | Site_View_104.jpg | Sabrina Davis | Eng. Abdullah (PM) | Emma Andersen
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-105 | 2025-02-13 | Contractor | Consultant | Daily Report - Day 105 | Sunny | 32C | 108 | 20 | Ongoing: Painting First Coat at multiple zones. | 14.38% | None | Site_View_105.jpg | Brianna Dunn | Eng. Abdullah (PM) | Andrea Nguyen
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-107 | 2025-02-15 | Contractor | Consultant | Daily Report - Day 107 | Sunny | 24C | 124 | 7 | Ongoing: Ceramic Tiling at multiple zones. | 14.66% | None | Site_View_107.jpg | Joshua Miller | Eng. Abdullah (PM) | Kevin Adkins
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-108 | 2025-02-16 | Contractor | Consultant | Daily Report - Day 108 | Sunny | 29C | 100 | 14 | Ongoing: Door Installation at multiple zones. | 14.79% | None | Site_View_108.jpg | Brenda Davis | Eng. Abdullah (PM) | Amanda Garcia
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-109 | 2025-02-17 | Contractor | Consultant | Daily Report - Day 109 | Very Hot | 48C | 56 | 7 | Ongoing: Gypsum Ceiling at multiple zones. | 14.93% | None | Site_View_109.jpg | Amanda Robinson | Eng. Abdullah (PM) | Willie Brown
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-110 | 2025-02-18 | Contractor | Consultant | Daily Report - Day 110 | Sunny | 31C | 87 | 10 | Ongoing: Painting First Coat at multiple zones. | 15.07% | Material Delay | Site_View_110.jpg | Tyler Wright | Eng. Abdullah (PM) | David Shaw
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-111 | 2025-02-19 | Contractor | Consultant | Daily Report - Day 111 | Very Hot | 48C | 82 | 19 | Ongoing: Door Installation at multiple zones. | 15.21% | None | Site_View_111.jpg | Nicholas Fleming | Eng. Abdullah (PM) | Michael Mcclure
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-112 | 2025-02-20 | Contractor | Consultant | Daily Report - Day 112 | Very Hot | 47C | 92 | 8 | Ongoing: Plastering at multiple zones. | 15.34% | Material Delay | Site_View_112.jpg | Angela Thompson | Eng. Abdullah (PM) | Tina Lambert
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-114 | 2025-02-22 | Contractor | Consultant | Daily Report - Day 114 | Sunny | 31C | 134 | 12 | Ongoing: Door Installation at multiple zones. | 15.62% | None | Site_View_114.jpg | Michael Ewing | Eng. Abdullah (PM) | Maria Williams
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-115 | 2025-02-23 | Contractor | Consultant | Daily Report - Day 115 | Sunny | 33C | 74 | 8 | Ongoing: Blockwork at multiple zones. | 15.75% | None | Site_View_115.jpg | Tonya Moses | Eng. Abdullah (PM) | Candice Haas
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-116 | 2025-02-24 | Contractor | Consultant | Daily Report - Day 116 | Sunny | 28C | 123 | 18 | Ongoing: Blockwork at multiple zones. | 15.89% | None | Site_View_116.jpg | James Morrison | Eng. Abdullah (PM) | Ashley Gregory
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-117 | 2025-02-25 | Contractor | Consultant | Daily Report - Day 117 | Sunny | 28C | 58 | 5 | Ongoing: Plastering at multiple zones. | 16.03% | None | Site_View_117.jpg | David Armstrong | Eng. Abdullah (PM) | Duane Medina
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-118 | 2025-02-26 | Contractor | Consultant | Daily Report - Day 118 | Sunny | 28C | 30 | 15 | Ongoing: Gypsum Ceiling at multiple zones. | 16.16% | None | Site_View_118.jpg | Kelly Bailey | Eng. Abdullah (PM) | Gabriella Romero
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-119 | 2025-02-27 | Contractor | Consultant | Daily Report - Day 119 | Sunny | 27C | 150 | 14 | Ongoing: Door Installation at multiple zones. | 16.3% | None | Site_View_119.jpg | Emily Brooks | Eng. Abdullah (PM) | Robert Robinson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-121 | 2025-03-01 | Contractor | Consultant | Daily Report - Day 121 | Sunny | 35C | 133 | 20 | Ongoing: Ceramic Tiling at multiple zones. | 16.58% | Material Delay | Site_View_121.jpg | Ryan Murray | Eng. Abdullah (PM) | Angela Cook
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-122 | 2025-03-02 | Contractor | Consultant | Daily Report - Day 122 | Sunny | 29C | 133 | 6 | Ongoing: Gypsum Ceiling at multiple zones. | 16.71% | None | Site_View_122.jpg | Sarah Cook | Eng. Abdullah (PM) | Karen Perez MD
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-123 | 2025-03-03 | Contractor | Consultant | Daily Report - Day 123 | Sunny | 36C | 57 | 16 | Ongoing: Door Installation at multiple zones. | 16.85% | None | Site_View_123.jpg | Katie Tran | Eng. Abdullah (PM) | Angela Christensen
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-124 | 2025-03-04 | Contractor | Consultant | Daily Report - Day 124 | Sunny | 29C | 118 | 8 | Ongoing: Painting First Coat at multiple zones. | 16.99% | None | Site_View_124.jpg | Meghan Scott | Eng. Abdullah (PM) | John Richmond
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-125 | 2025-03-05 | Contractor | Consultant | Daily Report - Day 125 | Very Hot | 43C | 124 | 16 | Ongoing: Painting First Coat at multiple zones. | 17.12% | None | Site_View_125.jpg | Andrew Webb | Eng. Abdullah (PM) | Sean Jenkins
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-126 | 2025-03-06 | Contractor | Consultant | Daily Report - Day 126 | Sunny | 39C | 121 | 10 | Ongoing: Plastering at multiple zones. | 17.26% | None | Site_View_126.jpg | Cynthia Martinez | Eng. Abdullah (PM) | Kelly Thornton
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-128 | 2025-03-08 | Contractor | Consultant | Daily Report - Day 128 | Sunny | 36C | 43 | 11 | Ongoing: Door Installation at multiple zones. | 17.53% | None | Site_View_128.jpg | Courtney Davila | Eng. Abdullah (PM) | Melissa Rich
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-129 | 2025-03-09 | Contractor | Consultant | Daily Report - Day 129 | Very Hot | 45C | 63 | 14 | Ongoing: Gypsum Ceiling at multiple zones. | 17.67% | None | Site_View_129.jpg | Michael Marquez | Eng. Abdullah (PM) | Vanessa Stevens
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-130 | 2025-03-10 | Contractor | Consultant | Daily Report - Day 130 | Very Hot | 41C | 105 | 17 | Ongoing: Ceramic Tiling at multiple zones. | 17.81% | None | Site_View_130.jpg | James Walker Jr. | Eng. Abdullah (PM) | Steven Thornton
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-131 | 2025-03-11 | Contractor | Consultant | Daily Report - Day 131 | Sunny | 26C | 147 | 12 | Ongoing: Door Installation at multiple zones. | 17.95% | None | Site_View_131.jpg | Mary Martinez | Eng. Abdullah (PM) | Andrew Lopez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-132 | 2025-03-12 | Contractor | Consultant | Daily Report - Day 132 | Sunny | 23C | 92 | 18 | Ongoing: Painting First Coat at multiple zones. | 18.08% | None | Site_View_132.jpg | Mrs. Sandra Simpson | Eng. Abdullah (PM) | Monica Gibson DDS
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-133 | 2025-03-13 | Contractor | Consultant | Daily Report - Day 133 | Sunny | 35C | 144 | 5 | Ongoing: Ceramic Tiling at multiple zones. | 18.22% | None | Site_View_133.jpg | Angela Cook | Eng. Abdullah (PM) | Arthur Dickerson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-135 | 2025-03-15 | Contractor | Consultant | Daily Report - Day 135 | Very Hot | 48C | 124 | 14 | Ongoing: Door Installation at multiple zones. | 18.49% | None | Site_View_135.jpg | Anthony Carter | Eng. Abdullah (PM) | Shelia Peterson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-136 | 2025-03-16 | Contractor | Consultant | Daily Report - Day 136 | Sunny | 32C | 36 | 7 | Ongoing: Gypsum Ceiling at multiple zones. | 18.63% | None | Site_View_136.jpg | Katherine Massey | Eng. Abdullah (PM) | Courtney Jones
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-137 | 2025-03-17 | Contractor | Consultant | Daily Report - Day 137 | Sunny | 23C | 99 | 8 | Ongoing: Blockwork at multiple zones. | 18.77% | None | Site_View_137.jpg | Theodore Robbins | Eng. Abdullah (PM) | David Blake
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-138 | 2025-03-18 | Contractor | Consultant | Daily Report - Day 138 | Sunny | 22C | 74 | 20 | Ongoing: Ceramic Tiling at multiple zones. | 18.9% | None | Site_View_138.jpg | Kyle Gordon | Eng. Abdullah (PM) | Ronald Pierce
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-139 | 2025-03-19 | Contractor | Consultant | Daily Report - Day 139 | Sunny | 28C | 54 | 12 | Ongoing: Gypsum Ceiling at multiple zones. | 19.04% | None | Site_View_139.jpg | Lawrence Ramsey | Eng. Abdullah (PM) | Jason Rasmussen
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-140 | 2025-03-20 | Contractor | Consultant | Daily Report - Day 140 | Sunny | 21C | 97 | 14 | Ongoing: Painting First Coat at multiple zones. | 19.18% | None | Site_View_140.jpg | Ricardo Lloyd | Eng. Abdullah (PM) | Melissa Singleton
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-142 | 2025-03-22 | Contractor | Consultant | Daily Report - Day 142 | Very Hot | 43C | 110 | 19 | Ongoing: Blockwork at multiple zones. | 19.45% | None | Site_View_142.jpg | Taylor Lynn | Eng. Abdullah (PM) | Gregory Collins
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-143 | 2025-03-23 | Contractor | Consultant | Daily Report - Day 143 | Very Hot | 40C | 107 | 8 | Ongoing: Ceramic Tiling at multiple zones. | 19.59% | None | Site_View_143.jpg | Adam Wood | Eng. Abdullah (PM) | Wesley Young
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-144 | 2025-03-24 | Contractor | Consultant | Daily Report - Day 144 | Sunny | 30C | 96 | 15 | Ongoing: Blockwork at multiple zones. | 19.73% | None | Site_View_144.jpg | Brian Watkins | Eng. Abdullah (PM) | Barbara Brown
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-145 | 2025-03-25 | Contractor | Consultant | Daily Report - Day 145 | Sunny | 38C | 95 | 19 | Ongoing: Door Installation at multiple zones. | 19.86% | None | Site_View_145.jpg | Jared Fitzgerald | Eng. Abdullah (PM) | Patricia Reynolds
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-146 | 2025-03-26 | Contractor | Consultant | Daily Report - Day 146 | Sunny | 33C | 41 | 16 | Ongoing: Plastering at multiple zones. | 20.0% | None | Site_View_146.jpg | Heather Turner | Eng. Abdullah (PM) | Ashley Fischer
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-147 | 2025-03-27 | Contractor | Consultant | Daily Report - Day 147 | Sunny | 33C | 52 | 19 | Ongoing: Ceramic Tiling at multiple zones. | 20.14% | None | Site_View_147.jpg | Joshua Freeman | Eng. Abdullah (PM) | Krista Medina
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-149 | 2025-03-29 | Contractor | Consultant | Daily Report - Day 149 | Sunny | 23C | 75 | 17 | Ongoing: Blockwork at multiple zones. | 20.41% | None | Site_View_149.jpg | Erin Manning | Eng. Abdullah (PM) | Shannon Rivera
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-150 | 2025-03-30 | Contractor | Consultant | Daily Report - Day 150 | Sunny | 23C | 95 | 11 | Ongoing: Ceramic Tiling at multiple zones. | 20.55% | None | Site_View_150.jpg | Lucas Parker | Eng. Abdullah (PM) | Joseph Clarke
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-151 | 2025-03-31 | Contractor | Consultant | Daily Report - Day 151 | Sunny | 20C | 124 | 17 | Ongoing: Ceramic Tiling at multiple zones. | 20.68% | None | Site_View_151.jpg | Michelle Powers | Eng. Abdullah (PM) | Marcus Gray
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-152 | 2025-04-01 | Contractor | Consultant | Daily Report - Day 152 | Sunny | 30C | 61 | 20 | Ongoing: Blockwork at multiple zones. | 20.82% | None | Site_View_152.jpg | Heather Rivera | Eng. Abdullah (PM) | Barbara Morales
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-153 | 2025-04-02 | Contractor | Consultant | Daily Report - Day 153 | Very Hot | 45C | 143 | 18 | Ongoing: Plastering at multiple zones. | 20.96% | None | Site_View_153.jpg | Patrick Williams | Eng. Abdullah (PM) | David Hanna
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-154 | 2025-04-03 | Contractor | Consultant | Daily Report - Day 154 | Very Hot | 47C | 57 | 20 | Ongoing: Plastering at multiple zones. | 21.1% | None | Site_View_154.jpg | Leslie Barnett | Eng. Abdullah (PM) | Emily Diaz
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-156 | 2025-04-05 | Contractor | Consultant | Daily Report - Day 156 | Very Hot | 45C | 135 | 13 | Ongoing: Door Installation at multiple zones. | 21.37% | None | Site_View_156.jpg | Susan Davis | Eng. Abdullah (PM) | Emily Leach
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-157 | 2025-04-06 | Contractor | Consultant | Daily Report - Day 157 | Sunny | 28C | 122 | 17 | Ongoing: Gypsum Ceiling at multiple zones. | 21.51% | None | Site_View_157.jpg | Derek Abbott | Eng. Abdullah (PM) | Janet Hoffman
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-158 | 2025-04-07 | Contractor | Consultant | Daily Report - Day 158 | Very Hot | 42C | 108 | 19 | Ongoing: Door Installation at multiple zones. | 21.64% | None | Site_View_158.jpg | Christina Morgan | Eng. Abdullah (PM) | James Williams DVM
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-159 | 2025-04-08 | Contractor | Consultant | Daily Report - Day 159 | Sunny | 29C | 96 | 6 | Ongoing: Plastering at multiple zones. | 21.78% | None | Site_View_159.jpg | Margaret Barnes | Eng. Abdullah (PM) | Derrick Anderson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-160 | 2025-04-09 | Contractor | Consultant | Daily Report - Day 160 | Very Hot | 40C | 73 | 19 | Ongoing: Ceramic Tiling at multiple zones. | 21.92% | Material Delay | Site_View_160.jpg | Jenny Barry | Eng. Abdullah (PM) | Steven Curtis
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-161 | 2025-04-10 | Contractor | Consultant | Daily Report - Day 161 | Sunny | 34C | 108 | 13 | Ongoing: Gypsum Ceiling at multiple zones. | 22.05% | None | Site_View_161.jpg | Tamara Holt | Eng. Abdullah (PM) | Kenneth Harris
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-163 | 2025-04-12 | Contractor | Consultant | Daily Report - Day 163 | Sunny | 22C | 85 | 12 | Ongoing: Plastering at multiple zones. | 22.33% | None | Site_View_163.jpg | Kara Snyder | Eng. Abdullah (PM) | Alexander Foster
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-164 | 2025-04-13 | Contractor | Consultant | Daily Report - Day 164 | Sunny | 33C | 128 | 20 | Ongoing: Painting First Coat at multiple zones. | 22.47% | None | Site_View_164.jpg | Kelly Cole | Eng. Abdullah (PM) | Daniel Walton
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-165 | 2025-04-14 | Contractor | Consultant | Daily Report - Day 165 | Sunny | 30C | 146 | 6 | Ongoing: Plastering at multiple zones. | 22.6% | None | Site_View_165.jpg | Theresa Smith | Eng. Abdullah (PM) | Kyle Richardson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-166 | 2025-04-15 | Contractor | Consultant | Daily Report - Day 166 | Very Hot | 46C | 109 | 19 | Ongoing: Door Installation at multiple zones. | 22.74% | None | Site_View_166.jpg | Amy Jackson | Eng. Abdullah (PM) | Ana Roberts
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-167 | 2025-04-16 | Contractor | Consultant | Daily Report - Day 167 | Sunny | 20C | 94 | 7 | Ongoing: Gypsum Ceiling at multiple zones. | 22.88% | None | Site_View_167.jpg | Patrick Cruz | Eng. Abdullah (PM) | Jamie Smith
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-168 | 2025-04-17 | Contractor | Consultant | Daily Report - Day 168 | Very Hot | 43C | 137 | 16 | Ongoing: Gypsum Ceiling at multiple zones. | 23.01% | Material Delay | Site_View_168.jpg | Corey Hernandez | Eng. Abdullah (PM) | Sarah Ballard
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-170 | 2025-04-19 | Contractor | Consultant | Daily Report - Day 170 | Very Hot | 40C | 92 | 7 | Ongoing: Plastering at multiple zones. | 23.29% | None | Site_View_170.jpg | Valerie Morrow | Eng. Abdullah (PM) | Joshua Hughes
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-171 | 2025-04-20 | Contractor | Consultant | Daily Report - Day 171 | Very Hot | 47C | 89 | 16 | Ongoing: Blockwork at multiple zones. | 23.42% | None | Site_View_171.jpg | Christopher Leach | Eng. Abdullah (PM) | Samantha Wilson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-172 | 2025-04-21 | Contractor | Consultant | Daily Report - Day 172 | Sunny | 24C | 51 | 9 | Ongoing: Plastering at multiple zones. | 23.56% | None | Site_View_172.jpg | Joseph Blair | Eng. Abdullah (PM) | Anthony Klein
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-173 | 2025-04-22 | Contractor | Consultant | Daily Report - Day 173 | Sunny | 34C | 37 | 9 | Ongoing: Ceramic Tiling at multiple zones. | 23.7% | None | Site_View_173.jpg | Michael Brown | Eng. Abdullah (PM) | Sara Simmons
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-174 | 2025-04-23 | Contractor | Consultant | Daily Report - Day 174 | Sunny | 23C | 72 | 19 | Ongoing: Plastering at multiple zones. | 23.84% | None | Site_View_174.jpg | Rebecca Ibarra | Eng. Abdullah (PM) | Edward Simon
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-175 | 2025-04-24 | Contractor | Consultant | Daily Report - Day 175 | Sunny | 26C | 84 | 11 | Ongoing: Door Installation at multiple zones. | 23.97% | Material Delay | Site_View_175.jpg | Shannon Guzman | Eng. Abdullah (PM) | Anne Mitchell
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-177 | 2025-04-26 | Contractor | Consultant | Daily Report - Day 177 | Very Hot | 44C | 114 | 16 | Ongoing: Blockwork at multiple zones. | 24.25% | None | Site_View_177.jpg | Kenneth Gordon | Eng. Abdullah (PM) | Michael Donovan
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-178 | 2025-04-27 | Contractor | Consultant | Daily Report - Day 178 | Sunny | 33C | 49 | 9 | Ongoing: Plastering at multiple zones. | 24.38% | None | Site_View_178.jpg | Michael Williams | Eng. Abdullah (PM) | William Dean
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-179 | 2025-04-28 | Contractor | Consultant | Daily Report - Day 179 | Sunny | 33C | 58 | 17 | Ongoing: Gypsum Ceiling at multiple zones. | 24.52% | None | Site_View_179.jpg | Jerry Wheeler | Eng. Abdullah (PM) | Tyrone Palmer DDS
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-180 | 2025-04-29 | Contractor | Consultant | Daily Report - Day 180 | Very Hot | 42C | 101 | 19 | Ongoing: Plastering at multiple zones. | 24.66% | None | Site_View_180.jpg | Ivan Porter | Eng. Abdullah (PM) | Susan Williams
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-181 | 2025-04-30 | Contractor | Consultant | Daily Report - Day 181 | Sunny | 36C | 125 | 6 | Ongoing: Painting First Coat at multiple zones. | 24.79% | None | Site_View_181.jpg | Maria Duarte | Eng. Abdullah (PM) | Amy Watkins
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-182 | 2025-05-01 | Contractor | Consultant | Daily Report - Day 182 | Very Hot | 42C | 67 | 9 | Ongoing: Ceramic Tiling at multiple zones. | 24.93% | None | Site_View_182.jpg | William Hancock | Eng. Abdullah (PM) | Kerry Carpenter MD
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-184 | 2025-05-03 | Contractor | Consultant | Daily Report - Day 184 | Sunny | 21C | 50 | 14 | Ongoing: Painting First Coat at multiple zones. | 25.21% | Material Delay | Site_View_184.jpg | Philip Mcdowell | Eng. Abdullah (PM) | Sarah Fry
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-185 | 2025-05-04 | Contractor | Consultant | Daily Report - Day 185 | Sunny | 29C | 133 | 14 | Ongoing: Gypsum Ceiling at multiple zones. | 25.34% | None | Site_View_185.jpg | Lisa Williams | Eng. Abdullah (PM) | Paula Miller
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-186 | 2025-05-05 | Contractor | Consultant | Daily Report - Day 186 | Sunny | 31C | 85 | 17 | Ongoing: Gypsum Ceiling at multiple zones. | 25.48% | None | Site_View_186.jpg | Christina Scott | Eng. Abdullah (PM) | Jeffery Gilbert
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-187 | 2025-05-06 | Contractor | Consultant | Daily Report - Day 187 | Sunny | 20C | 54 | 5 | Ongoing: Plastering at multiple zones. | 25.62% | None | Site_View_187.jpg | Craig Gallagher | Eng. Abdullah (PM) | Nichole Mckinney
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-188 | 2025-05-07 | Contractor | Consultant | Daily Report - Day 188 | Sunny | 26C | 44 | 16 | Ongoing: Blockwork at multiple zones. | 25.75% | Material Delay | Site_View_188.jpg | Donald Rose | Eng. Abdullah (PM) | Amy Martinez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-189 | 2025-05-08 | Contractor | Consultant | Daily Report - Day 189 | Sunny | 27C | 119 | 8 | Ongoing: Painting First Coat at multiple zones. | 25.89% | None | Site_View_189.jpg | Kimberly Harper | Eng. Abdullah (PM) | Rachel Armstrong
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-191 | 2025-05-10 | Contractor | Consultant | Daily Report - Day 191 | Sunny | 23C | 88 | 12 | Ongoing: Painting First Coat at multiple zones. | 26.16% | Material Delay | Site_View_191.jpg | Deborah Sanders | Eng. Abdullah (PM) | Jessica Singleton DDS
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-192 | 2025-05-11 | Contractor | Consultant | Daily Report - Day 192 | Very Hot | 42C | 68 | 13 | Ongoing: Ceramic Tiling at multiple zones. | 26.3% | None | Site_View_192.jpg | Christina Watts | Eng. Abdullah (PM) | Carolyn Jennings
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-193 | 2025-05-12 | Contractor | Consultant | Daily Report - Day 193 | Very Hot | 47C | 41 | 14 | Ongoing: Ceramic Tiling at multiple zones. | 26.44% | Material Delay | Site_View_193.jpg | Theodore Richards | Eng. Abdullah (PM) | John Ingram
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-194 | 2025-05-13 | Contractor | Consultant | Daily Report - Day 194 | Very Hot | 41C | 39 | 14 | Ongoing: Door Installation at multiple zones. | 26.58% | None | Site_View_194.jpg | Jordan Berry | Eng. Abdullah (PM) | Steven Perry
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-195 | 2025-05-14 | Contractor | Consultant | Daily Report - Day 195 | Sunny | 31C | 70 | 18 | Ongoing: Painting First Coat at multiple zones. | 26.71% | None | Site_View_195.jpg | Clinton Huynh | Eng. Abdullah (PM) | Anthony Ryan
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-196 | 2025-05-15 | Contractor | Consultant | Daily Report - Day 196 | Very Hot | 41C | 78 | 15 | Ongoing: Plastering at multiple zones. | 26.85% | None | Site_View_196.jpg | Jamie Burke | Eng. Abdullah (PM) | David Rojas
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-198 | 2025-05-17 | Contractor | Consultant | Daily Report - Day 198 | Sunny | 36C | 87 | 5 | Ongoing: Door Installation at multiple zones. | 27.12% | None | Site_View_198.jpg | Kyle Fuller | Eng. Abdullah (PM) | Anthony May
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-199 | 2025-05-18 | Contractor | Consultant | Daily Report - Day 199 | Sunny | 35C | 95 | 13 | Ongoing: Gypsum Ceiling at multiple zones. | 27.26% | None | Site_View_199.jpg | Janet Garcia | Eng. Abdullah (PM) | Gregory Sheppard Jr.
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-200 | 2025-05-19 | Contractor | Consultant | Daily Report - Day 200 | Sunny | 23C | 143 | 19 | Ongoing: Door Installation at multiple zones. | 27.4% | None | Site_View_200.jpg | Caitlin Schultz | Eng. Abdullah (PM) | Jeffrey Wells
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-201 | 2025-05-20 | Contractor | Consultant | Daily Report - Day 201 | Very Hot | 45C | 90 | 5 | Ongoing: Gypsum Ceiling at multiple zones. | 27.53% | None | Site_View_201.jpg | Kimberly King | Eng. Abdullah (PM) | John Holmes
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-202 | 2025-05-21 | Contractor | Consultant | Daily Report - Day 202 | Very Hot | 47C | 115 | 6 | Ongoing: Painting First Coat at multiple zones. | 27.67% | None | Site_View_202.jpg | Colin Smith | Eng. Abdullah (PM) | Nicholas Simpson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-203 | 2025-05-22 | Contractor | Consultant | Daily Report - Day 203 | Sunny | 20C | 48 | 7 | Ongoing: Door Installation at multiple zones. | 27.81% | None | Site_View_203.jpg | Barry Rogers | Eng. Abdullah (PM) | Erica Floyd
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-205 | 2025-05-24 | Contractor | Consultant | Daily Report - Day 205 | Sunny | 37C | 91 | 9 | Ongoing: Painting First Coat at multiple zones. | 28.08% | Material Delay | Site_View_205.jpg | Terry Lopez | Eng. Abdullah (PM) | Harold Rhodes
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-206 | 2025-05-25 | Contractor | Consultant | Daily Report - Day 206 | Sunny | 30C | 42 | 18 | Ongoing: Ceramic Tiling at multiple zones. | 28.22% | Material Delay | Site_View_206.jpg | Jasmine Warner | Eng. Abdullah (PM) | Rachel Wheeler
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-207 | 2025-05-26 | Contractor | Consultant | Daily Report - Day 207 | Sunny | 31C | 126 | 8 | Ongoing: Blockwork at multiple zones. | 28.36% | Material Delay | Site_View_207.jpg | Steven Smith | Eng. Abdullah (PM) | Shannon Deleon
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-208 | 2025-05-27 | Contractor | Consultant | Daily Report - Day 208 | Sunny | 27C | 51 | 13 | Ongoing: Painting First Coat at multiple zones. | 28.49% | Material Delay | Site_View_208.jpg | Patrick Johnson | Eng. Abdullah (PM) | Angela Gonzales
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-209 | 2025-05-28 | Contractor | Consultant | Daily Report - Day 209 | Very Hot | 41C | 111 | 7 | Ongoing: Blockwork at multiple zones. | 28.63% | None | Site_View_209.jpg | Kurt Murphy | Eng. Abdullah (PM) | Kathleen Garcia
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-210 | 2025-05-29 | Contractor | Consultant | Daily Report - Day 210 | Sunny | 30C | 80 | 8 | Ongoing: Plastering at multiple zones. | 28.77% | None | Site_View_210.jpg | Kevin White | Eng. Abdullah (PM) | Jordan Gordon
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-212 | 2025-05-31 | Contractor | Consultant | Daily Report - Day 212 | Sunny | 37C | 134 | 15 | Ongoing: Gypsum Ceiling at multiple zones. | 29.04% | None | Site_View_212.jpg | Kyle Lane | Eng. Abdullah (PM) | Michael Larsen
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-213 | 2025-06-01 | Contractor | Consultant | Daily Report - Day 213 | Sunny | 33C | 141 | 13 | Ongoing: Gypsum Ceiling at multiple zones. | 29.18% | None | Site_View_213.jpg | Andrea Keller | Eng. Abdullah (PM) | Tiffany Bradley
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-214 | 2025-06-02 | Contractor | Consultant | Daily Report - Day 214 | Sunny | 21C | 43 | 15 | Ongoing: Blockwork at multiple zones. | 29.32% | Material Delay | Site_View_214.jpg | Brenda Davis | Eng. Abdullah (PM) | Dana Monroe
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-215 | 2025-06-03 | Contractor | Consultant | Daily Report - Day 215 | Very Hot | 40C | 83 | 10 | Ongoing: Gypsum Ceiling at multiple zones. | 29.45% | None | Site_View_215.jpg | David Griffin | Eng. Abdullah (PM) | Jordan Clark
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-216 | 2025-06-04 | Contractor | Consultant | Daily Report - Day 216 | Sunny | 20C | 110 | 19 | Ongoing: Painting First Coat at multiple zones. | 29.59% | None | Site_View_216.jpg | Molly Burns | Eng. Abdullah (PM) | Jennifer Diaz
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-217 | 2025-06-05 | Contractor | Consultant | Daily Report - Day 217 | Sunny | 21C | 31 | 11 | Ongoing: Blockwork at multiple zones. | 29.73% | None | Site_View_217.jpg | Kelsey Phillips | Eng. Abdullah (PM) | Jesse Dean
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-219 | 2025-06-07 | Contractor | Consultant | Daily Report - Day 219 | Sunny | 21C | 52 | 19 | Ongoing: Door Installation at multiple zones. | 30.0% | None | Site_View_219.jpg | Abigail Fletcher | Eng. Abdullah (PM) | Logan Kelly
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-220 | 2025-06-08 | Contractor | Consultant | Daily Report - Day 220 | Sunny | 32C | 38 | 5 | Ongoing: Painting First Coat at multiple zones. | 30.14% | None | Site_View_220.jpg | Christopher Klein | Eng. Abdullah (PM) | Lori Hernandez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-221 | 2025-06-09 | Contractor | Consultant | Daily Report - Day 221 | Sunny | 29C | 36 | 9 | Ongoing: Plastering at multiple zones. | 30.27% | None | Site_View_221.jpg | Mary Peterson | Eng. Abdullah (PM) | Gary Frederick
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-222 | 2025-06-10 | Contractor | Consultant | Daily Report - Day 222 | Sunny | 27C | 91 | 19 | Ongoing: Plastering at multiple zones. | 30.41% | None | Site_View_222.jpg | Christopher Williamson | Eng. Abdullah (PM) | Angelica Rice
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-223 | 2025-06-11 | Contractor | Consultant | Daily Report - Day 223 | Sunny | 20C | 41 | 17 | Ongoing: Plastering at multiple zones. | 30.55% | Material Delay | Site_View_223.jpg | Jessica Garcia | Eng. Abdullah (PM) | David Moore
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-224 | 2025-06-12 | Contractor | Consultant | Daily Report - Day 224 | Very Hot | 48C | 69 | 9 | Ongoing: Door Installation at multiple zones. | 30.68% | None | Site_View_224.jpg | Brian Warner | Eng. Abdullah (PM) | Rebecca Garcia
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-226 | 2025-06-14 | Contractor | Consultant | Daily Report - Day 226 | Very Hot | 42C | 109 | 13 | Ongoing: Door Installation at multiple zones. | 30.96% | None | Site_View_226.jpg | Richard Garcia | Eng. Abdullah (PM) | Brooke Williams DDS
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-227 | 2025-06-15 | Contractor | Consultant | Daily Report - Day 227 | Very Hot | 40C | 30 | 19 | Ongoing: Painting First Coat at multiple zones. | 31.1% | None | Site_View_227.jpg | Kelly Hill | Eng. Abdullah (PM) | Mason Fox
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-228 | 2025-06-16 | Contractor | Consultant | Daily Report - Day 228 | Sunny | 21C | 100 | 13 | Ongoing: Plastering at multiple zones. | 31.23% | None | Site_View_228.jpg | Nicholas Jackson | Eng. Abdullah (PM) | Joshua Long
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-229 | 2025-06-17 | Contractor | Consultant | Daily Report - Day 229 | Sunny | 37C | 89 | 19 | Ongoing: Plastering at multiple zones. | 31.37% | None | Site_View_229.jpg | Mary Gonzalez | Eng. Abdullah (PM) | Stephanie Lopez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-230 | 2025-06-18 | Contractor | Consultant | Daily Report - Day 230 | Sunny | 30C | 78 | 10 | Ongoing: Plastering at multiple zones. | 31.51% | None | Site_View_230.jpg | Ruben Huynh | Eng. Abdullah (PM) | Whitney Payne
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-231 | 2025-06-19 | Contractor | Consultant | Daily Report - Day 231 | Sunny | 31C | 52 | 16 | Ongoing: Painting First Coat at multiple zones. | 31.64% | None | Site_View_231.jpg | Danielle Olsen | Eng. Abdullah (PM) | Gabriel Weber
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-233 | 2025-06-21 | Contractor | Consultant | Daily Report - Day 233 | Very Hot | 44C | 75 | 5 | Ongoing: Door Installation at multiple zones. | 31.92% | None | Site_View_233.jpg | Timothy Booth | Eng. Abdullah (PM) | Donald Roberts
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-234 | 2025-06-22 | Contractor | Consultant | Daily Report - Day 234 | Sunny | 31C | 37 | 9 | Ongoing: Gypsum Ceiling at multiple zones. | 32.05% | None | Site_View_234.jpg | Mark Berger | Eng. Abdullah (PM) | Rebecca Davis
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-235 | 2025-06-23 | Contractor | Consultant | Daily Report - Day 235 | Very Hot | 48C | 139 | 6 | Ongoing: Plastering at multiple zones. | 32.19% | None | Site_View_235.jpg | Jeremiah Galvan | Eng. Abdullah (PM) | Tracy Benson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-236 | 2025-06-24 | Contractor | Consultant | Daily Report - Day 236 | Sunny | 20C | 141 | 20 | Ongoing: Plastering at multiple zones. | 32.33% | Material Delay | Site_View_236.jpg | Daniel Snyder | Eng. Abdullah (PM) | James Tucker
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-237 | 2025-06-25 | Contractor | Consultant | Daily Report - Day 237 | Very Hot | 47C | 57 | 18 | Ongoing: Gypsum Ceiling at multiple zones. | 32.47% | None | Site_View_237.jpg | Donald Martin | Eng. Abdullah (PM) | Michael Henry
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-238 | 2025-06-26 | Contractor | Consultant | Daily Report - Day 238 | Sunny | 34C | 89 | 17 | Ongoing: Plastering at multiple zones. | 32.6% | Material Delay | Site_View_238.jpg | Sean James | Eng. Abdullah (PM) | Elizabeth Wood
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-240 | 2025-06-28 | Contractor | Consultant | Daily Report - Day 240 | Sunny | 23C | 104 | 11 | Ongoing: Painting First Coat at multiple zones. | 32.88% | None | Site_View_240.jpg | Ronald Perez | Eng. Abdullah (PM) | Robin Hogan MD
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-241 | 2025-06-29 | Contractor | Consultant | Daily Report - Day 241 | Sunny | 34C | 117 | 15 | Ongoing: Door Installation at multiple zones. | 33.01% | None | Site_View_241.jpg | Vincent Miller | Eng. Abdullah (PM) | Casey Mitchell
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-242 | 2025-06-30 | Contractor | Consultant | Daily Report - Day 242 | Sunny | 26C | 65 | 6 | Ongoing: Gypsum Ceiling at multiple zones. | 33.15% | None | Site_View_242.jpg | John Cruz | Eng. Abdullah (PM) | Derrick Washington
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-243 | 2025-07-01 | Contractor | Consultant | Daily Report - Day 243 | Very Hot | 42C | 106 | 8 | Ongoing: Blockwork at multiple zones. | 33.29% | None | Site_View_243.jpg | Victoria White | Eng. Abdullah (PM) | Derrick George
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-244 | 2025-07-02 | Contractor | Consultant | Daily Report - Day 244 | Very Hot | 44C | 71 | 7 | Ongoing: Ceramic Tiling at multiple zones. | 33.42% | None | Site_View_244.jpg | Natalie Gonzales | Eng. Abdullah (PM) | Kenneth Wilkins
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-245 | 2025-07-03 | Contractor | Consultant | Daily Report - Day 245 | Sunny | 27C | 88 | 20 | Ongoing: Ceramic Tiling at multiple zones. | 33.56% | None | Site_View_245.jpg | Donald Vazquez | Eng. Abdullah (PM) | Matthew Cole
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-247 | 2025-07-05 | Contractor | Consultant | Daily Report - Day 247 | Very Hot | 46C | 106 | 18 | Ongoing: Blockwork at multiple zones. | 33.84% | None | Site_View_247.jpg | Brian Andrews | Eng. Abdullah (PM) | Kelly Welch
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-248 | 2025-07-06 | Contractor | Consultant | Daily Report - Day 248 | Sunny | 25C | 42 | 7 | Ongoing: Blockwork at multiple zones. | 33.97% | None | Site_View_248.jpg | Blake Berger | Eng. Abdullah (PM) | Jeff Schmidt
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-249 | 2025-07-07 | Contractor | Consultant | Daily Report - Day 249 | Very Hot | 41C | 125 | 12 | Ongoing: Ceramic Tiling at multiple zones. | 34.11% | None | Site_View_249.jpg | Elizabeth Ross | Eng. Abdullah (PM) | Steven Harris
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-250 | 2025-07-08 | Contractor | Consultant | Daily Report - Day 250 | Sunny | 34C | 43 | 18 | Ongoing: Painting First Coat at multiple zones. | 34.25% | None | Site_View_250.jpg | Yvonne Smith | Eng. Abdullah (PM) | James Anderson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-251 | 2025-07-09 | Contractor | Consultant | Daily Report - Day 251 | Sunny | 30C | 81 | 15 | Ongoing: Ceramic Tiling at multiple zones. | 34.38% | None | Site_View_251.jpg | Brandy Herman | Eng. Abdullah (PM) | Jessica Baker
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-252 | 2025-07-10 | Contractor | Consultant | Daily Report - Day 252 | Very Hot | 48C | 62 | 8 | Ongoing: Painting First Coat at multiple zones. | 34.52% | None | Site_View_252.jpg | Thomas Aguirre | Eng. Abdullah (PM) | Anthony Lucas
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-254 | 2025-07-12 | Contractor | Consultant | Daily Report - Day 254 | Sunny | 28C | 92 | 6 | Ongoing: Gypsum Ceiling at multiple zones. | 34.79% | None | Site_View_254.jpg | Diana Cox | Eng. Abdullah (PM) | Dawn Mason
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-255 | 2025-07-13 | Contractor | Consultant | Daily Report - Day 255 | Sunny | 38C | 93 | 11 | Ongoing: Painting First Coat at multiple zones. | 34.93% | None | Site_View_255.jpg | David Walker | Eng. Abdullah (PM) | Tyler Mckenzie
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-256 | 2025-07-14 | Contractor | Consultant | Daily Report - Day 256 | Sunny | 29C | 36 | 8 | Ongoing: Blockwork at multiple zones. | 35.07% | None | Site_View_256.jpg | Dean Allison | Eng. Abdullah (PM) | Daniel Martin
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-257 | 2025-07-15 | Contractor | Consultant | Daily Report - Day 257 | Sunny | 35C | 80 | 7 | Ongoing: Plastering at multiple zones. | 35.21% | Material Delay | Site_View_257.jpg | Krystal Black | Eng. Abdullah (PM) | Joseph Sanchez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-258 | 2025-07-16 | Contractor | Consultant | Daily Report - Day 258 | Sunny | 31C | 31 | 10 | Ongoing: Painting First Coat at multiple zones. | 35.34% | None | Site_View_258.jpg | Bryan Sosa | Eng. Abdullah (PM) | Joshua Kennedy
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-259 | 2025-07-17 | Contractor | Consultant | Daily Report - Day 259 | Sunny | 31C | 50 | 15 | Ongoing: Ceramic Tiling at multiple zones. | 35.48% | Material Delay | Site_View_259.jpg | Lori Cross | Eng. Abdullah (PM) | Latoya Christensen
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-261 | 2025-07-19 | Contractor | Consultant | Daily Report - Day 261 | Very Hot | 45C | 73 | 16 | Ongoing: Ceramic Tiling at multiple zones. | 35.75% | None | Site_View_261.jpg | Paul Lopez | Eng. Abdullah (PM) | Julie Blair
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-262 | 2025-07-20 | Contractor | Consultant | Daily Report - Day 262 | Sunny | 36C | 102 | 9 | Ongoing: Gypsum Ceiling at multiple zones. | 35.89% | None | Site_View_262.jpg | Scott Nelson | Eng. Abdullah (PM) | Tracy Hunt
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-263 | 2025-07-21 | Contractor | Consultant | Daily Report - Day 263 | Very Hot | 46C | 115 | 7 | Ongoing: Gypsum Ceiling at multiple zones. | 36.03% | None | Site_View_263.jpg | Alan Kline | Eng. Abdullah (PM) | Samantha Jordan
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-264 | 2025-07-22 | Contractor | Consultant | Daily Report - Day 264 | Sunny | 28C | 85 | 10 | Ongoing: Painting First Coat at multiple zones. | 36.16% | None | Site_View_264.jpg | Bryan Coleman | Eng. Abdullah (PM) | Steven Johnston
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-265 | 2025-07-23 | Contractor | Consultant | Daily Report - Day 265 | Sunny | 39C | 41 | 7 | Ongoing: Blockwork at multiple zones. | 36.3% | None | Site_View_265.jpg | William Wilson | Eng. Abdullah (PM) | Shelley Sandoval
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-266 | 2025-07-24 | Contractor | Consultant | Daily Report - Day 266 | Very Hot | 45C | 69 | 18 | Ongoing: Blockwork at multiple zones. | 36.44% | None | Site_View_266.jpg | Ashley Monroe | Eng. Abdullah (PM) | Jeffrey Reed
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-268 | 2025-07-26 | Contractor | Consultant | Daily Report - Day 268 | Very Hot | 46C | 73 | 5 | Ongoing: Painting First Coat at multiple zones. | 36.71% | None | Site_View_268.jpg | Kayla Smith | Eng. Abdullah (PM) | Zachary Long
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-269 | 2025-07-27 | Contractor | Consultant | Daily Report - Day 269 | Sunny | 20C | 126 | 5 | Ongoing: Ceramic Tiling at multiple zones. | 36.85% | Material Delay | Site_View_269.jpg | Andrew Becker | Eng. Abdullah (PM) | Mercedes Durham
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-270 | 2025-07-28 | Contractor | Consultant | Daily Report - Day 270 | Sunny | 21C | 72 | 9 | Ongoing: Blockwork at multiple zones. | 36.99% | None | Site_View_270.jpg | Robert Carlson | Eng. Abdullah (PM) | Summer Roberson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-271 | 2025-07-29 | Contractor | Consultant | Daily Report - Day 271 | Sunny | 29C | 76 | 15 | Ongoing: Ceramic Tiling at multiple zones. | 37.12% | None | Site_View_271.jpg | Bryan Velez | Eng. Abdullah (PM) | Troy White
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-272 | 2025-07-30 | Contractor | Consultant | Daily Report - Day 272 | Sunny | 26C | 77 | 8 | Ongoing: Painting First Coat at multiple zones. | 37.26% | None | Site_View_272.jpg | Jeremy Moore | Eng. Abdullah (PM) | Ashley Young
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-273 | 2025-07-31 | Contractor | Consultant | Daily Report - Day 273 | Sunny | 28C | 59 | 20 | Ongoing: Plastering at multiple zones. | 37.4% | None | Site_View_273.jpg | Mark Guerrero | Eng. Abdullah (PM) | Jody Sanchez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-275 | 2025-08-02 | Contractor | Consultant | Daily Report - Day 275 | Sunny | 22C | 105 | 20 | Ongoing: Ceramic Tiling at multiple zones. | 37.67% | None | Site_View_275.jpg | Tara Carter | Eng. Abdullah (PM) | Robert Kline
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-276 | 2025-08-03 | Contractor | Consultant | Daily Report - Day 276 | Very Hot | 46C | 96 | 7 | Ongoing: Ceramic Tiling at multiple zones. | 37.81% | Material Delay | Site_View_276.jpg | Olivia Wyatt | Eng. Abdullah (PM) | Kristina Dean
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-277 | 2025-08-04 | Contractor | Consultant | Daily Report - Day 277 | Sunny | 21C | 106 | 20 | Ongoing: Painting First Coat at multiple zones. | 37.95% | None | Site_View_277.jpg | Timothy Woods | Eng. Abdullah (PM) | David Davis
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-278 | 2025-08-05 | Contractor | Consultant | Daily Report - Day 278 | Very Hot | 45C | 74 | 11 | Ongoing: Blockwork at multiple zones. | 38.08% | None | Site_View_278.jpg | Christopher Moore | Eng. Abdullah (PM) | Heather Thompson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-279 | 2025-08-06 | Contractor | Consultant | Daily Report - Day 279 | Sunny | 22C | 92 | 5 | Ongoing: Painting First Coat at multiple zones. | 38.22% | None | Site_View_279.jpg | Erik Jones | Eng. Abdullah (PM) | Richard Benson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-280 | 2025-08-07 | Contractor | Consultant | Daily Report - Day 280 | Sunny | 26C | 32 | 9 | Ongoing: Painting First Coat at multiple zones. | 38.36% | None | Site_View_280.jpg | Kristin Montoya | Eng. Abdullah (PM) | Brandon Bender
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-282 | 2025-08-09 | Contractor | Consultant | Daily Report - Day 282 | Very Hot | 41C | 97 | 13 | Ongoing: Blockwork at multiple zones. | 38.63% | None | Site_View_282.jpg | David Silva | Eng. Abdullah (PM) | David Camacho
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-283 | 2025-08-10 | Contractor | Consultant | Daily Report - Day 283 | Very Hot | 48C | 103 | 11 | Ongoing: Blockwork at multiple zones. | 38.77% | None | Site_View_283.jpg | Michelle Edwards DVM | Eng. Abdullah (PM) | Jennifer Gray
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-284 | 2025-08-11 | Contractor | Consultant | Daily Report - Day 284 | Sunny | 33C | 122 | 14 | Ongoing: Gypsum Ceiling at multiple zones. | 38.9% | None | Site_View_284.jpg | Oscar Miller | Eng. Abdullah (PM) | Lisa Hernandez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-285 | 2025-08-12 | Contractor | Consultant | Daily Report - Day 285 | Very Hot | 46C | 99 | 18 | Ongoing: Door Installation at multiple zones. | 39.04% | None | Site_View_285.jpg | Brian Harris | Eng. Abdullah (PM) | Steven Smith
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-286 | 2025-08-13 | Contractor | Consultant | Daily Report - Day 286 | Sunny | 27C | 61 | 18 | Ongoing: Painting First Coat at multiple zones. | 39.18% | None | Site_View_286.jpg | Donna Jordan | Eng. Abdullah (PM) | Heather Aguilar
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-287 | 2025-08-14 | Contractor | Consultant | Daily Report - Day 287 | Sunny | 23C | 149 | 17 | Ongoing: Ceramic Tiling at multiple zones. | 39.32% | None | Site_View_287.jpg | Justin White | Eng. Abdullah (PM) | Jacob Moore
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-289 | 2025-08-16 | Contractor | Consultant | Daily Report - Day 289 | Very Hot | 43C | 45 | 15 | Ongoing: Plastering at multiple zones. | 39.59% | Material Delay | Site_View_289.jpg | Cheryl Riddle | Eng. Abdullah (PM) | Erin Morrison
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-290 | 2025-08-17 | Contractor | Consultant | Daily Report - Day 290 | Sunny | 25C | 98 | 15 | Ongoing: Blockwork at multiple zones. | 39.73% | None | Site_View_290.jpg | Eric Gonzalez | Eng. Abdullah (PM) | Matthew Mcdonald
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-291 | 2025-08-18 | Contractor | Consultant | Daily Report - Day 291 | Sunny | 31C | 57 | 5 | Ongoing: Ceramic Tiling at multiple zones. | 39.86% | None | Site_View_291.jpg | Brittany Cox | Eng. Abdullah (PM) | Amy Brown
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-292 | 2025-08-19 | Contractor | Consultant | Daily Report - Day 292 | Sunny | 39C | 97 | 5 | Ongoing: Gypsum Ceiling at multiple zones. | 40.0% | None | Site_View_292.jpg | Jamie Chambers | Eng. Abdullah (PM) | Jennifer Strong
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-293 | 2025-08-20 | Contractor | Consultant | Daily Report - Day 293 | Sunny | 38C | 74 | 6 | Ongoing: Painting First Coat at multiple zones. | 40.14% | None | Site_View_293.jpg | Kathleen Nelson | Eng. Abdullah (PM) | Tyler Yates
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-294 | 2025-08-21 | Contractor | Consultant | Daily Report - Day 294 | Sunny | 20C | 150 | 13 | Ongoing: Door Installation at multiple zones. | 40.27% | Material Delay | Site_View_294.jpg | Scott Jones | Eng. Abdullah (PM) | Kyle Griffin
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-296 | 2025-08-23 | Contractor | Consultant | Daily Report - Day 296 | Sunny | 23C | 122 | 16 | Ongoing: Blockwork at multiple zones. | 40.55% | None | Site_View_296.jpg | Sharon Higgins | Eng. Abdullah (PM) | Gregory Winters
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-297 | 2025-08-24 | Contractor | Consultant | Daily Report - Day 297 | Very Hot | 48C | 104 | 11 | Ongoing: Ceramic Tiling at multiple zones. | 40.68% | None | Site_View_297.jpg | Maria Padilla | Eng. Abdullah (PM) | Jacob Mason
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-298 | 2025-08-25 | Contractor | Consultant | Daily Report - Day 298 | Sunny | 34C | 67 | 20 | Ongoing: Ceramic Tiling at multiple zones. | 40.82% | None | Site_View_298.jpg | Daniel Gomez | Eng. Abdullah (PM) | Gavin Morales
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-299 | 2025-08-26 | Contractor | Consultant | Daily Report - Day 299 | Sunny | 38C | 84 | 7 | Ongoing: Blockwork at multiple zones. | 40.96% | Material Delay | Site_View_299.jpg | Dr. Brenda Baker | Eng. Abdullah (PM) | Denise Burnett
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-300 | 2025-08-27 | Contractor | Consultant | Daily Report - Day 300 | Sunny | 39C | 109 | 9 | Ongoing: Gypsum Ceiling at multiple zones. | 41.1% | None | Site_View_300.jpg | Nicole Williams | Eng. Abdullah (PM) | Mr. Jose Ortiz
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-301 | 2025-08-28 | Contractor | Consultant | Daily Report - Day 301 | Sunny | 35C | 67 | 12 | Ongoing: Ceramic Tiling at multiple zones. | 41.23% | None | Site_View_301.jpg | Kimberly Hernandez | Eng. Abdullah (PM) | Jeremy Vega
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-303 | 2025-08-30 | Contractor | Consultant | Daily Report - Day 303 | Sunny | 24C | 92 | 18 | Ongoing: Blockwork at multiple zones. | 41.51% | None | Site_View_303.jpg | Richard Bailey | Eng. Abdullah (PM) | Garrett Gibson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-304 | 2025-08-31 | Contractor | Consultant | Daily Report - Day 304 | Sunny | 38C | 109 | 6 | Ongoing: Door Installation at multiple zones. | 41.64% | None | Site_View_304.jpg | Megan Oconnor | Eng. Abdullah (PM) | James Stone
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-305 | 2025-09-01 | Contractor | Consultant | Daily Report - Day 305 | Sunny | 28C | 58 | 5 | Ongoing: Gypsum Ceiling at multiple zones. | 41.78% | None | Site_View_305.jpg | Stacey Bowers | Eng. Abdullah (PM) | Richard Stevenson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-306 | 2025-09-02 | Contractor | Consultant | Daily Report - Day 306 | Sunny | 29C | 134 | 8 | Ongoing: Painting First Coat at multiple zones. | 41.92% | None | Site_View_306.jpg | Jordan Barry | Eng. Abdullah (PM) | Clifford Rodriguez MD
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-307 | 2025-09-03 | Contractor | Consultant | Daily Report - Day 307 | Sunny | 30C | 134 | 14 | Ongoing: Gypsum Ceiling at multiple zones. | 42.05% | None | Site_View_307.jpg | Lori Carrillo | Eng. Abdullah (PM) | Tonya Cardenas
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-308 | 2025-09-04 | Contractor | Consultant | Daily Report - Day 308 | Sunny | 35C | 37 | 12 | Ongoing: Gypsum Ceiling at multiple zones. | 42.19% | Material Delay | Site_View_308.jpg | Paul Maldonado | Eng. Abdullah (PM) | Rebecca Lyons
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-310 | 2025-09-06 | Contractor | Consultant | Daily Report - Day 310 | Sunny | 21C | 51 | 7 | Ongoing: Plastering at multiple zones. | 42.47% | None | Site_View_310.jpg | Eric Arnold | Eng. Abdullah (PM) | Mary Gordon
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-311 | 2025-09-07 | Contractor | Consultant | Daily Report - Day 311 | Sunny | 37C | 52 | 11 | Ongoing: Plastering at multiple zones. | 42.6% | None | Site_View_311.jpg | Johnathan Conley III | Eng. Abdullah (PM) | Elizabeth Rice
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-312 | 2025-09-08 | Contractor | Consultant | Daily Report - Day 312 | Very Hot | 47C | 39 | 20 | Ongoing: Plastering at multiple zones. | 42.74% | None | Site_View_312.jpg | Anna Evans | Eng. Abdullah (PM) | Carla Jones
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-313 | 2025-09-09 | Contractor | Consultant | Daily Report - Day 313 | Sunny | 34C | 89 | 17 | Ongoing: Door Installation at multiple zones. | 42.88% | None | Site_View_313.jpg | Jennifer Herring | Eng. Abdullah (PM) | Barbara Durham
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-314 | 2025-09-10 | Contractor | Consultant | Daily Report - Day 314 | Very Hot | 47C | 115 | 18 | Ongoing: Blockwork at multiple zones. | 43.01% | Material Delay | Site_View_314.jpg | Joseph Bird | Eng. Abdullah (PM) | Raven Parker
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-315 | 2025-09-11 | Contractor | Consultant | Daily Report - Day 315 | Very Hot | 48C | 45 | 5 | Ongoing: Blockwork at multiple zones. | 43.15% | None | Site_View_315.jpg | Cynthia Goodman | Eng. Abdullah (PM) | Mandy Rivera
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-317 | 2025-09-13 | Contractor | Consultant | Daily Report - Day 317 | Sunny | 29C | 139 | 13 | Ongoing: Ceramic Tiling at multiple zones. | 43.42% | None | Site_View_317.jpg | Robert Rodgers DDS | Eng. Abdullah (PM) | Marcus Miles
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-318 | 2025-09-14 | Contractor | Consultant | Daily Report - Day 318 | Very Hot | 48C | 133 | 8 | Ongoing: Ceramic Tiling at multiple zones. | 43.56% | Material Delay | Site_View_318.jpg | Brittany Anderson | Eng. Abdullah (PM) | Angela Cruz
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-319 | 2025-09-15 | Contractor | Consultant | Daily Report - Day 319 | Sunny | 32C | 86 | 18 | Ongoing: Blockwork at multiple zones. | 43.7% | None | Site_View_319.jpg | Ashley Palmer | Eng. Abdullah (PM) | Brianna Johnson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-320 | 2025-09-16 | Contractor | Consultant | Daily Report - Day 320 | Sunny | 23C | 65 | 7 | Ongoing: Plastering at multiple zones. | 43.84% | None | Site_View_320.jpg | Rhonda Brown | Eng. Abdullah (PM) | Dawn Gardner
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-321 | 2025-09-17 | Contractor | Consultant | Daily Report - Day 321 | Very Hot | 48C | 87 | 12 | Ongoing: Door Installation at multiple zones. | 43.97% | None | Site_View_321.jpg | Heather Hoover | Eng. Abdullah (PM) | Anthony Ward
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-322 | 2025-09-18 | Contractor | Consultant | Daily Report - Day 322 | Very Hot | 47C | 80 | 15 | Ongoing: Painting First Coat at multiple zones. | 44.11% | None | Site_View_322.jpg | Bryan Dunn | Eng. Abdullah (PM) | Miss Anna Smith MD
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-324 | 2025-09-20 | Contractor | Consultant | Daily Report - Day 324 | Sunny | 30C | 150 | 20 | Ongoing: Door Installation at multiple zones. | 44.38% | None | Site_View_324.jpg | Autumn Ford | Eng. Abdullah (PM) | Johnny Holt
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-325 | 2025-09-21 | Contractor | Consultant | Daily Report - Day 325 | Sunny | 29C | 144 | 19 | Ongoing: Door Installation at multiple zones. | 44.52% | None | Site_View_325.jpg | Ryan Phillips | Eng. Abdullah (PM) | Jennifer Lucas
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-326 | 2025-09-22 | Contractor | Consultant | Daily Report - Day 326 | Sunny | 33C | 89 | 5 | Ongoing: Door Installation at multiple zones. | 44.66% | None | Site_View_326.jpg | Micheal Stephenson | Eng. Abdullah (PM) | Robert Kent
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-327 | 2025-09-23 | Contractor | Consultant | Daily Report - Day 327 | Sunny | 34C | 57 | 12 | Ongoing: Blockwork at multiple zones. | 44.79% | Material Delay | Site_View_327.jpg | Janet Bennett | Eng. Abdullah (PM) | Catherine Sloan
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-328 | 2025-09-24 | Contractor | Consultant | Daily Report - Day 328 | Very Hot | 45C | 150 | 15 | Ongoing: Gypsum Ceiling at multiple zones. | 44.93% | None | Site_View_328.jpg | Brandon Herring | Eng. Abdullah (PM) | Gregory Ryan
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-329 | 2025-09-25 | Contractor | Consultant | Daily Report - Day 329 | Very Hot | 47C | 139 | 12 | Ongoing: Door Installation at multiple zones. | 45.07% | None | Site_View_329.jpg | Tammy Gonzalez | Eng. Abdullah (PM) | Sean Long
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-331 | 2025-09-27 | Contractor | Consultant | Daily Report - Day 331 | Very Hot | 47C | 149 | 9 | Ongoing: Door Installation at multiple zones. | 45.34% | None | Site_View_331.jpg | Colleen Stephenson | Eng. Abdullah (PM) | Jeffrey Rodriguez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-332 | 2025-09-28 | Contractor | Consultant | Daily Report - Day 332 | Sunny | 26C | 91 | 13 | Ongoing: Plastering at multiple zones. | 45.48% | None | Site_View_332.jpg | Brian Carroll | Eng. Abdullah (PM) | Bernard Jackson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-333 | 2025-09-29 | Contractor | Consultant | Daily Report - Day 333 | Sunny | 39C | 150 | 10 | Ongoing: Ceramic Tiling at multiple zones. | 45.62% | None | Site_View_333.jpg | Brandon Hamilton Jr. | Eng. Abdullah (PM) | Kelly Davis
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-334 | 2025-09-30 | Contractor | Consultant | Daily Report - Day 334 | Sunny | 36C | 37 | 18 | Ongoing: Painting First Coat at multiple zones. | 45.75% | Material Delay | Site_View_334.jpg | Matthew Martin | Eng. Abdullah (PM) | Kyle Avila
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-335 | 2025-10-01 | Contractor | Consultant | Daily Report - Day 335 | Sunny | 30C | 102 | 10 | Ongoing: Painting First Coat at multiple zones. | 45.89% | None | Site_View_335.jpg | Samantha Dixon | Eng. Abdullah (PM) | Brian Chapman
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-336 | 2025-10-02 | Contractor | Consultant | Daily Report - Day 336 | Sunny | 30C | 76 | 13 | Ongoing: Blockwork at multiple zones. | 46.03% | None | Site_View_336.jpg | Mandy Hansen | Eng. Abdullah (PM) | Sherry Marshall
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-338 | 2025-10-04 | Contractor | Consultant | Daily Report - Day 338 | Sunny | 21C | 136 | 12 | Ongoing: Gypsum Ceiling at multiple zones. | 46.3% | None | Site_View_338.jpg | Rebecca Carpenter | Eng. Abdullah (PM) | Elizabeth Patterson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-339 | 2025-10-05 | Contractor | Consultant | Daily Report - Day 339 | Sunny | 30C | 123 | 8 | Ongoing: Gypsum Ceiling at multiple zones. | 46.44% | None | Site_View_339.jpg | William Calhoun | Eng. Abdullah (PM) | Jessica Parsons
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-340 | 2025-10-06 | Contractor | Consultant | Daily Report - Day 340 | Very Hot | 41C | 85 | 5 | Ongoing: Gypsum Ceiling at multiple zones. | 46.58% | Material Delay | Site_View_340.jpg | Anne Thomas | Eng. Abdullah (PM) | Samantha Hall
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-341 | 2025-10-07 | Contractor | Consultant | Daily Report - Day 341 | Sunny | 22C | 32 | 5 | Ongoing: Blockwork at multiple zones. | 46.71% | None | Site_View_341.jpg | Andrew Perez | Eng. Abdullah (PM) | Stacy Diaz
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-342 | 2025-10-08 | Contractor | Consultant | Daily Report - Day 342 | Sunny | 38C | 40 | 17 | Ongoing: Plastering at multiple zones. | 46.85% | None | Site_View_342.jpg | Christopher Mathews | Eng. Abdullah (PM) | Frank Brown
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-343 | 2025-10-09 | Contractor | Consultant | Daily Report - Day 343 | Very Hot | 44C | 126 | 17 | Ongoing: Gypsum Ceiling at multiple zones. | 46.99% | Material Delay | Site_View_343.jpg | Hannah Christian | Eng. Abdullah (PM) | Christopher Perry
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-345 | 2025-10-11 | Contractor | Consultant | Daily Report - Day 345 | Sunny | 25C | 53 | 16 | Ongoing: Ceramic Tiling at multiple zones. | 47.26% | None | Site_View_345.jpg | Alyssa Quinn | Eng. Abdullah (PM) | Juan Thomas
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-346 | 2025-10-12 | Contractor | Consultant | Daily Report - Day 346 | Sunny | 22C | 130 | 5 | Ongoing: Ceramic Tiling at multiple zones. | 47.4% | None | Site_View_346.jpg | Gene Bryant | Eng. Abdullah (PM) | Michael Silva
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-347 | 2025-10-13 | Contractor | Consultant | Daily Report - Day 347 | Sunny | 25C | 67 | 19 | Ongoing: Blockwork at multiple zones. | 47.53% | Material Delay | Site_View_347.jpg | Daniel Rodriguez | Eng. Abdullah (PM) | Scott Rhodes
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-348 | 2025-10-14 | Contractor | Consultant | Daily Report - Day 348 | Very Hot | 40C | 102 | 7 | Ongoing: Gypsum Ceiling at multiple zones. | 47.67% | Material Delay | Site_View_348.jpg | Robert Ruiz | Eng. Abdullah (PM) | Valerie Anderson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-349 | 2025-10-15 | Contractor | Consultant | Daily Report - Day 349 | Sunny | 28C | 60 | 12 | Ongoing: Blockwork at multiple zones. | 47.81% | None | Site_View_349.jpg | Teresa Chaney | Eng. Abdullah (PM) | Michael Stephens
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-350 | 2025-10-16 | Contractor | Consultant | Daily Report - Day 350 | Very Hot | 41C | 89 | 15 | Ongoing: Blockwork at multiple zones. | 47.95% | None | Site_View_350.jpg | Matthew Manning | Eng. Abdullah (PM) | Todd Richmond
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-352 | 2025-10-18 | Contractor | Consultant | Daily Report - Day 352 | Sunny | 20C | 108 | 9 | Ongoing: Ceramic Tiling at multiple zones. | 48.22% | None | Site_View_352.jpg | Brandon Clark | Eng. Abdullah (PM) | Christina Elliott
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-353 | 2025-10-19 | Contractor | Consultant | Daily Report - Day 353 | Sunny | 28C | 97 | 8 | Ongoing: Gypsum Ceiling at multiple zones. | 48.36% | Material Delay | Site_View_353.jpg | Christopher Sanchez | Eng. Abdullah (PM) | Ryan Parker
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-354 | 2025-10-20 | Contractor | Consultant | Daily Report - Day 354 | Sunny | 26C | 117 | 14 | Ongoing: Gypsum Ceiling at multiple zones. | 48.49% | None | Site_View_354.jpg | Anthony Rhodes | Eng. Abdullah (PM) | Emily Stark
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-355 | 2025-10-21 | Contractor | Consultant | Daily Report - Day 355 | Sunny | 26C | 98 | 11 | Ongoing: Door Installation at multiple zones. | 48.63% | None | Site_View_355.jpg | David Wood | Eng. Abdullah (PM) | Amanda Reyes
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-356 | 2025-10-22 | Contractor | Consultant | Daily Report - Day 356 | Sunny | 35C | 111 | 9 | Ongoing: Plastering at multiple zones. | 48.77% | None | Site_View_356.jpg | Sarah Benson | Eng. Abdullah (PM) | Brittany Harris MD
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-357 | 2025-10-23 | Contractor | Consultant | Daily Report - Day 357 | Sunny | 34C | 100 | 5 | Ongoing: Ceramic Tiling at multiple zones. | 48.9% | None | Site_View_357.jpg | David Cisneros | Eng. Abdullah (PM) | Andrew Parks
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-359 | 2025-10-25 | Contractor | Consultant | Daily Report - Day 359 | Sunny | 35C | 116 | 16 | Ongoing: Door Installation at multiple zones. | 49.18% | None | Site_View_359.jpg | Steven Rodgers | Eng. Abdullah (PM) | Michelle Haas
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-360 | 2025-10-26 | Contractor | Consultant | Daily Report - Day 360 | Sunny | 36C | 119 | 6 | Ongoing: Blockwork at multiple zones. | 49.32% | None | Site_View_360.jpg | Daniel Martinez | Eng. Abdullah (PM) | Christopher Hart
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-361 | 2025-10-27 | Contractor | Consultant | Daily Report - Day 361 | Very Hot | 44C | 135 | 9 | Ongoing: Blockwork at multiple zones. | 49.45% | None | Site_View_361.jpg | Stephen Austin | Eng. Abdullah (PM) | April Wright
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-362 | 2025-10-28 | Contractor | Consultant | Daily Report - Day 362 | Very Hot | 42C | 52 | 11 | Ongoing: Ceramic Tiling at multiple zones. | 49.59% | None | Site_View_362.jpg | Amber Whitaker | Eng. Abdullah (PM) | Andrew Ortega
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-363 | 2025-10-29 | Contractor | Consultant | Daily Report - Day 363 | Sunny | 30C | 143 | 11 | Ongoing: Plastering at multiple zones. | 49.73% | None | Site_View_363.jpg | Ashley Gentry | Eng. Abdullah (PM) | Brian Cole
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-364 | 2025-10-30 | Contractor | Consultant | Daily Report - Day 364 | Very Hot | 47C | 88 | 9 | Ongoing: Gypsum Ceiling at multiple zones. | 49.86% | None | Site_View_364.jpg | Tony White | Eng. Abdullah (PM) | William Bowman
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-366 | 2025-11-01 | Contractor | Consultant | Daily Report - Day 366 | Very Hot | 43C | 92 | 20 | Ongoing: Door Installation at multiple zones. | 50.14% | None | Site_View_366.jpg | William Ball | Eng. Abdullah (PM) | Yesenia Webb
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-367 | 2025-11-02 | Contractor | Consultant | Daily Report - Day 367 | Very Hot | 41C | 127 | 16 | Ongoing: Plastering at multiple zones. | 50.27% | Material Delay | Site_View_367.jpg | James Wells | Eng. Abdullah (PM) | Brendan Sanchez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-368 | 2025-11-03 | Contractor | Consultant | Daily Report - Day 368 | Sunny | 30C | 139 | 7 | Ongoing: Gypsum Ceiling at multiple zones. | 50.41% | Material Delay | Site_View_368.jpg | Mrs. Jennifer Ayala DDS | Eng. Abdullah (PM) | Katie Mitchell
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-369 | 2025-11-04 | Contractor | Consultant | Daily Report - Day 369 | Sunny | 20C | 94 | 19 | Ongoing: Blockwork at multiple zones. | 50.55% | Material Delay | Site_View_369.jpg | Kirk Taylor | Eng. Abdullah (PM) | Scott Sanchez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-370 | 2025-11-05 | Contractor | Consultant | Daily Report - Day 370 | Sunny | 21C | 33 | 16 | Ongoing: Gypsum Ceiling at multiple zones. | 50.68% | Material Delay | Site_View_370.jpg | Brenda Thomas | Eng. Abdullah (PM) | Paul Reed
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-371 | 2025-11-06 | Contractor | Consultant | Daily Report - Day 371 | Sunny | 29C | 70 | 16 | Ongoing: Ceramic Tiling at multiple zones. | 50.82% | Material Delay | Site_View_371.jpg | Teresa Becker | Eng. Abdullah (PM) | Jessica Hopkins
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-373 | 2025-11-08 | Contractor | Consultant | Daily Report - Day 373 | Sunny | 25C | 146 | 18 | Ongoing: Plastering at multiple zones. | 51.1% | None | Site_View_373.jpg | April Combs | Eng. Abdullah (PM) | Jonathan Benton
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-374 | 2025-11-09 | Contractor | Consultant | Daily Report - Day 374 | Sunny | 29C | 135 | 6 | Ongoing: Ceramic Tiling at multiple zones. | 51.23% | None | Site_View_374.jpg | Logan Lewis | Eng. Abdullah (PM) | Roger Campos
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-375 | 2025-11-10 | Contractor | Consultant | Daily Report - Day 375 | Sunny | 39C | 67 | 19 | Ongoing: Ceramic Tiling at multiple zones. | 51.37% | None | Site_View_375.jpg | Christopher Rose | Eng. Abdullah (PM) | Anthony Arnold
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-376 | 2025-11-11 | Contractor | Consultant | Daily Report - Day 376 | Very Hot | 43C | 117 | 14 | Ongoing: Blockwork at multiple zones. | 51.51% | None | Site_View_376.jpg | Shelley Lawson | Eng. Abdullah (PM) | Kaylee Miles
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-377 | 2025-11-12 | Contractor | Consultant | Daily Report - Day 377 | Very Hot | 41C | 86 | 11 | Ongoing: Plastering at multiple zones. | 51.64% | None | Site_View_377.jpg | Patricia Ruiz | Eng. Abdullah (PM) | Victoria Kennedy
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-378 | 2025-11-13 | Contractor | Consultant | Daily Report - Day 378 | Sunny | 24C | 76 | 15 | Ongoing: Door Installation at multiple zones. | 51.78% | Material Delay | Site_View_378.jpg | Rachel Smith | Eng. Abdullah (PM) | Kristina Chung
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-380 | 2025-11-15 | Contractor | Consultant | Daily Report - Day 380 | Sunny | 30C | 33 | 7 | Ongoing: Ceramic Tiling at multiple zones. | 52.05% | None | Site_View_380.jpg | Valerie Durham | Eng. Abdullah (PM) | David Moore
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-381 | 2025-11-16 | Contractor | Consultant | Daily Report - Day 381 | Sunny | 27C | 124 | 7 | Ongoing: Gypsum Ceiling at multiple zones. | 52.19% | None | Site_View_381.jpg | Sara Bell | Eng. Abdullah (PM) | Kelly Williams
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-382 | 2025-11-17 | Contractor | Consultant | Daily Report - Day 382 | Very Hot | 47C | 106 | 6 | Ongoing: Blockwork at multiple zones. | 52.33% | None | Site_View_382.jpg | Rachel Wiley | Eng. Abdullah (PM) | Scott Bradley
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-383 | 2025-11-18 | Contractor | Consultant | Daily Report - Day 383 | Sunny | 28C | 127 | 17 | Ongoing: Plastering at multiple zones. | 52.47% | None | Site_View_383.jpg | Benjamin Estes | Eng. Abdullah (PM) | Antonio Hicks
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-384 | 2025-11-19 | Contractor | Consultant | Daily Report - Day 384 | Sunny | 28C | 45 | 9 | Ongoing: Blockwork at multiple zones. | 52.6% | None | Site_View_384.jpg | Jennifer Griffith | Eng. Abdullah (PM) | Jesse Figueroa
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-385 | 2025-11-20 | Contractor | Consultant | Daily Report - Day 385 | Sunny | 32C | 106 | 13 | Ongoing: Plastering at multiple zones. | 52.74% | Material Delay | Site_View_385.jpg | Pamela Mccall | Eng. Abdullah (PM) | Lisa Thompson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-387 | 2025-11-22 | Contractor | Consultant | Daily Report - Day 387 | Sunny | 23C | 102 | 9 | Ongoing: Door Installation at multiple zones. | 53.01% | None | Site_View_387.jpg | Mitchell Russo | Eng. Abdullah (PM) | Matthew Smith
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-388 | 2025-11-23 | Contractor | Consultant | Daily Report - Day 388 | Sunny | 21C | 64 | 14 | Ongoing: Painting First Coat at multiple zones. | 53.15% | Material Delay | Site_View_388.jpg | Andrea Cannon | Eng. Abdullah (PM) | Douglas Leblanc
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-389 | 2025-11-24 | Contractor | Consultant | Daily Report - Day 389 | Sunny | 20C | 136 | 6 | Ongoing: Blockwork at multiple zones. | 53.29% | None | Site_View_389.jpg | Julie Weber | Eng. Abdullah (PM) | Dillon Hodges
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-390 | 2025-11-25 | Contractor | Consultant | Daily Report - Day 390 | Sunny | 22C | 145 | 11 | Ongoing: Plastering at multiple zones. | 53.42% | Material Delay | Site_View_390.jpg | Tabitha Flores | Eng. Abdullah (PM) | Nancy Bender
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-391 | 2025-11-26 | Contractor | Consultant | Daily Report - Day 391 | Sunny | 38C | 95 | 14 | Ongoing: Door Installation at multiple zones. | 53.56% | None | Site_View_391.jpg | Stephanie Deleon | Eng. Abdullah (PM) | Tammy Young
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-392 | 2025-11-27 | Contractor | Consultant | Daily Report - Day 392 | Sunny | 27C | 99 | 19 | Ongoing: Plastering at multiple zones. | 53.7% | None | Site_View_392.jpg | Lauren Gross | Eng. Abdullah (PM) | Ronald Stephens
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-394 | 2025-11-29 | Contractor | Consultant | Daily Report - Day 394 | Very Hot | 42C | 58 | 17 | Ongoing: Blockwork at multiple zones. | 53.97% | None | Site_View_394.jpg | Richard Baxter | Eng. Abdullah (PM) | Juan Hill MD
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-395 | 2025-11-30 | Contractor | Consultant | Daily Report - Day 395 | Sunny | 25C | 107 | 14 | Ongoing: Plastering at multiple zones. | 54.11% | None | Site_View_395.jpg | Christina Klein | Eng. Abdullah (PM) | Beverly Campbell
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-396 | 2025-12-01 | Contractor | Consultant | Daily Report - Day 396 | Sunny | 35C | 94 | 8 | Ongoing: Door Installation at multiple zones. | 54.25% | None | Site_View_396.jpg | Tammy Taylor | Eng. Abdullah (PM) | Kerri Tate
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-397 | 2025-12-02 | Contractor | Consultant | Daily Report - Day 397 | Very Hot | 48C | 143 | 16 | Ongoing: Ceramic Tiling at multiple zones. | 54.38% | None | Site_View_397.jpg | Angela Miller MD | Eng. Abdullah (PM) | Hunter Navarro
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-398 | 2025-12-03 | Contractor | Consultant | Daily Report - Day 398 | Very Hot | 43C | 66 | 6 | Ongoing: Ceramic Tiling at multiple zones. | 54.52% | None | Site_View_398.jpg | Brenda Williams | Eng. Abdullah (PM) | Mark Bryant
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-399 | 2025-12-04 | Contractor | Consultant | Daily Report - Day 399 | Sunny | 24C | 107 | 20 | Ongoing: Ceramic Tiling at multiple zones. | 54.66% | None | Site_View_399.jpg | Emily Glenn | Eng. Abdullah (PM) | Allen Webb
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-401 | 2025-12-06 | Contractor | Consultant | Daily Report - Day 401 | Sunny | 33C | 119 | 10 | Ongoing: Door Installation at multiple zones. | 54.93% | Material Delay | Site_View_401.jpg | Heidi Hill | Eng. Abdullah (PM) | Haley Mendez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-402 | 2025-12-07 | Contractor | Consultant | Daily Report - Day 402 | Very Hot | 43C | 116 | 11 | Ongoing: Plastering at multiple zones. | 55.07% | None | Site_View_402.jpg | Alyssa Harris | Eng. Abdullah (PM) | Christian Lara
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-403 | 2025-12-08 | Contractor | Consultant | Daily Report - Day 403 | Sunny | 39C | 101 | 7 | Ongoing: Door Installation at multiple zones. | 55.21% | None | Site_View_403.jpg | Francisco Knapp | Eng. Abdullah (PM) | Jody Fitzgerald MD
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-404 | 2025-12-09 | Contractor | Consultant | Daily Report - Day 404 | Sunny | 27C | 136 | 12 | Ongoing: Plastering at multiple zones. | 55.34% | None | Site_View_404.jpg | Thomas George | Eng. Abdullah (PM) | Brent Orozco
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-405 | 2025-12-10 | Contractor | Consultant | Daily Report - Day 405 | Sunny | 28C | 81 | 20 | Ongoing: Door Installation at multiple zones. | 55.48% | None | Site_View_405.jpg | Matthew Anderson | Eng. Abdullah (PM) | Tim Gray
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-406 | 2025-12-11 | Contractor | Consultant | Daily Report - Day 406 | Sunny | 26C | 123 | 17 | Ongoing: Painting First Coat at multiple zones. | 55.62% | None | Site_View_406.jpg | Corey Brady | Eng. Abdullah (PM) | Carlos Miller
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-408 | 2025-12-13 | Contractor | Consultant | Daily Report - Day 408 | Sunny | 25C | 118 | 12 | Ongoing: Gypsum Ceiling at multiple zones. | 55.89% | None | Site_View_408.jpg | John Peters | Eng. Abdullah (PM) | Amanda Murillo
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-409 | 2025-12-14 | Contractor | Consultant | Daily Report - Day 409 | Sunny | 39C | 150 | 14 | Ongoing: Painting First Coat at multiple zones. | 56.03% | Material Delay | Site_View_409.jpg | Cynthia Miller MD | Eng. Abdullah (PM) | Daniel Long
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-410 | 2025-12-15 | Contractor | Consultant | Daily Report - Day 410 | Sunny | 35C | 102 | 6 | Ongoing: Painting First Coat at multiple zones. | 56.16% | None | Site_View_410.jpg | Heather Rice | Eng. Abdullah (PM) | Lindsay Adkins
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-411 | 2025-12-16 | Contractor | Consultant | Daily Report - Day 411 | Sunny | 20C | 122 | 12 | Ongoing: Door Installation at multiple zones. | 56.3% | None | Site_View_411.jpg | Duane Parsons | Eng. Abdullah (PM) | John Mccall
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-412 | 2025-12-17 | Contractor | Consultant | Daily Report - Day 412 | Very Hot | 47C | 114 | 10 | Ongoing: Door Installation at multiple zones. | 56.44% | None | Site_View_412.jpg | Joshua Blair | Eng. Abdullah (PM) | Christopher Harris
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-413 | 2025-12-18 | Contractor | Consultant | Daily Report - Day 413 | Sunny | 20C | 58 | 20 | Ongoing: Painting First Coat at multiple zones. | 56.58% | None | Site_View_413.jpg | Anne Johnson | Eng. Abdullah (PM) | Daniel Gay
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-415 | 2025-12-20 | Contractor | Consultant | Daily Report - Day 415 | Sunny | 34C | 94 | 10 | Ongoing: Ceramic Tiling at multiple zones. | 56.85% | None | Site_View_415.jpg | William Heath | Eng. Abdullah (PM) | Daniel Mendoza
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-416 | 2025-12-21 | Contractor | Consultant | Daily Report - Day 416 | Sunny | 21C | 82 | 8 | Ongoing: Gypsum Ceiling at multiple zones. | 56.99% | Material Delay | Site_View_416.jpg | Danielle Davis | Eng. Abdullah (PM) | Robert West
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-417 | 2025-12-22 | Contractor | Consultant | Daily Report - Day 417 | Sunny | 20C | 45 | 9 | Ongoing: Blockwork at multiple zones. | 57.12% | None | Site_View_417.jpg | Charles Taylor PhD | Eng. Abdullah (PM) | Erin Smith
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-418 | 2025-12-23 | Contractor | Consultant | Daily Report - Day 418 | Sunny | 32C | 118 | 14 | Ongoing: Painting First Coat at multiple zones. | 57.26% | None | Site_View_418.jpg | Natalie Bates | Eng. Abdullah (PM) | Andrea Lynch
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-419 | 2025-12-24 | Contractor | Consultant | Daily Report - Day 419 | Sunny | 38C | 149 | 14 | Ongoing: Door Installation at multiple zones. | 57.4% | None | Site_View_419.jpg | Kyle Hall | Eng. Abdullah (PM) | Carrie Spears
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-420 | 2025-12-25 | Contractor | Consultant | Daily Report - Day 420 | Sunny | 24C | 123 | 12 | Ongoing: Gypsum Ceiling at multiple zones. | 57.53% | Material Delay | Site_View_420.jpg | Brian Garcia | Eng. Abdullah (PM) | Christina Anderson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-422 | 2025-12-27 | Contractor | Consultant | Daily Report - Day 422 | Sunny | 33C | 124 | 9 | Ongoing: Blockwork at multiple zones. | 57.81% | Material Delay | Site_View_422.jpg | Stanley Wright | Eng. Abdullah (PM) | Diane Christian DVM
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-423 | 2025-12-28 | Contractor | Consultant | Daily Report - Day 423 | Sunny | 29C | 41 | 15 | Ongoing: Plastering at multiple zones. | 57.95% | None | Site_View_423.jpg | John Tyler | Eng. Abdullah (PM) | Christopher Choi
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-424 | 2025-12-29 | Contractor | Consultant | Daily Report - Day 424 | Sunny | 29C | 113 | 15 | Ongoing: Painting First Coat at multiple zones. | 58.08% | None | Site_View_424.jpg | Chelsea Silva | Eng. Abdullah (PM) | Christopher Mcknight
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-425 | 2025-12-30 | Contractor | Consultant | Daily Report - Day 425 | Very Hot | 40C | 36 | 13 | Ongoing: Door Installation at multiple zones. | 58.22% | Material Delay | Site_View_425.jpg | Thomas Buck | Eng. Abdullah (PM) | Amber Hickman
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-426 | 2025-12-31 | Contractor | Consultant | Daily Report - Day 426 | Sunny | 22C | 33 | 16 | Ongoing: Blockwork at multiple zones. | 58.36% | None | Site_View_426.jpg | Nathan Lindsey | Eng. Abdullah (PM) | Matthew Wilcox
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-427 | 2026-01-01 | Contractor | Consultant | Daily Report - Day 427 | Sunny | 23C | 32 | 11 | Ongoing: Painting First Coat at multiple zones. | 58.49% | None | Site_View_427.jpg | Nathan Conley | Eng. Abdullah (PM) | Tony Calderon
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-429 | 2026-01-03 | Contractor | Consultant | Daily Report - Day 429 | Very Hot | 46C | 32 | 19 | Ongoing: Blockwork at multiple zones. | 58.77% | None | Site_View_429.jpg | Sabrina Goodman | Eng. Abdullah (PM) | Jesse Graham
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-430 | 2026-01-04 | Contractor | Consultant | Daily Report - Day 430 | Sunny | 33C | 150 | 10 | Ongoing: Painting First Coat at multiple zones. | 58.9% | None | Site_View_430.jpg | Brandon Elliott DVM | Eng. Abdullah (PM) | Sharon Day
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-431 | 2026-01-05 | Contractor | Consultant | Daily Report - Day 431 | Sunny | 25C | 98 | 17 | Ongoing: Gypsum Ceiling at multiple zones. | 59.04% | None | Site_View_431.jpg | Ashley Crosby | Eng. Abdullah (PM) | Dawn Huynh
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-432 | 2026-01-06 | Contractor | Consultant | Daily Report - Day 432 | Sunny | 22C | 145 | 14 | Ongoing: Plastering at multiple zones. | 59.18% | None | Site_View_432.jpg | Shawn Webster | Eng. Abdullah (PM) | Jimmy Martin
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-433 | 2026-01-07 | Contractor | Consultant | Daily Report - Day 433 | Very Hot | 41C | 63 | 5 | Ongoing: Blockwork at multiple zones. | 59.32% | None | Site_View_433.jpg | Cheryl Daniels | Eng. Abdullah (PM) | Adam Bird
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-434 | 2026-01-08 | Contractor | Consultant | Daily Report - Day 434 | Sunny | 23C | 46 | 17 | Ongoing: Blockwork at multiple zones. | 59.45% | None | Site_View_434.jpg | Andrew Joyce | Eng. Abdullah (PM) | Samantha Fox
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-436 | 2026-01-10 | Contractor | Consultant | Daily Report - Day 436 | Very Hot | 48C | 83 | 14 | Ongoing: Painting First Coat at multiple zones. | 59.73% | None | Site_View_436.jpg | Danny Sanders | Eng. Abdullah (PM) | Amber Peters
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-437 | 2026-01-11 | Contractor | Consultant | Daily Report - Day 437 | Sunny | 31C | 38 | 16 | Ongoing: Plastering at multiple zones. | 59.86% | Material Delay | Site_View_437.jpg | Timothy Gay | Eng. Abdullah (PM) | Keith Scott
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-438 | 2026-01-12 | Contractor | Consultant | Daily Report - Day 438 | Sunny | 37C | 65 | 8 | Ongoing: Gypsum Ceiling at multiple zones. | 60.0% | None | Site_View_438.jpg | Hector Morris | Eng. Abdullah (PM) | Jacqueline Shaw
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-439 | 2026-01-13 | Contractor | Consultant | Daily Report - Day 439 | Sunny | 30C | 149 | 13 | Ongoing: Blockwork at multiple zones. | 60.14% | None | Site_View_439.jpg | Teresa Briggs | Eng. Abdullah (PM) | Philip Young
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-440 | 2026-01-14 | Contractor | Consultant | Daily Report - Day 440 | Very Hot | 40C | 49 | 8 | Ongoing: Door Installation at multiple zones. | 60.27% | None | Site_View_440.jpg | Joshua Fowler | Eng. Abdullah (PM) | Lori Ingram
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-441 | 2026-01-15 | Contractor | Consultant | Daily Report - Day 441 | Sunny | 38C | 78 | 13 | Ongoing: Blockwork at multiple zones. | 60.41% | None | Site_View_441.jpg | Elizabeth Adams | Eng. Abdullah (PM) | Marie Cortez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-443 | 2026-01-17 | Contractor | Consultant | Daily Report - Day 443 | Very Hot | 41C | 150 | 15 | Ongoing: Gypsum Ceiling at multiple zones. | 60.68% | None | Site_View_443.jpg | Jonathan Harris | Eng. Abdullah (PM) | Jennifer Cowan
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-444 | 2026-01-18 | Contractor | Consultant | Daily Report - Day 444 | Very Hot | 43C | 73 | 18 | Ongoing: Blockwork at multiple zones. | 60.82% | None | Site_View_444.jpg | Mrs. Bridget Martinez | Eng. Abdullah (PM) | Laura Schroeder
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-445 | 2026-01-19 | Contractor | Consultant | Daily Report - Day 445 | Very Hot | 42C | 146 | 11 | Ongoing: Ceramic Tiling at multiple zones. | 60.96% | Material Delay | Site_View_445.jpg | Judith Miller | Eng. Abdullah (PM) | Jon Shelton
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-446 | 2026-01-20 | Contractor | Consultant | Daily Report - Day 446 | Sunny | 25C | 131 | 14 | Ongoing: Plastering at multiple zones. | 61.1% | Material Delay | Site_View_446.jpg | Michael Miranda | Eng. Abdullah (PM) | Natalie Ingram
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-447 | 2026-01-21 | Contractor | Consultant | Daily Report - Day 447 | Very Hot | 47C | 103 | 20 | Ongoing: Plastering at multiple zones. | 61.23% | None | Site_View_447.jpg | Anthony Smith | Eng. Abdullah (PM) | Jonathan Oneill
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-448 | 2026-01-22 | Contractor | Consultant | Daily Report - Day 448 | Sunny | 39C | 90 | 18 | Ongoing: Painting First Coat at multiple zones. | 61.37% | None | Site_View_448.jpg | Savannah Robinson | Eng. Abdullah (PM) | Gloria Fischer
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-450 | 2026-01-24 | Contractor | Consultant | Daily Report - Day 450 | Sunny | 22C | 140 | 10 | Ongoing: Door Installation at multiple zones. | 61.64% | None | Site_View_450.jpg | Vicki Miller | Eng. Abdullah (PM) | Anne Baker
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-451 | 2026-01-25 | Contractor | Consultant | Daily Report - Day 451 | Very Hot | 44C | 33 | 11 | Ongoing: Plastering at multiple zones. | 61.78% | None | Site_View_451.jpg | Kyle Mccoy | Eng. Abdullah (PM) | Dr. Timothy White Jr.
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-452 | 2026-01-26 | Contractor | Consultant | Daily Report - Day 452 | Very Hot | 44C | 41 | 14 | Ongoing: Plastering at multiple zones. | 61.92% | None | Site_View_452.jpg | Kristen Dunn | Eng. Abdullah (PM) | Antonio Brown
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-453 | 2026-01-27 | Contractor | Consultant | Daily Report - Day 453 | Sunny | 31C | 78 | 19 | Ongoing: Plastering at multiple zones. | 62.05% | None | Site_View_453.jpg | Matthew Adams | Eng. Abdullah (PM) | Sarah Schultz
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-454 | 2026-01-28 | Contractor | Consultant | Daily Report - Day 454 | Sunny | 24C | 45 | 8 | Ongoing: Ceramic Tiling at multiple zones. | 62.19% | None | Site_View_454.jpg | Tammy Williams | Eng. Abdullah (PM) | Michele Martinez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-455 | 2026-01-29 | Contractor | Consultant | Daily Report - Day 455 | Sunny | 25C | 109 | 9 | Ongoing: Painting First Coat at multiple zones. | 62.33% | Material Delay | Site_View_455.jpg | Brandon Wright | Eng. Abdullah (PM) | Casey Phillips
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-457 | 2026-01-31 | Contractor | Consultant | Daily Report - Day 457 | Very Hot | 47C | 73 | 17 | Ongoing: Ceramic Tiling at multiple zones. | 62.6% | None | Site_View_457.jpg | Kathryn Martin | Eng. Abdullah (PM) | Casey Wilkins
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-458 | 2026-02-01 | Contractor | Consultant | Daily Report - Day 458 | Very Hot | 44C | 35 | 7 | Ongoing: Painting First Coat at multiple zones. | 62.74% | None | Site_View_458.jpg | John Austin | Eng. Abdullah (PM) | Kristin Wu
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-459 | 2026-02-02 | Contractor | Consultant | Daily Report - Day 459 | Very Hot | 40C | 68 | 8 | Ongoing: Gypsum Ceiling at multiple zones. | 62.88% | Material Delay | Site_View_459.jpg | John Livingston | Eng. Abdullah (PM) | Edwin Wallace
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-460 | 2026-02-03 | Contractor | Consultant | Daily Report - Day 460 | Sunny | 26C | 79 | 20 | Ongoing: Painting First Coat at multiple zones. | 63.01% | None | Site_View_460.jpg | Amy Smith | Eng. Abdullah (PM) | Leonard Castro
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-461 | 2026-02-04 | Contractor | Consultant | Daily Report - Day 461 | Sunny | 35C | 84 | 11 | Ongoing: Gypsum Ceiling at multiple zones. | 63.15% | None | Site_View_461.jpg | Kevin Cherry | Eng. Abdullah (PM) | Christopher Young
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-462 | 2026-02-05 | Contractor | Consultant | Daily Report - Day 462 | Very Hot | 42C | 67 | 5 | Ongoing: Gypsum Ceiling at multiple zones. | 63.29% | None | Site_View_462.jpg | Christopher Cunningham | Eng. Abdullah (PM) | Jason Randall
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-464 | 2026-02-07 | Contractor | Consultant | Daily Report - Day 464 | Very Hot | 40C | 141 | 13 | Ongoing: Ceramic Tiling at multiple zones. | 63.56% | Material Delay | Site_View_464.jpg | Douglas Brooks | Eng. Abdullah (PM) | Taylor Edwards
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-465 | 2026-02-08 | Contractor | Consultant | Daily Report - Day 465 | Very Hot | 46C | 87 | 6 | Ongoing: Plastering at multiple zones. | 63.7% | None | Site_View_465.jpg | Vanessa Anderson | Eng. Abdullah (PM) | Joshua Smith
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-466 | 2026-02-09 | Contractor | Consultant | Daily Report - Day 466 | Sunny | 26C | 135 | 13 | Ongoing: Gypsum Ceiling at multiple zones. | 63.84% | None | Site_View_466.jpg | Cody Lutz | Eng. Abdullah (PM) | Charles Stewart
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-467 | 2026-02-10 | Contractor | Consultant | Daily Report - Day 467 | Sunny | 27C | 126 | 14 | Ongoing: Painting First Coat at multiple zones. | 63.97% | None | Site_View_467.jpg | Carmen James | Eng. Abdullah (PM) | Erica Moore
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-468 | 2026-02-11 | Contractor | Consultant | Daily Report - Day 468 | Sunny | 29C | 57 | 15 | Ongoing: Painting First Coat at multiple zones. | 64.11% | Material Delay | Site_View_468.jpg | Michelle Diaz | Eng. Abdullah (PM) | Raymond Jones DVM
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-469 | 2026-02-12 | Contractor | Consultant | Daily Report - Day 469 | Very Hot | 46C | 120 | 20 | Ongoing: Door Installation at multiple zones. | 64.25% | None | Site_View_469.jpg | Ryan Lopez | Eng. Abdullah (PM) | David Callahan
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-471 | 2026-02-14 | Contractor | Consultant | Daily Report - Day 471 | Very Hot | 48C | 76 | 18 | Ongoing: Plastering at multiple zones. | 64.52% | Material Delay | Site_View_471.jpg | Lori Martin | Eng. Abdullah (PM) | Benjamin Palmer
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-472 | 2026-02-15 | Contractor | Consultant | Daily Report - Day 472 | Sunny | 30C | 116 | 5 | Ongoing: Ceramic Tiling at multiple zones. | 64.66% | None | Site_View_472.jpg | Gordon Sims | Eng. Abdullah (PM) | Mr. Darren Miller
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-473 | 2026-02-16 | Contractor | Consultant | Daily Report - Day 473 | Sunny | 36C | 59 | 13 | Ongoing: Gypsum Ceiling at multiple zones. | 64.79% | None | Site_View_473.jpg | Jeffery Shannon | Eng. Abdullah (PM) | Stacey Anderson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-474 | 2026-02-17 | Contractor | Consultant | Daily Report - Day 474 | Sunny | 29C | 128 | 14 | Ongoing: Plastering at multiple zones. | 64.93% | None | Site_View_474.jpg | Luis Moore | Eng. Abdullah (PM) | Monica Spencer
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-475 | 2026-02-18 | Contractor | Consultant | Daily Report - Day 475 | Sunny | 37C | 74 | 15 | Ongoing: Ceramic Tiling at multiple zones. | 65.07% | None | Site_View_475.jpg | Lisa Navarro | Eng. Abdullah (PM) | Anthony Blair
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-476 | 2026-02-19 | Contractor | Consultant | Daily Report - Day 476 | Very Hot | 46C | 134 | 18 | Ongoing: Painting First Coat at multiple zones. | 65.21% | None | Site_View_476.jpg | Kevin Moody | Eng. Abdullah (PM) | Christopher Garcia
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-478 | 2026-02-21 | Contractor | Consultant | Daily Report - Day 478 | Very Hot | 48C | 113 | 12 | Ongoing: Plastering at multiple zones. | 65.48% | None | Site_View_478.jpg | Sheila Austin | Eng. Abdullah (PM) | Morgan Turner
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-479 | 2026-02-22 | Contractor | Consultant | Daily Report - Day 479 | Sunny | 39C | 62 | 9 | Ongoing: Door Installation at multiple zones. | 65.62% | None | Site_View_479.jpg | Joanna Chapman | Eng. Abdullah (PM) | Rebecca Lutz
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-480 | 2026-02-23 | Contractor | Consultant | Daily Report - Day 480 | Sunny | 22C | 33 | 20 | Ongoing: Gypsum Ceiling at multiple zones. | 65.75% | Material Delay | Site_View_480.jpg | Christopher Harper | Eng. Abdullah (PM) | Paul Richardson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-481 | 2026-02-24 | Contractor | Consultant | Daily Report - Day 481 | Very Hot | 45C | 96 | 6 | Ongoing: Plastering at multiple zones. | 65.89% | Material Delay | Site_View_481.jpg | Bryan Peters | Eng. Abdullah (PM) | Angie Hopkins
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-482 | 2026-02-25 | Contractor | Consultant | Daily Report - Day 482 | Sunny | 38C | 33 | 15 | Ongoing: Gypsum Ceiling at multiple zones. | 66.03% | None | Site_View_482.jpg | Frank Dudley | Eng. Abdullah (PM) | Joseph Rodriguez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-483 | 2026-02-26 | Contractor | Consultant | Daily Report - Day 483 | Sunny | 31C | 66 | 20 | Ongoing: Door Installation at multiple zones. | 66.16% | None | Site_View_483.jpg | Joshua Huerta | Eng. Abdullah (PM) | Christian Guerra
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-485 | 2026-02-28 | Contractor | Consultant | Daily Report - Day 485 | Very Hot | 45C | 112 | 19 | Ongoing: Blockwork at multiple zones. | 66.44% | None | Site_View_485.jpg | Taylor Scott | Eng. Abdullah (PM) | Thomas Mcdaniel
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-486 | 2026-03-01 | Contractor | Consultant | Daily Report - Day 486 | Very Hot | 44C | 105 | 10 | Ongoing: Ceramic Tiling at multiple zones. | 66.58% | None | Site_View_486.jpg | Thomas Rodriguez | Eng. Abdullah (PM) | Kimberly Walls
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-487 | 2026-03-02 | Contractor | Consultant | Daily Report - Day 487 | Sunny | 36C | 43 | 9 | Ongoing: Gypsum Ceiling at multiple zones. | 66.71% | Material Delay | Site_View_487.jpg | Meredith Calhoun | Eng. Abdullah (PM) | Steve David
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-488 | 2026-03-03 | Contractor | Consultant | Daily Report - Day 488 | Sunny | 24C | 74 | 9 | Ongoing: Painting First Coat at multiple zones. | 66.85% | None | Site_View_488.jpg | Joseph French | Eng. Abdullah (PM) | David Jensen
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-489 | 2026-03-04 | Contractor | Consultant | Daily Report - Day 489 | Sunny | 39C | 57 | 11 | Ongoing: Painting First Coat at multiple zones. | 66.99% | None | Site_View_489.jpg | Courtney Ramos | Eng. Abdullah (PM) | Teresa Dunn
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-490 | 2026-03-05 | Contractor | Consultant | Daily Report - Day 490 | Sunny | 33C | 111 | 6 | Ongoing: Gypsum Ceiling at multiple zones. | 67.12% | Material Delay | Site_View_490.jpg | Kevin Elliott | Eng. Abdullah (PM) | Bradley Osborne
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-492 | 2026-03-07 | Contractor | Consultant | Daily Report - Day 492 | Sunny | 23C | 74 | 9 | Ongoing: Painting First Coat at multiple zones. | 67.4% | None | Site_View_492.jpg | Brandon Wolf | Eng. Abdullah (PM) | Thomas Evans
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-493 | 2026-03-08 | Contractor | Consultant | Daily Report - Day 493 | Sunny | 20C | 63 | 8 | Ongoing: Ceramic Tiling at multiple zones. | 67.53% | None | Site_View_493.jpg | Shelby Jones | Eng. Abdullah (PM) | Michael Wood
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-494 | 2026-03-09 | Contractor | Consultant | Daily Report - Day 494 | Very Hot | 46C | 83 | 15 | Ongoing: Door Installation at multiple zones. | 67.67% | None | Site_View_494.jpg | Joseph Cooper | Eng. Abdullah (PM) | Melissa Freeman
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-495 | 2026-03-10 | Contractor | Consultant | Daily Report - Day 495 | Sunny | 38C | 44 | 5 | Ongoing: Plastering at multiple zones. | 67.81% | None | Site_View_495.jpg | Donna Fitzpatrick | Eng. Abdullah (PM) | Donna Nichols
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-496 | 2026-03-11 | Contractor | Consultant | Daily Report - Day 496 | Sunny | 38C | 76 | 10 | Ongoing: Blockwork at multiple zones. | 67.95% | None | Site_View_496.jpg | Shannon Flores | Eng. Abdullah (PM) | Janice Johnson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-497 | 2026-03-12 | Contractor | Consultant | Daily Report - Day 497 | Sunny | 31C | 123 | 7 | Ongoing: Gypsum Ceiling at multiple zones. | 68.08% | Material Delay | Site_View_497.jpg | Cheryl Howard | Eng. Abdullah (PM) | Kevin Hinton
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-499 | 2026-03-14 | Contractor | Consultant | Daily Report - Day 499 | Sunny | 32C | 64 | 14 | Ongoing: Plastering at multiple zones. | 68.36% | None | Site_View_499.jpg | Vanessa Jenkins | Eng. Abdullah (PM) | Jose Perry
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-500 | 2026-03-15 | Contractor | Consultant | Daily Report - Day 500 | Very Hot | 41C | 69 | 16 | Ongoing: Gypsum Ceiling at multiple zones. | 68.49% | None | Site_View_500.jpg | Matthew Hernandez | Eng. Abdullah (PM) | Rodney Brown
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-501 | 2026-03-16 | Contractor | Consultant | Daily Report - Day 501 | Sunny | 25C | 114 | 13 | Ongoing: Plastering at multiple zones. | 68.63% | None | Site_View_501.jpg | Christopher Jackson | Eng. Abdullah (PM) | Joseph King
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-502 | 2026-03-17 | Contractor | Consultant | Daily Report - Day 502 | Very Hot | 45C | 87 | 18 | Ongoing: Ceramic Tiling at multiple zones. | 68.77% | None | Site_View_502.jpg | Anthony Anthony | Eng. Abdullah (PM) | Angela Walker
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-503 | 2026-03-18 | Contractor | Consultant | Daily Report - Day 503 | Sunny | 23C | 57 | 12 | Ongoing: Painting First Coat at multiple zones. | 68.9% | Material Delay | Site_View_503.jpg | Rachel Schneider | Eng. Abdullah (PM) | Gregory Long
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-504 | 2026-03-19 | Contractor | Consultant | Daily Report - Day 504 | Very Hot | 40C | 140 | 9 | Ongoing: Ceramic Tiling at multiple zones. | 69.04% | None | Site_View_504.jpg | Natasha Fernandez | Eng. Abdullah (PM) | David Saunders
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-506 | 2026-03-21 | Contractor | Consultant | Daily Report - Day 506 | Very Hot | 46C | 80 | 7 | Ongoing: Gypsum Ceiling at multiple zones. | 69.32% | None | Site_View_506.jpg | Caitlin Jones | Eng. Abdullah (PM) | Kimberly Jacobs
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-507 | 2026-03-22 | Contractor | Consultant | Daily Report - Day 507 | Sunny | 22C | 95 | 16 | Ongoing: Blockwork at multiple zones. | 69.45% | None | Site_View_507.jpg | Martha Davis | Eng. Abdullah (PM) | Joel Munoz
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-508 | 2026-03-23 | Contractor | Consultant | Daily Report - Day 508 | Sunny | 25C | 124 | 6 | Ongoing: Plastering at multiple zones. | 69.59% | None | Site_View_508.jpg | Travis Brooks | Eng. Abdullah (PM) | Henry Jacobs
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-509 | 2026-03-24 | Contractor | Consultant | Daily Report - Day 509 | Sunny | 21C | 103 | 15 | Ongoing: Door Installation at multiple zones. | 69.73% | None | Site_View_509.jpg | Brian Smith | Eng. Abdullah (PM) | Mark Lewis
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-510 | 2026-03-25 | Contractor | Consultant | Daily Report - Day 510 | Sunny | 39C | 143 | 15 | Ongoing: Door Installation at multiple zones. | 69.86% | Material Delay | Site_View_510.jpg | Christopher Anderson | Eng. Abdullah (PM) | Bethany Hernandez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-511 | 2026-03-26 | Contractor | Consultant | Daily Report - Day 511 | Very Hot | 42C | 51 | 16 | Ongoing: Plastering at multiple zones. | 70.0% | None | Site_View_511.jpg | Michael Shaw | Eng. Abdullah (PM) | Thomas Jones
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-513 | 2026-03-28 | Contractor | Consultant | Daily Report - Day 513 | Very Hot | 47C | 146 | 17 | Ongoing: Plastering at multiple zones. | 70.27% | None | Site_View_513.jpg | Joshua Stephenson MD | Eng. Abdullah (PM) | Tyler Thornton
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-514 | 2026-03-29 | Contractor | Consultant | Daily Report - Day 514 | Sunny | 27C | 58 | 9 | Ongoing: Door Installation at multiple zones. | 70.41% | None | Site_View_514.jpg | Janet Tucker | Eng. Abdullah (PM) | Chad Roberts
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-515 | 2026-03-30 | Contractor | Consultant | Daily Report - Day 515 | Sunny | 32C | 83 | 14 | Ongoing: Ceramic Tiling at multiple zones. | 70.55% | None | Site_View_515.jpg | Ms. Rachel Grimes | Eng. Abdullah (PM) | Daniel Gonzalez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-516 | 2026-03-31 | Contractor | Consultant | Daily Report - Day 516 | Very Hot | 48C | 143 | 15 | Ongoing: Blockwork at multiple zones. | 70.68% | None | Site_View_516.jpg | Natalie Miller | Eng. Abdullah (PM) | Cynthia Watson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-517 | 2026-04-01 | Contractor | Consultant | Daily Report - Day 517 | Sunny | 33C | 71 | 5 | Ongoing: Ceramic Tiling at multiple zones. | 70.82% | None | Site_View_517.jpg | Christy Ford | Eng. Abdullah (PM) | Martin Sanchez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-518 | 2026-04-02 | Contractor | Consultant | Daily Report - Day 518 | Sunny | 29C | 149 | 16 | Ongoing: Ceramic Tiling at multiple zones. | 70.96% | None | Site_View_518.jpg | Kayla James | Eng. Abdullah (PM) | Melissa Carter
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-520 | 2026-04-04 | Contractor | Consultant | Daily Report - Day 520 | Sunny | 29C | 109 | 10 | Ongoing: Door Installation at multiple zones. | 71.23% | None | Site_View_520.jpg | Kenneth Smith | Eng. Abdullah (PM) | Danny Collier
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-521 | 2026-04-05 | Contractor | Consultant | Daily Report - Day 521 | Sunny | 27C | 100 | 20 | Ongoing: Plastering at multiple zones. | 71.37% | None | Site_View_521.jpg | Judith Thomas | Eng. Abdullah (PM) | Desiree Morris
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-522 | 2026-04-06 | Contractor | Consultant | Daily Report - Day 522 | Very Hot | 42C | 52 | 11 | Ongoing: Ceramic Tiling at multiple zones. | 71.51% | None | Site_View_522.jpg | Donna Cruz | Eng. Abdullah (PM) | Sharon Taylor
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-523 | 2026-04-07 | Contractor | Consultant | Daily Report - Day 523 | Sunny | 25C | 144 | 18 | Ongoing: Door Installation at multiple zones. | 71.64% | None | Site_View_523.jpg | Jeff Bond | Eng. Abdullah (PM) | Alicia Hernandez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-524 | 2026-04-08 | Contractor | Consultant | Daily Report - Day 524 | Very Hot | 44C | 127 | 20 | Ongoing: Plastering at multiple zones. | 71.78% | None | Site_View_524.jpg | Russell Sloan | Eng. Abdullah (PM) | Robert Brown
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-525 | 2026-04-09 | Contractor | Consultant | Daily Report - Day 525 | Sunny | 30C | 89 | 14 | Ongoing: Gypsum Ceiling at multiple zones. | 71.92% | Material Delay | Site_View_525.jpg | Mark Thornton | Eng. Abdullah (PM) | Courtney Marquez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-527 | 2026-04-11 | Contractor | Consultant | Daily Report - Day 527 | Sunny | 39C | 79 | 6 | Ongoing: Blockwork at multiple zones. | 72.19% | None | Site_View_527.jpg | John Bradshaw | Eng. Abdullah (PM) | Sherry Thomas
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-528 | 2026-04-12 | Contractor | Consultant | Daily Report - Day 528 | Very Hot | 46C | 56 | 16 | Ongoing: Ceramic Tiling at multiple zones. | 72.33% | None | Site_View_528.jpg | Taylor Ewing | Eng. Abdullah (PM) | Kyle Jones
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-529 | 2026-04-13 | Contractor | Consultant | Daily Report - Day 529 | Very Hot | 42C | 127 | 11 | Ongoing: Painting First Coat at multiple zones. | 72.47% | None | Site_View_529.jpg | Daniel Little | Eng. Abdullah (PM) | Jennifer Torres
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-530 | 2026-04-14 | Contractor | Consultant | Daily Report - Day 530 | Very Hot | 45C | 110 | 9 | Ongoing: Door Installation at multiple zones. | 72.6% | None | Site_View_530.jpg | Zachary Lewis | Eng. Abdullah (PM) | Kimberly Rhodes
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-531 | 2026-04-15 | Contractor | Consultant | Daily Report - Day 531 | Very Hot | 43C | 121 | 7 | Ongoing: Ceramic Tiling at multiple zones. | 72.74% | None | Site_View_531.jpg | Megan Brown | Eng. Abdullah (PM) | Paul Mendoza
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-532 | 2026-04-16 | Contractor | Consultant | Daily Report - Day 532 | Sunny | 23C | 39 | 5 | Ongoing: Painting First Coat at multiple zones. | 72.88% | None | Site_View_532.jpg | Kim Zimmerman | Eng. Abdullah (PM) | Vanessa Butler
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-534 | 2026-04-18 | Contractor | Consultant | Daily Report - Day 534 | Sunny | 37C | 87 | 12 | Ongoing: Plastering at multiple zones. | 73.15% | None | Site_View_534.jpg | Brandon Kennedy | Eng. Abdullah (PM) | Oscar Williamson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-535 | 2026-04-19 | Contractor | Consultant | Daily Report - Day 535 | Sunny | 38C | 107 | 12 | Ongoing: Plastering at multiple zones. | 73.29% | None | Site_View_535.jpg | Kristen Coleman | Eng. Abdullah (PM) | Shawn Williams
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-536 | 2026-04-20 | Contractor | Consultant | Daily Report - Day 536 | Sunny | 32C | 105 | 15 | Ongoing: Painting First Coat at multiple zones. | 73.42% | Material Delay | Site_View_536.jpg | Jessica Wang | Eng. Abdullah (PM) | Summer Hill
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-537 | 2026-04-21 | Contractor | Consultant | Daily Report - Day 537 | Sunny | 31C | 81 | 5 | Ongoing: Plastering at multiple zones. | 73.56% | None | Site_View_537.jpg | Wanda Rice | Eng. Abdullah (PM) | Tyler Martin
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-538 | 2026-04-22 | Contractor | Consultant | Daily Report - Day 538 | Very Hot | 41C | 50 | 15 | Ongoing: Door Installation at multiple zones. | 73.7% | Material Delay | Site_View_538.jpg | Emily Olson | Eng. Abdullah (PM) | Kimberly Lewis
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-539 | 2026-04-23 | Contractor | Consultant | Daily Report - Day 539 | Very Hot | 42C | 80 | 13 | Ongoing: Gypsum Ceiling at multiple zones. | 73.84% | None | Site_View_539.jpg | Jeffrey Brown | Eng. Abdullah (PM) | Mark Reyes
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-541 | 2026-04-25 | Contractor | Consultant | Daily Report - Day 541 | Sunny | 24C | 58 | 11 | Ongoing: Blockwork at multiple zones. | 74.11% | None | Site_View_541.jpg | Laura Haley | Eng. Abdullah (PM) | Jennifer Bentley
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-542 | 2026-04-26 | Contractor | Consultant | Daily Report - Day 542 | Sunny | 22C | 147 | 10 | Ongoing: Gypsum Ceiling at multiple zones. | 74.25% | None | Site_View_542.jpg | Ricardo Price | Eng. Abdullah (PM) | Robert Nguyen
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-543 | 2026-04-27 | Contractor | Consultant | Daily Report - Day 543 | Sunny | 34C | 127 | 8 | Ongoing: Plastering at multiple zones. | 74.38% | None | Site_View_543.jpg | Michelle Lopez | Eng. Abdullah (PM) | Emily Tyler
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-544 | 2026-04-28 | Contractor | Consultant | Daily Report - Day 544 | Sunny | 31C | 52 | 16 | Ongoing: Gypsum Ceiling at multiple zones. | 74.52% | Material Delay | Site_View_544.jpg | Alison Knight | Eng. Abdullah (PM) | Lindsey Schmidt
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-545 | 2026-04-29 | Contractor | Consultant | Daily Report - Day 545 | Sunny | 26C | 69 | 7 | Ongoing: Plastering at multiple zones. | 74.66% | None | Site_View_545.jpg | Douglas Phillips | Eng. Abdullah (PM) | Justin Monroe
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-546 | 2026-04-30 | Contractor | Consultant | Daily Report - Day 546 | Sunny | 32C | 92 | 5 | Ongoing: Door Installation at multiple zones. | 74.79% | None | Site_View_546.jpg | Steven Tucker | Eng. Abdullah (PM) | Sarah Cunningham
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-548 | 2026-05-02 | Contractor | Consultant | Daily Report - Day 548 | Very Hot | 41C | 131 | 16 | Ongoing: Gypsum Ceiling at multiple zones. | 75.07% | None | Site_View_548.jpg | Jeffrey Watts | Eng. Abdullah (PM) | Shannon Guerrero MD
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-549 | 2026-05-03 | Contractor | Consultant | Daily Report - Day 549 | Very Hot | 43C | 71 | 7 | Ongoing: Ceramic Tiling at multiple zones. | 75.21% | Material Delay | Site_View_549.jpg | Tiffany Wood | Eng. Abdullah (PM) | Jonathan Adams
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-550 | 2026-05-04 | Contractor | Consultant | Daily Report - Day 550 | Very Hot | 47C | 135 | 17 | Ongoing: Gypsum Ceiling at multiple zones. | 75.34% | Material Delay | Site_View_550.jpg | Jacob Greer | Eng. Abdullah (PM) | Stephanie Gamble
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-551 | 2026-05-05 | Contractor | Consultant | Daily Report - Day 551 | Sunny | 21C | 130 | 19 | Ongoing: Plastering at multiple zones. | 75.48% | None | Site_View_551.jpg | Brian Middleton | Eng. Abdullah (PM) | Beth Mills
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-552 | 2026-05-06 | Contractor | Consultant | Daily Report - Day 552 | Sunny | 23C | 75 | 14 | Ongoing: Door Installation at multiple zones. | 75.62% | None | Site_View_552.jpg | Jonathon Klein | Eng. Abdullah (PM) | Dawn Hernandez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-553 | 2026-05-07 | Contractor | Consultant | Daily Report - Day 553 | Sunny | 24C | 57 | 18 | Ongoing: Painting First Coat at multiple zones. | 75.75% | None | Site_View_553.jpg | Robin Patrick | Eng. Abdullah (PM) | Patricia Blevins
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-555 | 2026-05-09 | Contractor | Consultant | Daily Report - Day 555 | Very Hot | 48C | 78 | 7 | Ongoing: Ceramic Tiling at multiple zones. | 76.03% | None | Site_View_555.jpg | Phillip Johnson | Eng. Abdullah (PM) | Misty Thomas
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-556 | 2026-05-10 | Contractor | Consultant | Daily Report - Day 556 | Sunny | 20C | 141 | 9 | Ongoing: Plastering at multiple zones. | 76.16% | None | Site_View_556.jpg | Brandon Baldwin | Eng. Abdullah (PM) | Meghan Jones
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-557 | 2026-05-11 | Contractor | Consultant | Daily Report - Day 557 | Very Hot | 47C | 42 | 9 | Ongoing: Painting First Coat at multiple zones. | 76.3% | None | Site_View_557.jpg | Virginia Sexton | Eng. Abdullah (PM) | David Phillips
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-558 | 2026-05-12 | Contractor | Consultant | Daily Report - Day 558 | Sunny | 24C | 122 | 9 | Ongoing: Plastering at multiple zones. | 76.44% | None | Site_View_558.jpg | Nicole Carpenter | Eng. Abdullah (PM) | Mrs. Diane Chavez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-559 | 2026-05-13 | Contractor | Consultant | Daily Report - Day 559 | Very Hot | 42C | 83 | 16 | Ongoing: Gypsum Ceiling at multiple zones. | 76.58% | None | Site_View_559.jpg | Timothy Jackson | Eng. Abdullah (PM) | Shane Rodriguez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-560 | 2026-05-14 | Contractor | Consultant | Daily Report - Day 560 | Sunny | 36C | 126 | 5 | Ongoing: Blockwork at multiple zones. | 76.71% | Material Delay | Site_View_560.jpg | Eric Sullivan | Eng. Abdullah (PM) | Jonathan Thomas
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-562 | 2026-05-16 | Contractor | Consultant | Daily Report - Day 562 | Sunny | 24C | 119 | 8 | Ongoing: Plastering at multiple zones. | 76.99% | None | Site_View_562.jpg | Mrs. Lindsey Richards PhD | Eng. Abdullah (PM) | Melinda Nelson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-563 | 2026-05-17 | Contractor | Consultant | Daily Report - Day 563 | Very Hot | 42C | 76 | 17 | Ongoing: Plastering at multiple zones. | 77.12% | None | Site_View_563.jpg | Randall Mullins | Eng. Abdullah (PM) | Karen Meadows
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-564 | 2026-05-18 | Contractor | Consultant | Daily Report - Day 564 | Very Hot | 47C | 141 | 9 | Ongoing: Gypsum Ceiling at multiple zones. | 77.26% | None | Site_View_564.jpg | David Atkins | Eng. Abdullah (PM) | Donna Miller
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-565 | 2026-05-19 | Contractor | Consultant | Daily Report - Day 565 | Sunny | 38C | 49 | 16 | Ongoing: Blockwork at multiple zones. | 77.4% | None | Site_View_565.jpg | Justin Taylor | Eng. Abdullah (PM) | Robert Robinson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-566 | 2026-05-20 | Contractor | Consultant | Daily Report - Day 566 | Very Hot | 43C | 122 | 12 | Ongoing: Ceramic Tiling at multiple zones. | 77.53% | None | Site_View_566.jpg | Donna Chan | Eng. Abdullah (PM) | Caitlin English
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-567 | 2026-05-21 | Contractor | Consultant | Daily Report - Day 567 | Sunny | 29C | 142 | 16 | Ongoing: Door Installation at multiple zones. | 77.67% | None | Site_View_567.jpg | Kelly Martin | Eng. Abdullah (PM) | Danielle Villarreal
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-569 | 2026-05-23 | Contractor | Consultant | Daily Report - Day 569 | Very Hot | 42C | 134 | 13 | Ongoing: Blockwork at multiple zones. | 77.95% | None | Site_View_569.jpg | Mr. Brett Jackson | Eng. Abdullah (PM) | Christine Horn
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-570 | 2026-05-24 | Contractor | Consultant | Daily Report - Day 570 | Sunny | 23C | 47 | 18 | Ongoing: Painting First Coat at multiple zones. | 78.08% | None | Site_View_570.jpg | Dalton Miles | Eng. Abdullah (PM) | Cynthia Lee
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-571 | 2026-05-25 | Contractor | Consultant | Daily Report - Day 571 | Sunny | 38C | 86 | 12 | Ongoing: Plastering at multiple zones. | 78.22% | Material Delay | Site_View_571.jpg | Mary Rodriguez | Eng. Abdullah (PM) | Zachary Martin
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-572 | 2026-05-26 | Contractor | Consultant | Daily Report - Day 572 | Sunny | 31C | 67 | 14 | Ongoing: Blockwork at multiple zones. | 78.36% | None | Site_View_572.jpg | Brett Church | Eng. Abdullah (PM) | Donna Smith
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-573 | 2026-05-27 | Contractor | Consultant | Daily Report - Day 573 | Sunny | 20C | 128 | 20 | Ongoing: Blockwork at multiple zones. | 78.49% | None | Site_View_573.jpg | Marco Miller | Eng. Abdullah (PM) | Dr. Kenneth Ward
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-574 | 2026-05-28 | Contractor | Consultant | Daily Report - Day 574 | Sunny | 23C | 103 | 12 | Ongoing: Painting First Coat at multiple zones. | 78.63% | None | Site_View_574.jpg | Roger Brown | Eng. Abdullah (PM) | Kenneth Bailey
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-576 | 2026-05-30 | Contractor | Consultant | Daily Report - Day 576 | Sunny | 24C | 149 | 8 | Ongoing: Gypsum Ceiling at multiple zones. | 78.9% | None | Site_View_576.jpg | Ms. Megan Carroll | Eng. Abdullah (PM) | Jacob Kim
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-577 | 2026-05-31 | Contractor | Consultant | Daily Report - Day 577 | Sunny | 36C | 49 | 5 | Ongoing: Plastering at multiple zones. | 79.04% | None | Site_View_577.jpg | Brian Williams | Eng. Abdullah (PM) | Jonathan Craig
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-578 | 2026-06-01 | Contractor | Consultant | Daily Report - Day 578 | Very Hot | 40C | 112 | 15 | Ongoing: Painting First Coat at multiple zones. | 79.18% | None | Site_View_578.jpg | Lawrence Cooper | Eng. Abdullah (PM) | Pamela Henderson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-579 | 2026-06-02 | Contractor | Consultant | Daily Report - Day 579 | Sunny | 26C | 102 | 16 | Ongoing: Ceramic Tiling at multiple zones. | 79.32% | None | Site_View_579.jpg | Cory Hutchinson | Eng. Abdullah (PM) | Ernest Hall
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-580 | 2026-06-03 | Contractor | Consultant | Daily Report - Day 580 | Sunny | 36C | 78 | 19 | Ongoing: Blockwork at multiple zones. | 79.45% | None | Site_View_580.jpg | Alicia Miller | Eng. Abdullah (PM) | Alexis Haas
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-581 | 2026-06-04 | Contractor | Consultant | Daily Report - Day 581 | Sunny | 29C | 107 | 10 | Ongoing: Plastering at multiple zones. | 79.59% | None | Site_View_581.jpg | Michael Clark | Eng. Abdullah (PM) | Cody Gordon
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-583 | 2026-06-06 | Contractor | Consultant | Daily Report - Day 583 | Sunny | 24C | 103 | 16 | Ongoing: Blockwork at multiple zones. | 79.86% | None | Site_View_583.jpg | Vanessa Curtis | Eng. Abdullah (PM) | Shirley Diaz
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-584 | 2026-06-07 | Contractor | Consultant | Daily Report - Day 584 | Sunny | 37C | 51 | 9 | Ongoing: Gypsum Ceiling at multiple zones. | 80.0% | None | Site_View_584.jpg | April Tyler | Eng. Abdullah (PM) | David Ross
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-585 | 2026-06-08 | Contractor | Consultant | Daily Report - Day 585 | Sunny | 36C | 112 | 17 | Ongoing: Ceramic Tiling at multiple zones. | 80.14% | None | Site_View_585.jpg | Justin Smith | Eng. Abdullah (PM) | Kelly Humphrey
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-586 | 2026-06-09 | Contractor | Consultant | Daily Report - Day 586 | Sunny | 37C | 96 | 14 | Ongoing: Door Installation at multiple zones. | 80.27% | None | Site_View_586.jpg | Jeffery Klein | Eng. Abdullah (PM) | Jennifer Moore
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-587 | 2026-06-10 | Contractor | Consultant | Daily Report - Day 587 | Sunny | 35C | 96 | 11 | Ongoing: Ceramic Tiling at multiple zones. | 80.41% | None | Site_View_587.jpg | Alvin Hicks | Eng. Abdullah (PM) | Joseph Montgomery
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-588 | 2026-06-11 | Contractor | Consultant | Daily Report - Day 588 | Very Hot | 40C | 95 | 13 | Ongoing: Plastering at multiple zones. | 80.55% | Material Delay | Site_View_588.jpg | Mitchell Jimenez | Eng. Abdullah (PM) | Ms. Lindsey English DDS
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-590 | 2026-06-13 | Contractor | Consultant | Daily Report - Day 590 | Very Hot | 46C | 140 | 18 | Ongoing: Gypsum Ceiling at multiple zones. | 80.82% | None | Site_View_590.jpg | Chelsea Dennis | Eng. Abdullah (PM) | Brenda Morgan
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-591 | 2026-06-14 | Contractor | Consultant | Daily Report - Day 591 | Very Hot | 45C | 65 | 7 | Ongoing: Plastering at multiple zones. | 80.96% | None | Site_View_591.jpg | Guy Wise | Eng. Abdullah (PM) | Kimberly Luna
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-592 | 2026-06-15 | Contractor | Consultant | Daily Report - Day 592 | Very Hot | 46C | 90 | 20 | Ongoing: Gypsum Ceiling at multiple zones. | 81.1% | None | Site_View_592.jpg | Erica Pollard MD | Eng. Abdullah (PM) | Randy Watts
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-593 | 2026-06-16 | Contractor | Consultant | Daily Report - Day 593 | Sunny | 29C | 93 | 19 | Ongoing: Painting First Coat at multiple zones. | 81.23% | None | Site_View_593.jpg | Jeffrey Cortez | Eng. Abdullah (PM) | Stephanie Webb
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-594 | 2026-06-17 | Contractor | Consultant | Daily Report - Day 594 | Sunny | 23C | 35 | 9 | Ongoing: Plastering at multiple zones. | 81.37% | None | Site_View_594.jpg | Ryan Wheeler | Eng. Abdullah (PM) | Brian White
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-595 | 2026-06-18 | Contractor | Consultant | Daily Report - Day 595 | Sunny | 30C | 105 | 7 | Ongoing: Blockwork at multiple zones. | 81.51% | None | Site_View_595.jpg | Kenneth Willis | Eng. Abdullah (PM) | Eric Lawson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-597 | 2026-06-20 | Contractor | Consultant | Daily Report - Day 597 | Sunny | 23C | 120 | 14 | Ongoing: Blockwork at multiple zones. | 81.78% | None | Site_View_597.jpg | Gina Reese | Eng. Abdullah (PM) | Timothy Cherry
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-598 | 2026-06-21 | Contractor | Consultant | Daily Report - Day 598 | Sunny | 24C | 87 | 14 | Ongoing: Gypsum Ceiling at multiple zones. | 81.92% | None | Site_View_598.jpg | Logan Perkins | Eng. Abdullah (PM) | Brandon Jones
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-599 | 2026-06-22 | Contractor | Consultant | Daily Report - Day 599 | Very Hot | 46C | 52 | 8 | Ongoing: Plastering at multiple zones. | 82.05% | None | Site_View_599.jpg | Ronald Allen | Eng. Abdullah (PM) | Alicia Fitzgerald
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-600 | 2026-06-23 | Contractor | Consultant | Daily Report - Day 600 | Very Hot | 47C | 33 | 12 | Ongoing: Plastering at multiple zones. | 82.19% | None | Site_View_600.jpg | Valerie Johnson | Eng. Abdullah (PM) | Austin Carey
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-601 | 2026-06-24 | Contractor | Consultant | Daily Report - Day 601 | Sunny | 27C | 72 | 12 | Ongoing: Painting First Coat at multiple zones. | 82.33% | None | Site_View_601.jpg | Jacqueline Barry | Eng. Abdullah (PM) | Anthony Mcguire
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-602 | 2026-06-25 | Contractor | Consultant | Daily Report - Day 602 | Sunny | 21C | 35 | 17 | Ongoing: Plastering at multiple zones. | 82.47% | None | Site_View_602.jpg | Lauren Morales | Eng. Abdullah (PM) | David Cohen
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-604 | 2026-06-27 | Contractor | Consultant | Daily Report - Day 604 | Sunny | 36C | 42 | 15 | Ongoing: Plastering at multiple zones. | 82.74% | None | Site_View_604.jpg | Amanda Butler | Eng. Abdullah (PM) | Kaylee Lopez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-605 | 2026-06-28 | Contractor | Consultant | Daily Report - Day 605 | Sunny | 21C | 54 | 14 | Ongoing: Plastering at multiple zones. | 82.88% | None | Site_View_605.jpg | Leslie Richardson | Eng. Abdullah (PM) | Mark Young
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-606 | 2026-06-29 | Contractor | Consultant | Daily Report - Day 606 | Sunny | 32C | 138 | 16 | Ongoing: Plastering at multiple zones. | 83.01% | None | Site_View_606.jpg | Andrew Johnson | Eng. Abdullah (PM) | Janet Hill
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-607 | 2026-06-30 | Contractor | Consultant | Daily Report - Day 607 | Sunny | 36C | 141 | 14 | Ongoing: Gypsum Ceiling at multiple zones. | 83.15% | None | Site_View_607.jpg | Ashley Johnson | Eng. Abdullah (PM) | Aaron Woods
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-608 | 2026-07-01 | Contractor | Consultant | Daily Report - Day 608 | Very Hot | 46C | 52 | 7 | Ongoing: Painting First Coat at multiple zones. | 83.29% | None | Site_View_608.jpg | Robert Williamson | Eng. Abdullah (PM) | Mark Fuller
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-609 | 2026-07-02 | Contractor | Consultant | Daily Report - Day 609 | Sunny | 26C | 134 | 14 | Ongoing: Ceramic Tiling at multiple zones. | 83.42% | None | Site_View_609.jpg | Linda Mcintosh | Eng. Abdullah (PM) | Mrs. Jennifer Freeman
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-611 | 2026-07-04 | Contractor | Consultant | Daily Report - Day 611 | Very Hot | 42C | 128 | 7 | Ongoing: Door Installation at multiple zones. | 83.7% | None | Site_View_611.jpg | Nathan Browning | Eng. Abdullah (PM) | Robert Barajas
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-612 | 2026-07-05 | Contractor | Consultant | Daily Report - Day 612 | Sunny | 39C | 92 | 18 | Ongoing: Door Installation at multiple zones. | 83.84% | None | Site_View_612.jpg | Kyle Thomas | Eng. Abdullah (PM) | Randall Thompson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-613 | 2026-07-06 | Contractor | Consultant | Daily Report - Day 613 | Sunny | 30C | 81 | 10 | Ongoing: Gypsum Ceiling at multiple zones. | 83.97% | None | Site_View_613.jpg | Tiffany Long | Eng. Abdullah (PM) | Suzanne Roberson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-614 | 2026-07-07 | Contractor | Consultant | Daily Report - Day 614 | Sunny | 36C | 102 | 16 | Ongoing: Plastering at multiple zones. | 84.11% | None | Site_View_614.jpg | Jessica Wyatt | Eng. Abdullah (PM) | Michael Howard
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-615 | 2026-07-08 | Contractor | Consultant | Daily Report - Day 615 | Sunny | 37C | 93 | 11 | Ongoing: Gypsum Ceiling at multiple zones. | 84.25% | Material Delay | Site_View_615.jpg | Ricky Wilson | Eng. Abdullah (PM) | Monique Cruz
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-616 | 2026-07-09 | Contractor | Consultant | Daily Report - Day 616 | Sunny | 23C | 113 | 11 | Ongoing: Gypsum Ceiling at multiple zones. | 84.38% | None | Site_View_616.jpg | Michael Hernandez | Eng. Abdullah (PM) | Robin Garcia
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-618 | 2026-07-11 | Contractor | Consultant | Daily Report - Day 618 | Sunny | 36C | 61 | 8 | Ongoing: Blockwork at multiple zones. | 84.66% | None | Site_View_618.jpg | Mrs. Kimberly Walker | Eng. Abdullah (PM) | Nicole Gillespie
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-619 | 2026-07-12 | Contractor | Consultant | Daily Report - Day 619 | Sunny | 28C | 128 | 8 | Ongoing: Gypsum Ceiling at multiple zones. | 84.79% | None | Site_View_619.jpg | Mary Ray | Eng. Abdullah (PM) | Haley Reilly DDS
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-620 | 2026-07-13 | Contractor | Consultant | Daily Report - Day 620 | Very Hot | 46C | 40 | 12 | Ongoing: Gypsum Ceiling at multiple zones. | 84.93% | None | Site_View_620.jpg | Benjamin Ford | Eng. Abdullah (PM) | Virginia Lucas
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-621 | 2026-07-14 | Contractor | Consultant | Daily Report - Day 621 | Sunny | 34C | 34 | 18 | Ongoing: Painting First Coat at multiple zones. | 85.07% | None | Site_View_621.jpg | Paul Daniels | Eng. Abdullah (PM) | Christian Walker
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-622 | 2026-07-15 | Contractor | Consultant | Daily Report - Day 622 | Very Hot | 42C | 67 | 19 | Ongoing: Ceramic Tiling at multiple zones. | 85.21% | None | Site_View_622.jpg | Justin White | Eng. Abdullah (PM) | Ariel Levy
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-623 | 2026-07-16 | Contractor | Consultant | Daily Report - Day 623 | Sunny | 35C | 65 | 18 | Ongoing: Ceramic Tiling at multiple zones. | 85.34% | None | Site_View_623.jpg | Nicole Watson | Eng. Abdullah (PM) | Joseph Conley
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-625 | 2026-07-18 | Contractor | Consultant | Daily Report - Day 625 | Sunny | 37C | 137 | 17 | Ongoing: Plastering at multiple zones. | 85.62% | None | Site_View_625.jpg | Jennifer Donaldson | Eng. Abdullah (PM) | Mary Wright
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-626 | 2026-07-19 | Contractor | Consultant | Daily Report - Day 626 | Sunny | 38C | 49 | 19 | Ongoing: Ceramic Tiling at multiple zones. | 85.75% | None | Site_View_626.jpg | Cody Fox | Eng. Abdullah (PM) | Keith Harris
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-627 | 2026-07-20 | Contractor | Consultant | Daily Report - Day 627 | Sunny | 36C | 42 | 19 | Ongoing: Painting First Coat at multiple zones. | 85.89% | None | Site_View_627.jpg | Tiffany Christian | Eng. Abdullah (PM) | Ian Sweeney
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-628 | 2026-07-21 | Contractor | Consultant | Daily Report - Day 628 | Sunny | 24C | 69 | 19 | Ongoing: Gypsum Ceiling at multiple zones. | 86.03% | None | Site_View_628.jpg | Jose Bender | Eng. Abdullah (PM) | Nicholas Davis
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-629 | 2026-07-22 | Contractor | Consultant | Daily Report - Day 629 | Sunny | 33C | 104 | 16 | Ongoing: Blockwork at multiple zones. | 86.16% | None | Site_View_629.jpg | Whitney Sherman | Eng. Abdullah (PM) | Adrian Graham
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-630 | 2026-07-23 | Contractor | Consultant | Daily Report - Day 630 | Sunny | 33C | 86 | 19 | Ongoing: Gypsum Ceiling at multiple zones. | 86.3% | Material Delay | Site_View_630.jpg | Cheryl Harris | Eng. Abdullah (PM) | Alex Diaz
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-632 | 2026-07-25 | Contractor | Consultant | Daily Report - Day 632 | Sunny | 39C | 47 | 19 | Ongoing: Plastering at multiple zones. | 86.58% | None | Site_View_632.jpg | Gerald Nicholson | Eng. Abdullah (PM) | Lauren Collins
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-633 | 2026-07-26 | Contractor | Consultant | Daily Report - Day 633 | Sunny | 37C | 133 | 5 | Ongoing: Blockwork at multiple zones. | 86.71% | Material Delay | Site_View_633.jpg | Blake Hess | Eng. Abdullah (PM) | Ryan Gonzalez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-634 | 2026-07-27 | Contractor | Consultant | Daily Report - Day 634 | Sunny | 32C | 55 | 17 | Ongoing: Blockwork at multiple zones. | 86.85% | None | Site_View_634.jpg | Jose Gordon | Eng. Abdullah (PM) | Miss Debbie Smith
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-635 | 2026-07-28 | Contractor | Consultant | Daily Report - Day 635 | Very Hot | 42C | 143 | 16 | Ongoing: Blockwork at multiple zones. | 86.99% | None | Site_View_635.jpg | Edgar Reynolds | Eng. Abdullah (PM) | Jessica Estrada
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-636 | 2026-07-29 | Contractor | Consultant | Daily Report - Day 636 | Very Hot | 46C | 99 | 6 | Ongoing: Ceramic Tiling at multiple zones. | 87.12% | Material Delay | Site_View_636.jpg | Andrea Moore | Eng. Abdullah (PM) | Billy Hale
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-637 | 2026-07-30 | Contractor | Consultant | Daily Report - Day 637 | Very Hot | 40C | 55 | 12 | Ongoing: Ceramic Tiling at multiple zones. | 87.26% | None | Site_View_637.jpg | Erin Cook | Eng. Abdullah (PM) | Vanessa Mckay
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-639 | 2026-08-01 | Contractor | Consultant | Daily Report - Day 639 | Sunny | 39C | 144 | 20 | Ongoing: Blockwork at multiple zones. | 87.53% | None | Site_View_639.jpg | Stephen Johnston | Eng. Abdullah (PM) | Christopher Hernandez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-640 | 2026-08-02 | Contractor | Consultant | Daily Report - Day 640 | Very Hot | 43C | 96 | 18 | Ongoing: Ceramic Tiling at multiple zones. | 87.67% | None | Site_View_640.jpg | Jessica Turner | Eng. Abdullah (PM) | Martha Mitchell
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-641 | 2026-08-03 | Contractor | Consultant | Daily Report - Day 641 | Sunny | 30C | 53 | 20 | Ongoing: Ceramic Tiling at multiple zones. | 87.81% | None | Site_View_641.jpg | Teresa Powell | Eng. Abdullah (PM) | Kathryn Carter
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-642 | 2026-08-04 | Contractor | Consultant | Daily Report - Day 642 | Sunny | 31C | 150 | 7 | Ongoing: Plastering at multiple zones. | 87.95% | Material Delay | Site_View_642.jpg | Samantha Hernandez | Eng. Abdullah (PM) | Mary Pruitt
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-643 | 2026-08-05 | Contractor | Consultant | Daily Report - Day 643 | Sunny | 23C | 90 | 15 | Ongoing: Blockwork at multiple zones. | 88.08% | None | Site_View_643.jpg | Laura Perez | Eng. Abdullah (PM) | Joshua Schmidt
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-644 | 2026-08-06 | Contractor | Consultant | Daily Report - Day 644 | Sunny | 39C | 83 | 12 | Ongoing: Ceramic Tiling at multiple zones. | 88.22% | None | Site_View_644.jpg | Eric Green | Eng. Abdullah (PM) | Dylan Wyatt
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-646 | 2026-08-08 | Contractor | Consultant | Daily Report - Day 646 | Sunny | 26C | 134 | 10 | Ongoing: Painting First Coat at multiple zones. | 88.49% | None | Site_View_646.jpg | Tiffany Wise | Eng. Abdullah (PM) | Sara Norton
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-647 | 2026-08-09 | Contractor | Consultant | Daily Report - Day 647 | Very Hot | 41C | 106 | 6 | Ongoing: Blockwork at multiple zones. | 88.63% | None | Site_View_647.jpg | Joel Kent | Eng. Abdullah (PM) | Christina Ho
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-648 | 2026-08-10 | Contractor | Consultant | Daily Report - Day 648 | Very Hot | 43C | 74 | 18 | Ongoing: Plastering at multiple zones. | 88.77% | Material Delay | Site_View_648.jpg | Ricky Washington | Eng. Abdullah (PM) | Christopher Simpson
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-649 | 2026-08-11 | Contractor | Consultant | Daily Report - Day 649 | Very Hot | 44C | 57 | 9 | Ongoing: Blockwork at multiple zones. | 88.9% | None | Site_View_649.jpg | Joanna Lucero | Eng. Abdullah (PM) | Nicholas Nichols
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-650 | 2026-08-12 | Contractor | Consultant | Daily Report - Day 650 | Sunny | 34C | 62 | 12 | Ongoing: Ceramic Tiling at multiple zones. | 89.04% | None | Site_View_650.jpg | Megan Johnson | Eng. Abdullah (PM) | Jonathan Martin
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-651 | 2026-08-13 | Contractor | Consultant | Daily Report - Day 651 | Sunny | 36C | 111 | 6 | Ongoing: Ceramic Tiling at multiple zones. | 89.18% | Material Delay | Site_View_651.jpg | Tara Little | Eng. Abdullah (PM) | Michael Buck
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-653 | 2026-08-15 | Contractor | Consultant | Daily Report - Day 653 | Sunny | 21C | 44 | 7 | Ongoing: Door Installation at multiple zones. | 89.45% | None | Site_View_653.jpg | Jose Lloyd | Eng. Abdullah (PM) | James Smith
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-654 | 2026-08-16 | Contractor | Consultant | Daily Report - Day 654 | Sunny | 39C | 96 | 20 | Ongoing: Ceramic Tiling at multiple zones. | 89.59% | None | Site_View_654.jpg | Blake Garrett | Eng. Abdullah (PM) | Christina Gutierrez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-655 | 2026-08-17 | Contractor | Consultant | Daily Report - Day 655 | Sunny | 21C | 141 | 11 | Ongoing: Gypsum Ceiling at multiple zones. | 89.73% | None | Site_View_655.jpg | Nicole Ayala | Eng. Abdullah (PM) | Tammy Hines
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-656 | 2026-08-18 | Contractor | Consultant | Daily Report - Day 656 | Very Hot | 47C | 125 | 14 | Ongoing: Blockwork at multiple zones. | 89.86% | None | Site_View_656.jpg | Bryan Smith | Eng. Abdullah (PM) | William Carroll
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-657 | 2026-08-19 | Contractor | Consultant | Daily Report - Day 657 | Sunny | 21C | 52 | 10 | Ongoing: Plastering at multiple zones. | 90.0% | None | Site_View_657.jpg | Jill Murphy MD | Eng. Abdullah (PM) | Dorothy Jenkins
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-658 | 2026-08-20 | Contractor | Consultant | Daily Report - Day 658 | Sunny | 36C | 62 | 8 | Ongoing: Blockwork at multiple zones. | 90.14% | None | Site_View_658.jpg | Michele Williamson | Eng. Abdullah (PM) | Kelsey Russell
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-660 | 2026-08-22 | Contractor | Consultant | Daily Report - Day 660 | Sunny | 35C | 129 | 19 | Ongoing: Painting First Coat at multiple zones. | 90.41% | None | Site_View_660.jpg | Bruce Morton | Eng. Abdullah (PM) | Angela Fields
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-661 | 2026-08-23 | Contractor | Consultant | Daily Report - Day 661 | Sunny | 39C | 134 | 10 | Ongoing: Painting First Coat at multiple zones. | 90.55% | None | Site_View_661.jpg | Judith Reyes | Eng. Abdullah (PM) | Bruce Murphy
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-662 | 2026-08-24 | Contractor | Consultant | Daily Report - Day 662 | Sunny | 30C | 68 | 13 | Ongoing: Painting First Coat at multiple zones. | 90.68% | None | Site_View_662.jpg | Beth Ortega | Eng. Abdullah (PM) | Wendy Carney
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-663 | 2026-08-25 | Contractor | Consultant | Daily Report - Day 663 | Sunny | 33C | 76 | 18 | Ongoing: Blockwork at multiple zones. | 90.82% | None | Site_View_663.jpg | Alejandro Moore | Eng. Abdullah (PM) | Ashley Williams
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-664 | 2026-08-26 | Contractor | Consultant | Daily Report - Day 664 | Sunny | 21C | 93 | 8 | Ongoing: Plastering at multiple zones. | 90.96% | None | Site_View_664.jpg | Dennis Miller | Eng. Abdullah (PM) | Phyllis Brown
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-665 | 2026-08-27 | Contractor | Consultant | Daily Report - Day 665 | Sunny | 38C | 53 | 12 | Ongoing: Painting First Coat at multiple zones. | 91.1% | None | Site_View_665.jpg | Robert Smith | Eng. Abdullah (PM) | Stephen May
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-667 | 2026-08-29 | Contractor | Consultant | Daily Report - Day 667 | Very Hot | 44C | 37 | 9 | Ongoing: Plastering at multiple zones. | 91.37% | None | Site_View_667.jpg | Alicia Terry | Eng. Abdullah (PM) | Mrs. Tracy Garcia
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-668 | 2026-08-30 | Contractor | Consultant | Daily Report - Day 668 | Sunny | 33C | 130 | 12 | Ongoing: Plastering at multiple zones. | 91.51% | None | Site_View_668.jpg | Brent Brooks | Eng. Abdullah (PM) | Patricia Ryan
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-669 | 2026-08-31 | Contractor | Consultant | Daily Report - Day 669 | Sunny | 29C | 137 | 6 | Ongoing: Door Installation at multiple zones. | 91.64% | None | Site_View_669.jpg | Tracy Long | Eng. Abdullah (PM) | Bradley Diaz
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-670 | 2026-09-01 | Contractor | Consultant | Daily Report - Day 670 | Sunny | 38C | 43 | 17 | Ongoing: Blockwork at multiple zones. | 91.78% | None | Site_View_670.jpg | Parker Parker | Eng. Abdullah (PM) | Charles Montgomery
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-671 | 2026-09-02 | Contractor | Consultant | Daily Report - Day 671 | Very Hot | 43C | 104 | 6 | Ongoing: Plastering at multiple zones. | 91.92% | None | Site_View_671.jpg | Michael Smith | Eng. Abdullah (PM) | Joseph Snyder
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-672 | 2026-09-03 | Contractor | Consultant | Daily Report - Day 672 | Very Hot | 44C | 134 | 10 | Ongoing: Painting First Coat at multiple zones. | 92.05% | None | Site_View_672.jpg | Matthew French | Eng. Abdullah (PM) | Alexandra Bonilla
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-674 | 2026-09-05 | Contractor | Consultant | Daily Report - Day 674 | Sunny | 26C | 50 | 9 | Ongoing: Ceramic Tiling at multiple zones. | 92.33% | None | Site_View_674.jpg | Charles Sandoval | Eng. Abdullah (PM) | Mary Murphy
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-675 | 2026-09-06 | Contractor | Consultant | Daily Report - Day 675 | Sunny | 30C | 83 | 20 | Ongoing: Door Installation at multiple zones. | 92.47% | None | Site_View_675.jpg | Matthew Berg | Eng. Abdullah (PM) | Vanessa Maynard
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-676 | 2026-09-07 | Contractor | Consultant | Daily Report - Day 676 | Sunny | 37C | 42 | 12 | Ongoing: Plastering at multiple zones. | 92.6% | None | Site_View_676.jpg | Carrie Jimenez | Eng. Abdullah (PM) | Martin Garcia
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-677 | 2026-09-08 | Contractor | Consultant | Daily Report - Day 677 | Sunny | 23C | 89 | 7 | Ongoing: Blockwork at multiple zones. | 92.74% | None | Site_View_677.jpg | Michael Hudson | Eng. Abdullah (PM) | Robert Robbins
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-678 | 2026-09-09 | Contractor | Consultant | Daily Report - Day 678 | Sunny | 22C | 132 | 9 | Ongoing: Painting First Coat at multiple zones. | 92.88% | Material Delay | Site_View_678.jpg | Kevin Hunter | Eng. Abdullah (PM) | Peter Koch
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-679 | 2026-09-10 | Contractor | Consultant | Daily Report - Day 679 | Sunny | 21C | 71 | 5 | Ongoing: Painting First Coat at multiple zones. | 93.01% | None | Site_View_679.jpg | Caitlin Gray | Eng. Abdullah (PM) | Stephanie Miller
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-681 | 2026-09-12 | Contractor | Consultant | Daily Report - Day 681 | Sunny | 38C | 79 | 12 | Ongoing: Plastering at multiple zones. | 93.29% | None | Site_View_681.jpg | Jessica Nunez | Eng. Abdullah (PM) | Jasmine Chavez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-682 | 2026-09-13 | Contractor | Consultant | Daily Report - Day 682 | Very Hot | 41C | 145 | 7 | Ongoing: Plastering at multiple zones. | 93.42% | None | Site_View_682.jpg | Jason Alexander | Eng. Abdullah (PM) | Meghan Herrera
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-683 | 2026-09-14 | Contractor | Consultant | Daily Report - Day 683 | Sunny | 25C | 118 | 12 | Ongoing: Door Installation at multiple zones. | 93.56% | None | Site_View_683.jpg | Tiffany Bird | Eng. Abdullah (PM) | Anita Smith
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-684 | 2026-09-15 | Contractor | Consultant | Daily Report - Day 684 | Sunny | 33C | 117 | 6 | Ongoing: Gypsum Ceiling at multiple zones. | 93.7% | None | Site_View_684.jpg | Daniel Williamson | Eng. Abdullah (PM) | Kayla Wolfe
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-685 | 2026-09-16 | Contractor | Consultant | Daily Report - Day 685 | Very Hot | 42C | 47 | 17 | Ongoing: Ceramic Tiling at multiple zones. | 93.84% | None | Site_View_685.jpg | Gabriel King | Eng. Abdullah (PM) | Natasha James
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-686 | 2026-09-17 | Contractor | Consultant | Daily Report - Day 686 | Sunny | 20C | 107 | 14 | Ongoing: Plastering at multiple zones. | 93.97% | None | Site_View_686.jpg | Xavier Ramos | Eng. Abdullah (PM) | Barbara Cole
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-688 | 2026-09-19 | Contractor | Consultant | Daily Report - Day 688 | Very Hot | 48C | 44 | 17 | Ongoing: Door Installation at multiple zones. | 94.25% | Material Delay | Site_View_688.jpg | Justin Richmond | Eng. Abdullah (PM) | Erin Galvan
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-689 | 2026-09-20 | Contractor | Consultant | Daily Report - Day 689 | Very Hot | 41C | 117 | 7 | Ongoing: Painting First Coat at multiple zones. | 94.38% | Material Delay | Site_View_689.jpg | Robert Curtis | Eng. Abdullah (PM) | Amber Tran
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-690 | 2026-09-21 | Contractor | Consultant | Daily Report - Day 690 | Sunny | 32C | 57 | 11 | Ongoing: Painting First Coat at multiple zones. | 94.52% | None | Site_View_690.jpg | Lawrence Jensen | Eng. Abdullah (PM) | Jessica Thomas DDS
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-691 | 2026-09-22 | Contractor | Consultant | Daily Report - Day 691 | Very Hot | 46C | 138 | 19 | Ongoing: Painting First Coat at multiple zones. | 94.66% | Material Delay | Site_View_691.jpg | Don Dalton | Eng. Abdullah (PM) | Nicole Oliver
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-692 | 2026-09-23 | Contractor | Consultant | Daily Report - Day 692 | Sunny | 26C | 115 | 18 | Ongoing: Plastering at multiple zones. | 94.79% | None | Site_View_692.jpg | Cassandra Adams | Eng. Abdullah (PM) | Kyle Fischer
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-693 | 2026-09-24 | Contractor | Consultant | Daily Report - Day 693 | Very Hot | 44C | 77 | 18 | Ongoing: Plastering at multiple zones. | 94.93% | None | Site_View_693.jpg | Katherine Rivera | Eng. Abdullah (PM) | Timothy Rivers
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-695 | 2026-09-26 | Contractor | Consultant | Daily Report - Day 695 | Sunny | 28C | 144 | 14 | Ongoing: Door Installation at multiple zones. | 95.21% | None | Site_View_695.jpg | Casey Martinez | Eng. Abdullah (PM) | Heidi Bailey
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-696 | 2026-09-27 | Contractor | Consultant | Daily Report - Day 696 | Sunny | 39C | 61 | 10 | Ongoing: Plastering at multiple zones. | 95.34% | None | Site_View_696.jpg | Raymond Harper | Eng. Abdullah (PM) | Raymond Ingram
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-697 | 2026-09-28 | Contractor | Consultant | Daily Report - Day 697 | Sunny | 33C | 107 | 8 | Ongoing: Painting First Coat at multiple zones. | 95.48% | None | Site_View_697.jpg | Deborah Kidd DVM | Eng. Abdullah (PM) | Timothy Garcia
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-698 | 2026-09-29 | Contractor | Consultant | Daily Report - Day 698 | Very Hot | 47C | 66 | 7 | Ongoing: Gypsum Ceiling at multiple zones. | 95.62% | None | Site_View_698.jpg | Pam Herrera | Eng. Abdullah (PM) | Gary Boyle
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-699 | 2026-09-30 | Contractor | Consultant | Daily Report - Day 699 | Very Hot | 44C | 94 | 5 | Ongoing: Ceramic Tiling at multiple zones. | 95.75% | None | Site_View_699.jpg | Herbert Norton Jr. | Eng. Abdullah (PM) | John Bartlett
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-700 | 2026-10-01 | Contractor | Consultant | Daily Report - Day 700 | Very Hot | 43C | 112 | 12 | Ongoing: Door Installation at multiple zones. | 95.89% | None | Site_View_700.jpg | Michael Collins | Eng. Abdullah (PM) | Gloria Thomas
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-702 | 2026-10-03 | Contractor | Consultant | Daily Report - Day 702 | Very Hot | 44C | 127 | 20 | Ongoing: Gypsum Ceiling at multiple zones. | 96.16% | None | Site_View_702.jpg | Jason Hanna | Eng. Abdullah (PM) | Dr. Lawrence Fletcher
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-703 | 2026-10-04 | Contractor | Consultant | Daily Report - Day 703 | Very Hot | 45C | 122 | 12 | Ongoing: Gypsum Ceiling at multiple zones. | 96.3% | None | Site_View_703.jpg | Tony Moody | Eng. Abdullah (PM) | Caroline Ross
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-704 | 2026-10-05 | Contractor | Consultant | Daily Report - Day 704 | Very Hot | 46C | 49 | 10 | Ongoing: Blockwork at multiple zones. | 96.44% | None | Site_View_704.jpg | Alexandra Lucas | Eng. Abdullah (PM) | Christopher Bryant
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-705 | 2026-10-06 | Contractor | Consultant | Daily Report - Day 705 | Very Hot | 44C | 117 | 6 | Ongoing: Plastering at multiple zones. | 96.58% | None | Site_View_705.jpg | Carla Morales | Eng. Abdullah (PM) | Joseph Morris
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-706 | 2026-10-07 | Contractor | Consultant | Daily Report - Day 706 | Sunny | 27C | 48 | 10 | Ongoing: Plastering at multiple zones. | 96.71% | None | Site_View_706.jpg | Shannon Frazier | Eng. Abdullah (PM) | Beverly Jones
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-707 | 2026-10-08 | Contractor | Consultant | Daily Report - Day 707 | Very Hot | 42C | 130 | 9 | Ongoing: Door Installation at multiple zones. | 96.85% | None | Site_View_707.jpg | Abigail Palmer | Eng. Abdullah (PM) | Derrick Brown
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-709 | 2026-10-10 | Contractor | Consultant | Daily Report - Day 709 | Very Hot | 46C | 41 | 20 | Ongoing: Gypsum Ceiling at multiple zones. | 97.12% | None | Site_View_709.jpg | Patricia Brown | Eng. Abdullah (PM) | Kimberly Mcdonald
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-710 | 2026-10-11 | Contractor | Consultant | Daily Report - Day 710 | Sunny | 31C | 132 | 10 | Ongoing: Painting First Coat at multiple zones. | 97.26% | None | Site_View_710.jpg | Steven Hughes | Eng. Abdullah (PM) | Miss Carrie Jones DDS
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-711 | 2026-10-12 | Contractor | Consultant | Daily Report - Day 711 | Very Hot | 40C | 49 | 14 | Ongoing: Painting First Coat at multiple zones. | 97.4% | None | Site_View_711.jpg | Patrick Crawford | Eng. Abdullah (PM) | Amy Jones
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-712 | 2026-10-13 | Contractor | Consultant | Daily Report - Day 712 | Sunny | 36C | 59 | 17 | Ongoing: Gypsum Ceiling at multiple zones. | 97.53% | Material Delay | Site_View_712.jpg | Dr. Jennifer Smith | Eng. Abdullah (PM) | Terry Garcia
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-713 | 2026-10-14 | Contractor | Consultant | Daily Report - Day 713 | Sunny | 32C | 60 | 6 | Ongoing: Painting First Coat at multiple zones. | 97.67% | None | Site_View_713.jpg | Stephen Contreras | Eng. Abdullah (PM) | Jennifer Garcia
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-714 | 2026-10-15 | Contractor | Consultant | Daily Report - Day 714 | Sunny | 26C | 122 | 12 | Ongoing: Ceramic Tiling at multiple zones. | 97.81% | None | Site_View_714.jpg | Kirk Tate | Eng. Abdullah (PM) | Benjamin Dougherty
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-716 | 2026-10-17 | Contractor | Consultant | Daily Report - Day 716 | Very Hot | 42C | 123 | 6 | Ongoing: Ceramic Tiling at multiple zones. | 98.08% | None | Site_View_716.jpg | Kimberly Hawkins | Eng. Abdullah (PM) | Julia Mueller
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-717 | 2026-10-18 | Contractor | Consultant | Daily Report - Day 717 | Very Hot | 47C | 140 | 12 | Ongoing: Ceramic Tiling at multiple zones. | 98.22% | Material Delay | Site_View_717.jpg | Stephen Curry | Eng. Abdullah (PM) | Sharon Martin DDS
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-718 | 2026-10-19 | Contractor | Consultant | Daily Report - Day 718 | Very Hot | 42C | 36 | 5 | Ongoing: Ceramic Tiling at multiple zones. | 98.36% | None | Site_View_718.jpg | Patricia Walker | Eng. Abdullah (PM) | Dennis Simon
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-719 | 2026-10-20 | Contractor | Consultant | Daily Report - Day 719 | Sunny | 38C | 102 | 18 | Ongoing: Plastering at multiple zones. | 98.49% | None | Site_View_719.jpg | Veronica Wells | Eng. Abdullah (PM) | Joseph Moore
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-720 | 2026-10-21 | Contractor | Consultant | Daily Report - Day 720 | Sunny | 29C | 88 | 16 | Ongoing: Ceramic Tiling at multiple zones. | 98.63% | None | Site_View_720.jpg | Ricky Turner | Eng. Abdullah (PM) | Gregory Martinez
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-721 | 2026-10-22 | Contractor | Consultant | Daily Report - Day 721 | Sunny | 21C | 68 | 17 | Ongoing: Gypsum Ceiling at multiple zones. | 98.77% | None | Site_View_721.jpg | Richard Sellers | Eng. Abdullah (PM) | Brandon Clay
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-723 | 2026-10-24 | Contractor | Consultant | Daily Report - Day 723 | Sunny | 37C | 111 | 9 | Ongoing: Painting First Coat at multiple zones. | 99.04% | None | Site_View_723.jpg | Thomas Navarro | Eng. Abdullah (PM) | David Huang
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-724 | 2026-10-25 | Contractor | Consultant | Daily Report - Day 724 | Sunny | 33C | 48 | 14 | Ongoing: Blockwork at multiple zones. | 99.18% | None | Site_View_724.jpg | Anthony Weaver | Eng. Abdullah (PM) | Lauren Ruiz
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-725 | 2026-10-26 | Contractor | Consultant | Daily Report - Day 725 | Sunny | 25C | 104 | 12 | Ongoing: Blockwork at multiple zones. | 99.32% | None | Site_View_725.jpg | Destiny Martinez | Eng. Abdullah (PM) | Jon Roberts
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-726 | 2026-10-27 | Contractor | Consultant | Daily Report - Day 726 | Very Hot | 45C | 119 | 5 | Ongoing: Door Installation at multiple zones. | 99.45% | None | Site_View_726.jpg | Michelle Nguyen | Eng. Abdullah (PM) | Alicia Powell
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-727 | 2026-10-28 | Contractor | Consultant | Daily Report - Day 727 | Sunny | 27C | 42 | 12 | Ongoing: Gypsum Ceiling at multiple zones. | 99.59% | None | Site_View_727.jpg | Heather Wise | Eng. Abdullah (PM) | John Ross
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-728 | 2026-10-29 | Contractor | Consultant | Daily Report - Day 728 | Sunny | 31C | 99 | 20 | Ongoing: Ceramic Tiling at multiple zones. | 99.73% | None | Site_View_728.jpg | Chad Mcclain | Eng. Abdullah (PM) | Elijah Bryan
Logos.png | Roshn Residential Community | Daily Site Report (DSR) | PRJ-BLD-ROSHN-09-DSR-730 | 2026-10-31 | Contractor | Consultant | Daily Report - Day 730 | Sunny | 27C | 132 | 19 | Ongoing: Plastering at multiple zones. | 100.0% | None | Site_View_730.jpg | Brian Moyer | Eng. Abdullah (PM) | Savannah Jackson