## Sheet1
شعارات المشروع (Logos) | اسم المشروع (Project Name) | عنوان المستند (Doc Title) | الرقم المرجعي (Ref. No) | تاريخ الإصدار (Date) | المرسل (From) | المستقبل (To) | الموضوع (Subject) | رقم المخطط (Dwg No) | رقم النسخة (Rev No) | عنوان المخطط (Title) | التخصص (Discipline) | المقياس (Scale) | سبب الإصدار (Reason) | الملف (Attachment) | تم الإنشاء (Prepared By) | المراجعة (Reviewed By) | الاعتماد (Consultant)
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-001 | 2025-05-04 | Contractor | Consultant | Details for Plastering | DWG-BUILD-001 | 02 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_1.pdf | Justin Taylor | Eng. Senior Design | Brian Miller
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-002 | 2025-06-10 | Contractor | Consultant | Details for Plastering | DWG-BUILD-002 | 00 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_2.pdf | Alan Rodriguez | Eng. Senior Design | Dominique Macdonald
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-003 | 2025-09-05 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-003 | 01 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_3.pdf | Samantha Parker | Eng. Senior Design | Shane Pena
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-004 | 2025-08-20 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-004 | 02 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_4.pdf | Rachel Barr | Eng. Senior Design | Haley Vasquez
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-005 | 2025-12-11 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-005 | 01 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_5.pdf | Jill Swanson | Eng. Senior Design | Russell Leonard
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-006 | 2025-08-10 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-006 | 02 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_6.pdf | Allen Little | Eng. Senior Design | Stephanie Martin
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-007 | 2026-10-21 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-007 | 00 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_7.pdf | Trevor Morris | Eng. Senior Design | Gregory Wall
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-008 | 2026-05-05 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-008 | 01 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_8.pdf | Matthew Chapman | Eng. Senior Design | Ryan King
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-009 | 2026-10-15 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-009 | 01 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_9.pdf | Robert Ray | Eng. Senior Design | Stephen Wilkinson
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-010 | 2024-11-22 | Contractor | Consultant | Details for Plastering | DWG-BUILD-010 | 01 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_10.pdf | Beth Arnold | Eng. Senior Design | Sharon Silva
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-011 | 2025-11-27 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-011 | 01 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_11.pdf | Aaron Richards | Eng. Senior Design | Elizabeth Reed
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-012 | 2026-10-06 | Contractor | Consultant | Details for Plastering | DWG-BUILD-012 | 02 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_12.pdf | Jackie Sanders | Eng. Senior Design | Cody Davis
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-013 | 2026-03-07 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-013 | 02 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_13.pdf | Lisa Nichols | Eng. Senior Design | George Lowe
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-014 | 2025-06-01 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-014 | 00 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_14.pdf | Michael Ward | Eng. Senior Design | Shannon Gibson
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-015 | 2026-06-25 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-015 | 02 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_15.pdf | Paul Rowe | Eng. Senior Design | Tracey Matthews
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-016 | 2026-04-07 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-016 | 01 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_16.pdf | April Zimmerman | Eng. Senior Design | Heather Chen
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-017 | 2025-02-11 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-017 | 00 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_17.pdf | Tonya Hayes | Eng. Senior Design | Omar Stevens
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-018 | 2026-06-05 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-018 | 01 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_18.pdf | Katrina Buchanan | Eng. Senior Design | Patricia Ross
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-019 | 2025-08-28 | Contractor | Consultant | Details for Plastering | DWG-BUILD-019 | 02 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_19.pdf | Pamela Lane | Eng. Senior Design | Mrs. Gabrielle Young
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-020 | 2026-03-20 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-020 | 01 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_20.pdf | Robin Olson | Eng. Senior Design | Sandra Buchanan
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-021 | 2025-11-15 | Contractor | Consultant | Details for Door Installation | DWG-BUILD-021 | 02 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_21.pdf | Ashley Winters | Eng. Senior Design | Elizabeth Hernandez
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-022 | 2025-09-04 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-022 | 00 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_22.pdf | Danielle Marshall | Eng. Senior Design | Adam Brown
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-023 | 2026-05-11 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-023 | 02 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_23.pdf | Michael Riley | Eng. Senior Design | Sue Lopez
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-024 | 2026-04-15 | Contractor | Consultant | Details for Door Installation | DWG-BUILD-024 | 02 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_24.pdf | Cynthia Barajas | Eng. Senior Design | Melissa Bishop
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-025 | 2025-12-28 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-025 | 02 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_25.pdf | Richard Shannon | Eng. Senior Design | Barbara Huff
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-026 | 2025-09-10 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-026 | 00 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_26.pdf | Heather Byrd | Eng. Senior Design | Carrie Walter
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-027 | 2024-12-31 | Contractor | Consultant | Details for Plastering | DWG-BUILD-027 | 01 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_27.pdf | David Brennan | Eng. Senior Design | Sharon Jones
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-028 | 2026-04-23 | Contractor | Consultant | Details for Plastering | DWG-BUILD-028 | 01 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_28.pdf | Brenda Harper | Eng. Senior Design | Henry Scott
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-029 | 2025-04-05 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-029 | 00 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_29.pdf | Andrew Rowe | Eng. Senior Design | Chad Jones
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-030 | 2024-11-02 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-030 | 02 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_30.pdf | Tiffany Galvan | Eng. Senior Design | Reginald Vincent
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-031 | 2025-05-17 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-031 | 01 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_31.pdf | John Woods | Eng. Senior Design | Lisa Lindsey
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-032 | 2024-11-22 | Contractor | Consultant | Details for Plastering | DWG-BUILD-032 | 00 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_32.pdf | Mr. Joshua Stephenson | Eng. Senior Design | Nicole Clark
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-033 | 2025-04-03 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-033 | 01 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_33.pdf | Robert Golden | Eng. Senior Design | Laura Salas
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-034 | 2025-07-05 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-034 | 02 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_34.pdf | Martha Price | Eng. Senior Design | Jeffrey Wood
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-035 | 2025-09-03 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-035 | 00 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_35.pdf | Debbie Smith | Eng. Senior Design | Misty Mcintyre
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-036 | 2025-07-14 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-036 | 00 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_36.pdf | Sharon Moore | Eng. Senior Design | Aaron Lee
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-037 | 2025-04-19 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-037 | 02 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_37.pdf | Sandra Gordon | Eng. Senior Design | Katelyn Smith
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-038 | 2026-07-12 | Contractor | Consultant | Details for Plastering | DWG-BUILD-038 | 01 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_38.pdf | Ryan Cole | Eng. Senior Design | Kayla Gonzalez
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-039 | 2025-10-15 | Contractor | Consultant | Details for Door Installation | DWG-BUILD-039 | 00 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_39.pdf | Carol Castillo | Eng. Senior Design | Angela Butler
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-040 | 2024-11-17 | Contractor | Consultant | Details for Door Installation | DWG-BUILD-040 | 01 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_40.pdf | Megan Murphy | Eng. Senior Design | Jose Duncan
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-041 | 2025-05-19 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-041 | 01 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_41.pdf | Bradley Wiggins | Eng. Senior Design | Michele Garrett
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-042 | 2026-08-22 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-042 | 02 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_42.pdf | Patricia Anderson DDS | Eng. Senior Design | Selena Todd
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-043 | 2025-08-01 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-043 | 01 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_43.pdf | Gregory Porter | Eng. Senior Design | Lawrence Anderson
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-044 | 2025-02-21 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-044 | 00 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_44.pdf | Jessica Meyers | Eng. Senior Design | Gerald Carrillo
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-045 | 2026-06-25 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-045 | 00 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_45.pdf | Matthew Roberts DDS | Eng. Senior Design | Christopher Ramos
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-046 | 2026-02-22 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-046 | 00 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_46.pdf | Becky Harvey | Eng. Senior Design | Timothy Kim
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-047 | 2026-04-12 | Contractor | Consultant | Details for Plastering | DWG-BUILD-047 | 00 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_47.pdf | Timothy Fleming | Eng. Senior Design | Michael Fox
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-048 | 2025-08-18 | Contractor | Consultant | Details for Plastering | DWG-BUILD-048 | 01 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_48.pdf | Alexandria Thompson | Eng. Senior Design | Tommy Jennings
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-049 | 2026-03-12 | Contractor | Consultant | Details for Plastering | DWG-BUILD-049 | 01 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_49.pdf | Brittany Holmes | Eng. Senior Design | Christopher Archer
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-050 | 2025-09-24 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-050 | 02 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_50.pdf | Cindy Perez | Eng. Senior Design | Kayla Wilkins
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-051 | 2025-05-21 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-051 | 00 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_51.pdf | Erin Jenkins | Eng. Senior Design | Brian Walsh
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-052 | 2025-10-18 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-052 | 01 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_52.pdf | Mathew Shelton | Eng. Senior Design | Michelle Wagner
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-053 | 2026-08-24 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-053 | 01 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_53.pdf | Wendy Hicks | Eng. Senior Design | Francis Oliver
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-054 | 2026-01-02 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-054 | 00 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_54.pdf | Sara Hardy | Eng. Senior Design | Bryan Donovan
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-055 | 2026-02-05 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-055 | 00 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_55.pdf | William Washington | Eng. Senior Design | Andrew Bass
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-056 | 2025-07-04 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-056 | 02 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_56.pdf | Jack Peterson | Eng. Senior Design | James Grimes
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-057 | 2024-11-15 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-057 | 00 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_57.pdf | Tiffany Scott | Eng. Senior Design | Shannon Morrow
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-058 | 2025-12-08 | Contractor | Consultant | Details for Door Installation | DWG-BUILD-058 | 01 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_58.pdf | Kelly Davis | Eng. Senior Design | Daniel Ho
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-059 | 2026-01-11 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-059 | 01 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_59.pdf | Lori Smith | Eng. Senior Design | Kathleen Maldonado
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-060 | 2026-04-12 | Contractor | Consultant | Details for Plastering | DWG-BUILD-060 | 00 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_60.pdf | Amanda Thomas | Eng. Senior Design | Kevin Kennedy
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-061 | 2025-02-03 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-061 | 00 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_61.pdf | Jennifer Washington | Eng. Senior Design | Bianca Taylor
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-062 | 2026-03-08 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-062 | 00 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_62.pdf | Kathryn Chavez | Eng. Senior Design | Mary Jackson
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-063 | 2024-11-27 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-063 | 01 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_63.pdf | Kimberly Thomas | Eng. Senior Design | Amy Gross
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-064 | 2025-08-08 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-064 | 02 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_64.pdf | Kayla Russo | Eng. Senior Design | Eric Glenn
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-065 | 2026-10-15 | Contractor | Consultant | Details for Plastering | DWG-BUILD-065 | 01 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_65.pdf | Tammy Smith | Eng. Senior Design | Tyler Williams
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-066 | 2025-11-17 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-066 | 02 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_66.pdf | Jesse Davis | Eng. Senior Design | Joseph Jarvis
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-067 | 2024-11-06 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-067 | 02 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_67.pdf | Derek Scott | Eng. Senior Design | Thomas Sherman
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-068 | 2026-10-15 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-068 | 00 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_68.pdf | Tanya Spencer | Eng. Senior Design | Dakota Walker
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-069 | 2026-01-02 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-069 | 02 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_69.pdf | David Black | Eng. Senior Design | Amy Casey
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-070 | 2025-12-20 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-070 | 02 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_70.pdf | Amanda Frost | Eng. Senior Design | Dr. Eric Blair
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-071 | 2025-07-26 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-071 | 00 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_71.pdf | Laura Nichols | Eng. Senior Design | Carlos Lopez
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-072 | 2025-11-23 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-072 | 01 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_72.pdf | Felicia Caldwell | Eng. Senior Design | Emily Ashley
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-073 | 2026-07-16 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-073 | 00 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_73.pdf | Carrie Mitchell | Eng. Senior Design | Brian Davis
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-074 | 2025-01-09 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-074 | 00 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_74.pdf | Jordan Green | Eng. Senior Design | Jacqueline Daniel
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-075 | 2026-09-19 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-075 | 01 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_75.pdf | Natalie Cole | Eng. Senior Design | Thomas Yang
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-076 | 2025-10-12 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-076 | 02 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_76.pdf | Emily Stevens | Eng. Senior Design | Elizabeth Moody
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-077 | 2026-05-28 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-077 | 00 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_77.pdf | Samantha Gray | Eng. Senior Design | John Sosa
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-078 | 2025-08-25 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-078 | 02 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_78.pdf | Elizabeth Foster | Eng. Senior Design | Natalie Bowers
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-079 | 2024-12-22 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-079 | 02 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_79.pdf | Johnny Fisher | Eng. Senior Design | Jerome Brooks
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-080 | 2026-07-28 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-080 | 02 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_80.pdf | Jacob Lee | Eng. Senior Design | Stephen Maxwell
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-081 | 2025-02-01 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-081 | 01 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_81.pdf | Edward Frederick | Eng. Senior Design | Mrs. Sarah Snyder
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-082 | 2026-08-31 | Contractor | Consultant | Details for Door Installation | DWG-BUILD-082 | 01 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_82.pdf | Raymond Parker | Eng. Senior Design | Jose Washington
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-083 | 2025-04-15 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-083 | 01 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_83.pdf | Donna Romero | Eng. Senior Design | Jordan King
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-084 | 2025-01-28 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-084 | 01 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_84.pdf | Gabriela Singleton | Eng. Senior Design | Marcus Watson
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-085 | 2026-05-15 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-085 | 01 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_85.pdf | Joshua Becker | Eng. Senior Design | Diane Williams
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-086 | 2025-07-13 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-086 | 02 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_86.pdf | Kenneth Thomas | Eng. Senior Design | Tyler Gilmore
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-087 | 2026-10-17 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-087 | 02 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_87.pdf | Rachel Hamilton | Eng. Senior Design | Cynthia Chapman
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-088 | 2025-10-20 | Contractor | Consultant | Details for Plastering | DWG-BUILD-088 | 02 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_88.pdf | Michael Sawyer | Eng. Senior Design | Jennifer Martinez
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-089 | 2026-09-30 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-089 | 02 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_89.pdf | James Hill | Eng. Senior Design | Joseph Hernandez
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-090 | 2025-10-18 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-090 | 02 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_90.pdf | Derek Garcia | Eng. Senior Design | Jacqueline Lara
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-091 | 2026-03-04 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-091 | 01 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_91.pdf | Ryan Garrett | Eng. Senior Design | Joseph Wilson
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-092 | 2026-04-02 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-092 | 02 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_92.pdf | Heather Cabrera | Eng. Senior Design | Patricia Farley
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-093 | 2026-08-11 | Contractor | Consultant | Details for Plastering | DWG-BUILD-093 | 02 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_93.pdf | Jacob Gray | Eng. Senior Design | Lisa Randall
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-094 | 2026-03-31 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-094 | 00 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_94.pdf | Jessica Lopez | Eng. Senior Design | Elijah Stafford
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-095 | 2026-01-02 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-095 | 00 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_95.pdf | Kenneth Williams | Eng. Senior Design | Peter Hawkins
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-096 | 2026-01-17 | Contractor | Consultant | Details for Plastering | DWG-BUILD-096 | 00 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_96.pdf | Joe Carrillo | Eng. Senior Design | Adrian Martin
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-097 | 2026-05-27 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-097 | 01 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_97.pdf | Andrea Mercado | Eng. Senior Design | Jonathan Rose
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-098 | 2026-03-24 | Contractor | Consultant | Details for Door Installation | DWG-BUILD-098 | 02 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_98.pdf | Christina Rice | Eng. Senior Design | Elizabeth Ortiz
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-099 | 2026-08-02 | Contractor | Consultant | Details for Door Installation | DWG-BUILD-099 | 01 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_99.pdf | Robin Andrews | Eng. Senior Design | Christina Chapman
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-100 | 2025-10-22 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-100 | 02 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_100.pdf | Jessica Romero | Eng. Senior Design | Laura Robinson
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-101 | 2026-07-12 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-101 | 01 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_101.pdf | Tara Gregory | Eng. Senior Design | Taylor Rodriguez
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-102 | 2025-06-16 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-102 | 00 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_102.pdf | Luke Sims | Eng. Senior Design | Chelsey Ayala
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-103 | 2026-04-25 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-103 | 00 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_103.pdf | Corey Valdez | Eng. Senior Design | Justin Jackson
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-104 | 2025-12-16 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-104 | 02 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_104.pdf | Kyle Lewis | Eng. Senior Design | Kylie Wong
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-105 | 2026-02-18 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-105 | 02 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_105.pdf | Matthew Medina | Eng. Senior Design | Jason Martin
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-106 | 2026-04-16 | Contractor | Consultant | Details for Door Installation | DWG-BUILD-106 | 02 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_106.pdf | Teresa Smith | Eng. Senior Design | Karen Willis
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-107 | 2025-03-09 | Contractor | Consultant | Details for Plastering | DWG-BUILD-107 | 01 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_107.pdf | Adriana Scott | Eng. Senior Design | Kenneth Mcgee
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-108 | 2025-07-31 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-108 | 01 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_108.pdf | Jack Nguyen | Eng. Senior Design | Scott Bishop
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-109 | 2025-12-11 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-109 | 00 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_109.pdf | Louis Allen | Eng. Senior Design | William Vargas
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-110 | 2025-05-14 | Contractor | Consultant | Details for Door Installation | DWG-BUILD-110 | 01 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_110.pdf | Catherine Martinez | Eng. Senior Design | Connie Freeman
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-111 | 2026-10-23 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-111 | 01 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_111.pdf | Dominic Hodge | Eng. Senior Design | Angela Robertson
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-112 | 2026-01-12 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-112 | 01 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_112.pdf | Jeffrey Paul | Eng. Senior Design | Nathan Spencer
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-113 | 2025-05-30 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-113 | 00 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_113.pdf | Debra Whitehead | Eng. Senior Design | Gwendolyn Jenkins
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-114 | 2025-04-11 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-114 | 01 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_114.pdf | David Smith | Eng. Senior Design | Evan Robbins
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-115 | 2026-04-02 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-115 | 00 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_115.pdf | Ann Carr | Eng. Senior Design | Gary Navarro
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-116 | 2025-02-17 | Contractor | Consultant | Details for Door Installation | DWG-BUILD-116 | 01 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_116.pdf | Henry Harris | Eng. Senior Design | Dr. Paul Wood
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-117 | 2026-01-15 | Contractor | Consultant | Details for Door Installation | DWG-BUILD-117 | 02 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_117.pdf | Christopher Peck | Eng. Senior Design | Alyssa Huff
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-118 | 2025-07-13 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-118 | 01 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_118.pdf | Jacqueline Rios | Eng. Senior Design | Crystal Williams
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-119 | 2025-03-29 | Contractor | Consultant | Details for Plastering | DWG-BUILD-119 | 00 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_119.pdf | Catherine White | Eng. Senior Design | Pamela Eaton
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-120 | 2025-06-12 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-120 | 02 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_120.pdf | Ryan Horn Jr. | Eng. Senior Design | Jasmin Adkins
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-121 | 2026-10-22 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-121 | 02 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_121.pdf | Rebecca Johnson | Eng. Senior Design | Steven Meyer
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-122 | 2025-12-14 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-122 | 00 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_122.pdf | Michael Miller | Eng. Senior Design | Gary Richardson
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-123 | 2024-12-22 | Contractor | Consultant | Details for Plastering | DWG-BUILD-123 | 02 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_123.pdf | Tracy Lopez | Eng. Senior Design | Elizabeth Wright
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-124 | 2025-02-21 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-124 | 02 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_124.pdf | Joseph Hicks | Eng. Senior Design | Jaclyn Page
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-125 | 2025-09-07 | Contractor | Consultant | Details for Plastering | DWG-BUILD-125 | 00 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_125.pdf | Benjamin Mora | Eng. Senior Design | David Bullock
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-126 | 2025-10-31 | Contractor | Consultant | Details for Plastering | DWG-BUILD-126 | 00 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_126.pdf | Angela Holmes | Eng. Senior Design | Shannon Good
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-127 | 2026-01-23 | Contractor | Consultant | Details for Door Installation | DWG-BUILD-127 | 02 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_127.pdf | Terry Kelly | Eng. Senior Design | Danielle Jackson
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-128 | 2025-03-19 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-128 | 02 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_128.pdf | Paula Hall | Eng. Senior Design | Justin Pruitt
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-129 | 2025-08-25 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-129 | 00 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_129.pdf | Rodney Fisher | Eng. Senior Design | Deborah Cobb
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-130 | 2024-11-17 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-130 | 02 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_130.pdf | Lance Jones | Eng. Senior Design | Bryan Moody
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-131 | 2025-11-05 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-131 | 02 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_131.pdf | Jacob Brown | Eng. Senior Design | Alfred Clark
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-132 | 2026-01-18 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-132 | 00 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_132.pdf | Brian Sanders | Eng. Senior Design | Elizabeth Thompson
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-133 | 2025-07-18 | Contractor | Consultant | Details for Plastering | DWG-BUILD-133 | 02 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_133.pdf | Joseph Norton | Eng. Senior Design | Christine Olson MD
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-134 | 2026-04-29 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-134 | 00 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_134.pdf | Aaron Delgado | Eng. Senior Design | Daniel Walker PhD
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-135 | 2025-06-07 | Contractor | Consultant | Details for Door Installation | DWG-BUILD-135 | 01 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_135.pdf | Michael Booth | Eng. Senior Design | Garrett Atkinson
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-136 | 2026-01-04 | Contractor | Consultant | Details for Door Installation | DWG-BUILD-136 | 02 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_136.pdf | Emily Stein | Eng. Senior Design | Eric Mcguire
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-137 | 2025-12-31 | Contractor | Consultant | Details for Door Installation | DWG-BUILD-137 | 00 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_137.pdf | Penny Vincent | Eng. Senior Design | Gregory Sullivan
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-138 | 2026-01-12 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-138 | 01 | Layout Plan - Zone 3 | BUILD | 1:100 | For Approval | DWG_138.pdf | Matthew Jackson | Eng. Senior Design | Isaiah Gonzalez
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-139 | 2026-10-31 | Contractor | Consultant | Details for Plastering | DWG-BUILD-139 | 02 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_139.pdf | Margaret Turner | Eng. Senior Design | Alan Tucker
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-140 | 2026-06-22 | Contractor | Consultant | Details for Plastering | DWG-BUILD-140 | 00 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_140.pdf | Taylor Hernandez | Eng. Senior Design | Robert Sanders
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-141 | 2026-04-16 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-141 | 01 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_141.pdf | Alisha French | Eng. Senior Design | Steven Brown
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-142 | 2026-06-17 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-142 | 02 | Layout Plan - Zone 1 | BUILD | 1:100 | For Approval | DWG_142.pdf | Alicia Brown | Eng. Senior Design | Connie Hamilton
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-143 | 2026-09-16 | Contractor | Consultant | Details for Plastering | DWG-BUILD-143 | 02 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_143.pdf | Ricky Nguyen | Eng. Senior Design | Kimberly King
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-144 | 2026-05-08 | Contractor | Consultant | Details for Door Installation | DWG-BUILD-144 | 00 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_144.pdf | Megan Patel | Eng. Senior Design | Stephen Garcia
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-145 | 2026-10-26 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-145 | 02 | Layout Plan - Zone 4 | BUILD | 1:100 | For Approval | DWG_145.pdf | Travis Barron | Eng. Senior Design | Chad Jackson
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-146 | 2025-02-13 | Contractor | Consultant | Details for Painting First Coat | DWG-BUILD-146 | 02 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_146.pdf | John Johnston | Eng. Senior Design | Christopher Adkins
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-147 | 2025-04-11 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-147 | 02 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_147.pdf | Felicia Flores | Eng. Senior Design | Aaron Harris
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-148 | 2026-04-14 | Contractor | Consultant | Details for Blockwork | DWG-BUILD-148 | 02 | Layout Plan - Zone 2 | BUILD | 1:100 | For Approval | DWG_148.pdf | Shelia Brown | Eng. Senior Design | Derrick Graham
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-149 | 2025-05-23 | Contractor | Consultant | Details for Ceramic Tiling | DWG-BUILD-149 | 01 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_149.pdf | Lisa Maldonado DDS | Eng. Senior Design | Brittany Lopez
Logos.png | Roshn Residential Community | Shop Drawing Submittal | PRJ-BLD-ROSHN-09-ENG-150 | 2025-03-29 | Contractor | Consultant | Details for Gypsum Ceiling | DWG-BUILD-150 | 01 | Layout Plan - Zone 5 | BUILD | 1:100 | For Approval | DWG_150.pdf | Brandon Butler | Eng. Senior Design | Vincent Chavez