## Sheet1
شعارات المشروع (Logos) | اسم المشروع (Project Name) | عنوان المستند (Doc Title) | الرقم المرجعي (Ref. No) | تاريخ الإصدار (Date) | المرسل (From) | المستقبل (To) | الموضوع (Subject) | رقم المخطط (Dwg No) | رقم النسخة (Rev No) | عنوان المخطط (Title) | التخصص (Discipline) | المقياس (Scale) | سبب الإصدار (Reason) | الملف (Attachment) | تم الإنشاء (Prepared By) | المراجعة (Reviewed By) | الاعتماد (Consultant)
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-001 | 2025-12-26 | Contractor | Consultant | Details for HV Cable Pulling | DWG-ELEC-001 | 02 | Layout Plan - Zone 2 | ELEC | 1:100 | For Approval | DWG_1.pdf | Cassandra Bell | Eng. Senior Design | Susan Martinez
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-002 | 2025-03-09 | Contractor | Consultant | Details for Transformer Installation | DWG-ELEC-002 | 02 | Layout Plan - Zone 3 | ELEC | 1:100 | For Approval | DWG_2.pdf | Dr. Christopher Charles | Eng. Senior Design | Eric Miller
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-003 | 2025-12-28 | Contractor | Consultant | Details for Grounding Grid | DWG-ELEC-003 | 02 | Layout Plan - Zone 2 | ELEC | 1:100 | For Approval | DWG_3.pdf | Crystal Jennings | Eng. Senior Design | Robert Wall
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-004 | 2025-09-05 | Contractor | Consultant | Details for HV Cable Pulling | DWG-ELEC-004 | 00 | Layout Plan - Zone 3 | ELEC | 1:100 | For Approval | DWG_4.pdf | Linda Lopez | Eng. Senior Design | Christopher Watkins
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-005 | 2026-02-04 | Contractor | Consultant | Details for HV Cable Pulling | DWG-ELEC-005 | 00 | Layout Plan - Zone 3 | ELEC | 1:100 | For Approval | DWG_5.pdf | Sarah Wilson DVM | Eng. Senior Design | Norma Lawson
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-006 | 2025-09-13 | Contractor | Consultant | Details for Fiber Splicing | DWG-ELEC-006 | 00 | Layout Plan - Zone 3 | ELEC | 1:100 | For Approval | DWG_6.pdf | Michael Sullivan | Eng. Senior Design | Michael Jones
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-007 | 2026-02-07 | Contractor | Consultant | Details for Grounding Grid | DWG-ELEC-007 | 02 | Layout Plan - Zone 5 | ELEC | 1:100 | For Approval | DWG_7.pdf | Bradley Garrison | Eng. Senior Design | Lauren Jones
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-008 | 2025-06-13 | Contractor | Consultant | Details for Switchgear Termination | DWG-ELEC-008 | 00 | Layout Plan - Zone 3 | ELEC | 1:100 | For Approval | DWG_8.pdf | Kathleen Frost | Eng. Senior Design | Lisa Villegas
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-009 | 2025-04-11 | Contractor | Consultant | Details for Switchgear Termination | DWG-ELEC-009 | 02 | Layout Plan - Zone 2 | ELEC | 1:100 | For Approval | DWG_9.pdf | Susan Williams | Eng. Senior Design | Tracy Dunn MD
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-010 | 2026-02-13 | Contractor | Consultant | Details for Switchgear Termination | DWG-ELEC-010 | 01 | Layout Plan - Zone 1 | ELEC | 1:100 | For Approval | DWG_10.pdf | George Johnson | Eng. Senior Design | Carol Kennedy
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-011 | 2026-01-24 | Contractor | Consultant | Details for Switchgear Termination | DWG-ELEC-011 | 00 | Layout Plan - Zone 2 | ELEC | 1:100 | For Approval | DWG_11.pdf | Wendy Jennings | Eng. Senior Design | Rhonda Vargas
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-012 | 2025-07-21 | Contractor | Consultant | Details for Switchgear Termination | DWG-ELEC-012 | 02 | Layout Plan - Zone 2 | ELEC | 1:100 | For Approval | DWG_12.pdf | Michelle Garza | Eng. Senior Design | Shannon Sims
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-013 | 2025-06-24 | Contractor | Consultant | Details for Grounding Grid | DWG-ELEC-013 | 01 | Layout Plan - Zone 5 | ELEC | 1:100 | For Approval | DWG_13.pdf | Jason Macias | Eng. Senior Design | Richard Jackson
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-014 | 2025-11-07 | Contractor | Consultant | Details for Transformer Installation | DWG-ELEC-014 | 00 | Layout Plan - Zone 4 | ELEC | 1:100 | For Approval | DWG_14.pdf | Mrs. Valerie Klein | Eng. Senior Design | Ryan Hess II
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-015 | 2025-10-12 | Contractor | Consultant | Details for Grounding Grid | DWG-ELEC-015 | 01 | Layout Plan - Zone 4 | ELEC | 1:100 | For Approval | DWG_15.pdf | Jamie Reeves | Eng. Senior Design | Charles Hoffman
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-016 | 2025-04-23 | Contractor | Consultant | Details for Grounding Grid | DWG-ELEC-016 | 01 | Layout Plan - Zone 4 | ELEC | 1:100 | For Approval | DWG_16.pdf | Thomas Sanchez | Eng. Senior Design | Bonnie Mitchell
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-017 | 2025-07-09 | Contractor | Consultant | Details for Grounding Grid | DWG-ELEC-017 | 00 | Layout Plan - Zone 3 | ELEC | 1:100 | For Approval | DWG_17.pdf | Katrina Davis | Eng. Senior Design | Rachel Hall
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-018 | 2025-07-10 | Contractor | Consultant | Details for Fiber Splicing | DWG-ELEC-018 | 01 | Layout Plan - Zone 3 | ELEC | 1:100 | For Approval | DWG_18.pdf | Casey Carey | Eng. Senior Design | Nicole Best
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-019 | 2025-11-16 | Contractor | Consultant | Details for Grounding Grid | DWG-ELEC-019 | 00 | Layout Plan - Zone 2 | ELEC | 1:100 | For Approval | DWG_19.pdf | Tabitha Pearson | Eng. Senior Design | Cameron Jones
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-020 | 2025-08-24 | Contractor | Consultant | Details for Fiber Splicing | DWG-ELEC-020 | 01 | Layout Plan - Zone 4 | ELEC | 1:100 | For Approval | DWG_20.pdf | Anthony Kelly | Eng. Senior Design | Erica Burton
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-021 | 2025-06-06 | Contractor | Consultant | Details for Grounding Grid | DWG-ELEC-021 | 01 | Layout Plan - Zone 2 | ELEC | 1:100 | For Approval | DWG_21.pdf | Matthew Hawkins | Eng. Senior Design | Jennifer Torres
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-022 | 2025-10-26 | Contractor | Consultant | Details for Transformer Installation | DWG-ELEC-022 | 01 | Layout Plan - Zone 1 | ELEC | 1:100 | For Approval | DWG_22.pdf | Kirsten Hubbard | Eng. Senior Design | Sabrina Mcmillan
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-023 | 2026-02-02 | Contractor | Consultant | Details for HV Cable Pulling | DWG-ELEC-023 | 00 | Layout Plan - Zone 4 | ELEC | 1:100 | For Approval | DWG_23.pdf | Matthew Dean | Eng. Senior Design | Brandon Adams
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-024 | 2025-09-14 | Contractor | Consultant | Details for Switchgear Termination | DWG-ELEC-024 | 01 | Layout Plan - Zone 1 | ELEC | 1:100 | For Approval | DWG_24.pdf | Kiara George | Eng. Senior Design | Adam Thomas
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-025 | 2025-08-21 | Contractor | Consultant | Details for Switchgear Termination | DWG-ELEC-025 | 00 | Layout Plan - Zone 5 | ELEC | 1:100 | For Approval | DWG_25.pdf | Elizabeth Cole | Eng. Senior Design | Nicholas Garcia
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-026 | 2025-04-23 | Contractor | Consultant | Details for HV Cable Pulling | DWG-ELEC-026 | 01 | Layout Plan - Zone 4 | ELEC | 1:100 | For Approval | DWG_26.pdf | Brandon Lucas | Eng. Senior Design | Patrick Bass
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-027 | 2025-09-04 | Contractor | Consultant | Details for Grounding Grid | DWG-ELEC-027 | 00 | Layout Plan - Zone 2 | ELEC | 1:100 | For Approval | DWG_27.pdf | Brett Smith | Eng. Senior Design | Hannah Hess
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-028 | 2025-03-01 | Contractor | Consultant | Details for HV Cable Pulling | DWG-ELEC-028 | 02 | Layout Plan - Zone 4 | ELEC | 1:100 | For Approval | DWG_28.pdf | Lori Allen | Eng. Senior Design | Justin Baldwin
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-029 | 2025-11-18 | Contractor | Consultant | Details for Grounding Grid | DWG-ELEC-029 | 01 | Layout Plan - Zone 2 | ELEC | 1:100 | For Approval | DWG_29.pdf | Joshua Sandoval | Eng. Senior Design | Jonathan Turner
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-030 | 2025-07-04 | Contractor | Consultant | Details for HV Cable Pulling | DWG-ELEC-030 | 02 | Layout Plan - Zone 4 | ELEC | 1:100 | For Approval | DWG_30.pdf | Mrs. Ann Villanueva | Eng. Senior Design | Michael Mitchell
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-031 | 2025-05-05 | Contractor | Consultant | Details for Transformer Installation | DWG-ELEC-031 | 02 | Layout Plan - Zone 5 | ELEC | 1:100 | For Approval | DWG_31.pdf | Susan Nguyen | Eng. Senior Design | Mr. John Anderson
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-032 | 2025-09-07 | Contractor | Consultant | Details for HV Cable Pulling | DWG-ELEC-032 | 00 | Layout Plan - Zone 1 | ELEC | 1:100 | For Approval | DWG_32.pdf | Derrick Meyers | Eng. Senior Design | Kiara Thomas
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-033 | 2025-10-26 | Contractor | Consultant | Details for Switchgear Termination | DWG-ELEC-033 | 01 | Layout Plan - Zone 4 | ELEC | 1:100 | For Approval | DWG_33.pdf | Elizabeth Castro | Eng. Senior Design | Mark Nolan
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-034 | 2025-11-30 | Contractor | Consultant | Details for HV Cable Pulling | DWG-ELEC-034 | 00 | Layout Plan - Zone 1 | ELEC | 1:100 | For Approval | DWG_34.pdf | Henry Moore | Eng. Senior Design | David Thompson
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-035 | 2025-10-01 | Contractor | Consultant | Details for Grounding Grid | DWG-ELEC-035 | 00 | Layout Plan - Zone 3 | ELEC | 1:100 | For Approval | DWG_35.pdf | Dean Mcintosh | Eng. Senior Design | Thomas Brown
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-036 | 2025-10-18 | Contractor | Consultant | Details for Grounding Grid | DWG-ELEC-036 | 02 | Layout Plan - Zone 1 | ELEC | 1:100 | For Approval | DWG_36.pdf | Jacqueline Gomez | Eng. Senior Design | William Robertson
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-037 | 2026-02-04 | Contractor | Consultant | Details for Grounding Grid | DWG-ELEC-037 | 02 | Layout Plan - Zone 1 | ELEC | 1:100 | For Approval | DWG_37.pdf | Michael Bruce | Eng. Senior Design | Whitney Stark
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-038 | 2025-07-10 | Contractor | Consultant | Details for Transformer Installation | DWG-ELEC-038 | 00 | Layout Plan - Zone 5 | ELEC | 1:100 | For Approval | DWG_38.pdf | Holly Simpson | Eng. Senior Design | Dr. Ashley Riley
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-039 | 2026-02-11 | Contractor | Consultant | Details for Transformer Installation | DWG-ELEC-039 | 02 | Layout Plan - Zone 2 | ELEC | 1:100 | For Approval | DWG_39.pdf | Rodney King | Eng. Senior Design | Sean Lopez
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-040 | 2025-06-20 | Contractor | Consultant | Details for Transformer Installation | DWG-ELEC-040 | 02 | Layout Plan - Zone 4 | ELEC | 1:100 | For Approval | DWG_40.pdf | Lindsay Silva | Eng. Senior Design | Sonya Nolan
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-041 | 2025-09-13 | Contractor | Consultant | Details for Transformer Installation | DWG-ELEC-041 | 00 | Layout Plan - Zone 5 | ELEC | 1:100 | For Approval | DWG_41.pdf | James Garcia | Eng. Senior Design | Curtis Golden
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-042 | 2025-04-16 | Contractor | Consultant | Details for HV Cable Pulling | DWG-ELEC-042 | 01 | Layout Plan - Zone 4 | ELEC | 1:100 | For Approval | DWG_42.pdf | Mathew Camacho | Eng. Senior Design | Melissa Robinson
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-043 | 2025-07-15 | Contractor | Consultant | Details for Grounding Grid | DWG-ELEC-043 | 02 | Layout Plan - Zone 5 | ELEC | 1:100 | For Approval | DWG_43.pdf | Brenda Thomas | Eng. Senior Design | Elizabeth Gilbert
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-044 | 2025-08-02 | Contractor | Consultant | Details for Fiber Splicing | DWG-ELEC-044 | 00 | Layout Plan - Zone 1 | ELEC | 1:100 | For Approval | DWG_44.pdf | Kimberly Daniel | Eng. Senior Design | John Lewis
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-045 | 2026-02-15 | Contractor | Consultant | Details for Grounding Grid | DWG-ELEC-045 | 00 | Layout Plan - Zone 5 | ELEC | 1:100 | For Approval | DWG_45.pdf | Terry Atkinson | Eng. Senior Design | Margaret Harvey
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-046 | 2025-04-25 | Contractor | Consultant | Details for Transformer Installation | DWG-ELEC-046 | 00 | Layout Plan - Zone 2 | ELEC | 1:100 | For Approval | DWG_46.pdf | Christopher Green | Eng. Senior Design | Jennifer Espinoza
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-047 | 2026-02-03 | Contractor | Consultant | Details for HV Cable Pulling | DWG-ELEC-047 | 00 | Layout Plan - Zone 1 | ELEC | 1:100 | For Approval | DWG_47.pdf | Jason Nash | Eng. Senior Design | Steven Howard
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-048 | 2025-04-19 | Contractor | Consultant | Details for Grounding Grid | DWG-ELEC-048 | 02 | Layout Plan - Zone 3 | ELEC | 1:100 | For Approval | DWG_48.pdf | Jesus Wilson | Eng. Senior Design | Sharon Diaz
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-049 | 2025-03-11 | Contractor | Consultant | Details for Grounding Grid | DWG-ELEC-049 | 00 | Layout Plan - Zone 1 | ELEC | 1:100 | For Approval | DWG_49.pdf | Jose Brady | Eng. Senior Design | Julie Hartman
Logos.png | SEC Grid Expansion Project | Shop Drawing Submittal | PRJ-ELEC-SEC-05-ENG-050 | 2026-01-13 | Contractor | Consultant | Details for Fiber Splicing | DWG-ELEC-050 | 00 | Layout Plan - Zone 5 | ELEC | 1:100 | For Approval | DWG_50.pdf | Mindy Bowen | Eng. Senior Design | Martin Shannon