## Sheet1
شعارات المشروع (Logos) | اسم المشروع (Project Name) | عنوان المستند (Doc Title) | الرقم المرجعي (Ref. No) | تاريخ الإصدار (Date) | المرسل (From) | المستقبل (To) | الموضوع (Subject) | رقم المخطط (Dwg No) | رقم النسخة (Rev No) | عنوان المخطط (Title) | التخصص (Discipline) | المقياس (Scale) | سبب الإصدار (Reason) | الملف (Attachment) | تم الإنشاء (Prepared By) | المراجعة (Reviewed By) | الاعتماد (Consultant)
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-001 | 2025-03-19 | Contractor | Consultant | Details for Manhole Installation | DWG-INFRA-001 | 00 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_1.pdf | James Howard | Eng. Senior Design | Courtney Todd
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-002 | 2025-07-11 | Contractor | Consultant | Details for Manhole Installation | DWG-INFRA-002 | 00 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_2.pdf | Matthew Wilson | Eng. Senior Design | Brian Banks
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-003 | 2025-09-12 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-003 | 01 | Layout Plan - Zone 2 | INFRA | 1:100 | For Approval | DWG_3.pdf | Brittany Novak | Eng. Senior Design | Paul Cochran
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-004 | 2026-06-24 | Contractor | Consultant | Details for Sub-base Compaction | DWG-INFRA-004 | 02 | Layout Plan - Zone 5 | INFRA | 1:100 | For Approval | DWG_4.pdf | Lawrence Evans | Eng. Senior Design | Heather Colon
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-005 | 2025-04-16 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-005 | 01 | Layout Plan - Zone 5 | INFRA | 1:100 | For Approval | DWG_5.pdf | Kayla Simmons | Eng. Senior Design | Jessica Lewis
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-006 | 2025-05-15 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-006 | 02 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_6.pdf | Robert Watson | Eng. Senior Design | Allen Walker
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-007 | 2026-01-08 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-007 | 02 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_7.pdf | Laura Taylor | Eng. Senior Design | Robert Frost
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-008 | 2026-02-06 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-008 | 00 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_8.pdf | Kimberly Cook | Eng. Senior Design | William Lowery MD
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-009 | 2025-06-24 | Contractor | Consultant | Details for Pipe Laying 600mm | DWG-INFRA-009 | 02 | Layout Plan - Zone 4 | INFRA | 1:100 | For Approval | DWG_9.pdf | Shawn Beasley | Eng. Senior Design | Mr. Matthew Anderson Jr.
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-010 | 2025-07-27 | Contractor | Consultant | Details for Manhole Installation | DWG-INFRA-010 | 00 | Layout Plan - Zone 5 | INFRA | 1:100 | For Approval | DWG_10.pdf | John Benitez IV | Eng. Senior Design | Monica Greer
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-011 | 2026-06-17 | Contractor | Consultant | Details for Manhole Installation | DWG-INFRA-011 | 01 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_11.pdf | Lisa Roberson | Eng. Senior Design | Michael Peck
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-012 | 2026-06-13 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-012 | 02 | Layout Plan - Zone 4 | INFRA | 1:100 | For Approval | DWG_12.pdf | Lydia Jarvis | Eng. Senior Design | Kimberly Peterson
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-013 | 2026-06-13 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-013 | 01 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_13.pdf | Hannah Lowery | Eng. Senior Design | Jamie Parker
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-014 | 2025-08-31 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-014 | 01 | Layout Plan - Zone 4 | INFRA | 1:100 | For Approval | DWG_14.pdf | Shelia Alexander | Eng. Senior Design | Deborah Wolfe
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-015 | 2026-06-07 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-015 | 00 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_15.pdf | Katherine Walker | Eng. Senior Design | Aaron Chaney
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-016 | 2025-08-28 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-016 | 02 | Layout Plan - Zone 5 | INFRA | 1:100 | For Approval | DWG_16.pdf | Brittany Cantu | Eng. Senior Design | Crystal Jackson
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-017 | 2026-06-23 | Contractor | Consultant | Details for Pipe Laying 600mm | DWG-INFRA-017 | 02 | Layout Plan - Zone 5 | INFRA | 1:100 | For Approval | DWG_17.pdf | Nathan Smith | Eng. Senior Design | Heather Johnson
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-018 | 2026-02-18 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-018 | 02 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_18.pdf | Fernando Garcia | Eng. Senior Design | Maria Stanton
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-019 | 2026-03-18 | Contractor | Consultant | Details for Sub-base Compaction | DWG-INFRA-019 | 02 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_19.pdf | John Stanton | Eng. Senior Design | Samantha Blevins
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-020 | 2025-06-14 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-020 | 02 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_20.pdf | Heather Hunt | Eng. Senior Design | Kimberly Gonzales
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-021 | 2025-07-29 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-021 | 00 | Layout Plan - Zone 2 | INFRA | 1:100 | For Approval | DWG_21.pdf | Jesse Macias | Eng. Senior Design | Debbie Harmon
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-022 | 2025-09-10 | Contractor | Consultant | Details for Manhole Installation | DWG-INFRA-022 | 00 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_22.pdf | Gloria Horne | Eng. Senior Design | Tammy Walsh
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-023 | 2025-05-19 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-023 | 01 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_23.pdf | Diane Jones | Eng. Senior Design | Morgan Williams
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-024 | 2026-03-30 | Contractor | Consultant | Details for Manhole Installation | DWG-INFRA-024 | 01 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_24.pdf | Sara Robbins DDS | Eng. Senior Design | Rachel Johnson
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-025 | 2026-04-18 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-025 | 00 | Layout Plan - Zone 2 | INFRA | 1:100 | For Approval | DWG_25.pdf | Mary Butler | Eng. Senior Design | Amber Hale
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-026 | 2026-03-01 | Contractor | Consultant | Details for Manhole Installation | DWG-INFRA-026 | 02 | Layout Plan - Zone 4 | INFRA | 1:100 | For Approval | DWG_26.pdf | Cody Tate | Eng. Senior Design | Christina Rowe
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-027 | 2026-01-24 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-027 | 02 | Layout Plan - Zone 4 | INFRA | 1:100 | For Approval | DWG_27.pdf | Christopher Bradley | Eng. Senior Design | Courtney Garrett
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-028 | 2026-06-21 | Contractor | Consultant | Details for Pipe Laying 600mm | DWG-INFRA-028 | 02 | Layout Plan - Zone 2 | INFRA | 1:100 | For Approval | DWG_28.pdf | Jerry Peterson | Eng. Senior Design | Andre Roberts
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-029 | 2025-05-08 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-029 | 00 | Layout Plan - Zone 2 | INFRA | 1:100 | For Approval | DWG_29.pdf | Michael Walker | Eng. Senior Design | Aaron Gray
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-030 | 2025-09-17 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-030 | 01 | Layout Plan - Zone 5 | INFRA | 1:100 | For Approval | DWG_30.pdf | Johnny Harmon | Eng. Senior Design | David Keller
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-031 | 2025-06-26 | Contractor | Consultant | Details for Pipe Laying 600mm | DWG-INFRA-031 | 01 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_31.pdf | Andrea Chaney | Eng. Senior Design | Nathan Fox
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-032 | 2025-07-16 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-032 | 00 | Layout Plan - Zone 4 | INFRA | 1:100 | For Approval | DWG_32.pdf | Tara Myers | Eng. Senior Design | Lisa Daniels
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-033 | 2026-05-23 | Contractor | Consultant | Details for Pipe Laying 600mm | DWG-INFRA-033 | 02 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_33.pdf | Elijah Ward | Eng. Senior Design | Janet Eaton
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-034 | 2025-07-10 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-034 | 01 | Layout Plan - Zone 4 | INFRA | 1:100 | For Approval | DWG_34.pdf | Mary Jones | Eng. Senior Design | Martha Campbell
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-035 | 2025-05-18 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-035 | 01 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_35.pdf | Jeremy Silva | Eng. Senior Design | Andrew Bell
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-036 | 2025-08-14 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-036 | 00 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_36.pdf | James Martin | Eng. Senior Design | Jason Andrade
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-037 | 2025-04-29 | Contractor | Consultant | Details for Pipe Laying 600mm | DWG-INFRA-037 | 02 | Layout Plan - Zone 2 | INFRA | 1:100 | For Approval | DWG_37.pdf | Nicholas Lewis | Eng. Senior Design | Matthew Guerrero
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-038 | 2026-05-23 | Contractor | Consultant | Details for Sub-base Compaction | DWG-INFRA-038 | 01 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_38.pdf | Adam Smith | Eng. Senior Design | Steven Morales
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-039 | 2025-10-27 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-039 | 01 | Layout Plan - Zone 2 | INFRA | 1:100 | For Approval | DWG_39.pdf | Mark Brewer | Eng. Senior Design | Kristin Nelson
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-040 | 2025-03-10 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-040 | 00 | Layout Plan - Zone 2 | INFRA | 1:100 | For Approval | DWG_40.pdf | Amanda Willis | Eng. Senior Design | Kyle Harris
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-041 | 2025-09-18 | Contractor | Consultant | Details for Pipe Laying 600mm | DWG-INFRA-041 | 02 | Layout Plan - Zone 4 | INFRA | 1:100 | For Approval | DWG_41.pdf | Billy Coleman | Eng. Senior Design | Susan Jones
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-042 | 2025-09-26 | Contractor | Consultant | Details for Pipe Laying 600mm | DWG-INFRA-042 | 02 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_42.pdf | Garrett Wilson | Eng. Senior Design | David Ford
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-043 | 2025-09-11 | Contractor | Consultant | Details for Manhole Installation | DWG-INFRA-043 | 01 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_43.pdf | David Peterson | Eng. Senior Design | Alyssa Miller
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-044 | 2025-10-13 | Contractor | Consultant | Details for Sub-base Compaction | DWG-INFRA-044 | 02 | Layout Plan - Zone 4 | INFRA | 1:100 | For Approval | DWG_44.pdf | Nicole Ward | Eng. Senior Design | Alan Griffin
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-045 | 2025-05-12 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-045 | 01 | Layout Plan - Zone 4 | INFRA | 1:100 | For Approval | DWG_45.pdf | Crystal Gomez | Eng. Senior Design | Heidi Wright
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-046 | 2025-01-31 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-046 | 00 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_46.pdf | Cassandra Morales | Eng. Senior Design | Aaron Sanchez
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-047 | 2025-11-06 | Contractor | Consultant | Details for Pipe Laying 600mm | DWG-INFRA-047 | 01 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_47.pdf | Craig Duarte | Eng. Senior Design | Danny Petersen
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-048 | 2025-11-09 | Contractor | Consultant | Details for Manhole Installation | DWG-INFRA-048 | 00 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_48.pdf | Sharon Hull | Eng. Senior Design | Brian Rich
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-049 | 2025-06-05 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-049 | 01 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_49.pdf | Shawn Foley | Eng. Senior Design | Brooke Chapman
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-050 | 2025-01-29 | Contractor | Consultant | Details for Manhole Installation | DWG-INFRA-050 | 00 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_50.pdf | Emily Brown | Eng. Senior Design | Kathleen Lloyd
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-051 | 2025-06-24 | Contractor | Consultant | Details for Sub-base Compaction | DWG-INFRA-051 | 02 | Layout Plan - Zone 4 | INFRA | 1:100 | For Approval | DWG_51.pdf | Gary Moreno | Eng. Senior Design | Steven Eaton
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-052 | 2025-08-30 | Contractor | Consultant | Details for Pipe Laying 600mm | DWG-INFRA-052 | 02 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_52.pdf | William Martinez | Eng. Senior Design | Steven Bishop
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-053 | 2026-05-30 | Contractor | Consultant | Details for Pipe Laying 600mm | DWG-INFRA-053 | 01 | Layout Plan - Zone 4 | INFRA | 1:100 | For Approval | DWG_53.pdf | Christina Gay | Eng. Senior Design | Margaret Castaneda
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-054 | 2025-07-30 | Contractor | Consultant | Details for Manhole Installation | DWG-INFRA-054 | 01 | Layout Plan - Zone 5 | INFRA | 1:100 | For Approval | DWG_54.pdf | Emma Norman | Eng. Senior Design | Rebecca Saunders
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-055 | 2026-02-15 | Contractor | Consultant | Details for Sub-base Compaction | DWG-INFRA-055 | 00 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_55.pdf | Crystal Jackson | Eng. Senior Design | Tony Moore
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-056 | 2025-08-26 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-056 | 02 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_56.pdf | Debra Sherman | Eng. Senior Design | Jordan Rodriguez
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-057 | 2025-08-10 | Contractor | Consultant | Details for Pipe Laying 600mm | DWG-INFRA-057 | 02 | Layout Plan - Zone 2 | INFRA | 1:100 | For Approval | DWG_57.pdf | Megan Ortiz | Eng. Senior Design | Jeffery Lee
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-058 | 2025-10-12 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-058 | 00 | Layout Plan - Zone 5 | INFRA | 1:100 | For Approval | DWG_58.pdf | Anthony Sanchez | Eng. Senior Design | Jacob Shaw
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-059 | 2025-03-26 | Contractor | Consultant | Details for Manhole Installation | DWG-INFRA-059 | 02 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_59.pdf | April Austin | Eng. Senior Design | Brenda Lewis
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-060 | 2025-08-11 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-060 | 02 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_60.pdf | Sherry Osborne | Eng. Senior Design | Matthew Smith
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-061 | 2026-02-16 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-061 | 02 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_61.pdf | Kristi Combs | Eng. Senior Design | Danielle Carter
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-062 | 2026-06-11 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-062 | 00 | Layout Plan - Zone 5 | INFRA | 1:100 | For Approval | DWG_62.pdf | Lisa Ortiz | Eng. Senior Design | Mr. Michael Roberson
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-063 | 2025-11-27 | Contractor | Consultant | Details for Sub-base Compaction | DWG-INFRA-063 | 02 | Layout Plan - Zone 5 | INFRA | 1:100 | For Approval | DWG_63.pdf | Mary Gomez | Eng. Senior Design | Alexis Williams
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-064 | 2026-01-27 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-064 | 01 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_64.pdf | Aaron Holland | Eng. Senior Design | William Woods
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-065 | 2025-04-07 | Contractor | Consultant | Details for Sub-base Compaction | DWG-INFRA-065 | 02 | Layout Plan - Zone 5 | INFRA | 1:100 | For Approval | DWG_65.pdf | Christopher Moreno | Eng. Senior Design | Thomas Phillips
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-066 | 2025-10-11 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-066 | 02 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_66.pdf | Rhonda Hicks | Eng. Senior Design | Thomas Bradley
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-067 | 2026-05-30 | Contractor | Consultant | Details for Sub-base Compaction | DWG-INFRA-067 | 02 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_67.pdf | William Saunders | Eng. Senior Design | Emily Gonzalez
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-068 | 2025-06-15 | Contractor | Consultant | Details for Pipe Laying 600mm | DWG-INFRA-068 | 01 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_68.pdf | Aaron Kemp | Eng. Senior Design | Steven Jordan
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-069 | 2025-02-13 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-069 | 02 | Layout Plan - Zone 2 | INFRA | 1:100 | For Approval | DWG_69.pdf | Jeffrey Hill | Eng. Senior Design | Karen Shields
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-070 | 2025-05-13 | Contractor | Consultant | Details for Pipe Laying 600mm | DWG-INFRA-070 | 00 | Layout Plan - Zone 2 | INFRA | 1:100 | For Approval | DWG_70.pdf | David Robinson | Eng. Senior Design | David Lopez
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-071 | 2026-03-24 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-071 | 00 | Layout Plan - Zone 4 | INFRA | 1:100 | For Approval | DWG_71.pdf | Joseph Powell | Eng. Senior Design | Latasha Porter
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-072 | 2026-03-29 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-072 | 00 | Layout Plan - Zone 2 | INFRA | 1:100 | For Approval | DWG_72.pdf | Kristin Howard DDS | Eng. Senior Design | Sharon Taylor
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-073 | 2025-04-02 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-073 | 02 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_73.pdf | Keith Kaufman | Eng. Senior Design | Amber Anderson
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-074 | 2025-04-21 | Contractor | Consultant | Details for Manhole Installation | DWG-INFRA-074 | 01 | Layout Plan - Zone 2 | INFRA | 1:100 | For Approval | DWG_74.pdf | Patricia Rodriguez | Eng. Senior Design | Christina Reilly
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-075 | 2025-12-16 | Contractor | Consultant | Details for Asphalt Laying | DWG-INFRA-075 | 01 | Layout Plan - Zone 4 | INFRA | 1:100 | For Approval | DWG_75.pdf | Anna Strickland | Eng. Senior Design | Joyce Cabrera
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-076 | 2025-09-15 | Contractor | Consultant | Details for Excavation Works | DWG-INFRA-076 | 01 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_76.pdf | Kelsey Cox | Eng. Senior Design | Amber Bowers
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-077 | 2025-05-24 | Contractor | Consultant | Details for Pipe Laying 600mm | DWG-INFRA-077 | 01 | Layout Plan - Zone 4 | INFRA | 1:100 | For Approval | DWG_77.pdf | Christopher Roth | Eng. Senior Design | Laura Graham
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-078 | 2025-05-03 | Contractor | Consultant | Details for Sub-base Compaction | DWG-INFRA-078 | 00 | Layout Plan - Zone 4 | INFRA | 1:100 | For Approval | DWG_78.pdf | Sarah Andrews | Eng. Senior Design | Benjamin Cruz
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-079 | 2025-06-08 | Contractor | Consultant | Details for Manhole Installation | DWG-INFRA-079 | 01 | Layout Plan - Zone 3 | INFRA | 1:100 | For Approval | DWG_79.pdf | Randy Hughes | Eng. Senior Design | Nicole Contreras
Logos.png | Al-Arid Infrastructure Project | Shop Drawing Submittal | PRJ-INF-2025-01-ENG-080 | 2025-07-10 | Contractor | Consultant | Details for Manhole Installation | DWG-INFRA-080 | 01 | Layout Plan - Zone 1 | INFRA | 1:100 | For Approval | DWG_80.pdf | Kevin Hernandez | Eng. Senior Design | William Macdonald